## HVAC
M/S Director Development
NASTP PAF Faisal Karachi | [9 empty] | 21 Oct 2023
NTN 4312149-7
Request for Release of Payment
1 | Supply of Additional 6" Pipe |  | 160 Rft
2 | Supply of Additional 4" Pipe |  | 460 Rft
3 | Supply of Additional 1" Pipe |  | 140 Rft
M/S Pioneer has completed 100% work at site as per contract.
A
Bill for Installation of HVAC System at 'ZONE B' NASTP KARACHI
S. # | Description | Unit | Qty in contract | Qty Work done | Work done % | Material Rate | Labour Rate | Material Amount | Labour Amount | Total Amount Work Done
Machine Made G.I Sheet metal Duct
1 | Supply, Installation, testing & Commissioning of medium/low Machine made pressure G.I. sheet metal ducting complete in all respect. | Sqft | 9500 | 9500 | 100% | 350 | 60 | 3325000 | 570000 | 3895000
Fierglass insulation
2 | Supply and installation of 1 inch thick Fiber Glass Insulation of density 24 kg/m3 with Aluminum Foil, tape, Canvas Cloth & anti funguspaint complete in all respect. | Sqft | 9500 | 9500 | 100% | 160 | 55 | 1520000 | 522500 | 2042500 | 215
Air devices
3 | Supply & Installation of Supply air diffuser. 15 x 15 | Nos | 124 | 124 | 100% | 5500 | 800 | 682000 | 99200 | 781200
4 | Supply & Installation of Exhaust Air Register. | [6 empty] | 0 | 0 | 0
i | 09 x 09 | Nos | 39 | 39 | 100% | 2200 | 1000 | 85800 | 39000 | 124800
ii | 12 x 12 | Nos | 22 | 18 | 100% | 3500 | 1000 | 63000 | 18000 | 81000
5 | Supply and installation of Exhaust Air Louver as per drawings.
i | 28 x 12 | No | 2 | 2 | 100% | 7500 | 900 | 15000 | 1800 | 16800
ii | 30 x 12 | No | 2 | 2 | 100% | 9000 | 900 | 18000 | 1800 | 19800
6 | Supply and installation of volume control damper
i | 38 x 16 | Nos | 7 | 7 | 100% | 14500 | 1000 | 101500 | 7000 | 108500
ii | 32 x 14 | Nos | 4 | 4 | 100% | 10750 | 1000 | 43000 | 4000 | 47000
7 | Supply and installation of Fire Damper
i | 38 x 16 | Nos | 7 | 7 | 100% | 14500 | 1000 | 101500 | 7000 | 108500
ii | 32 x 14 | Nos | 4 | 4 | 100% | 11800 | 1000 | 47200 | 4000 | 51200
8 | Supply and installation of access door for fire / split damper. Size 18 x 18 | Nos | 11 | 11 | 100% | 8000 | 1000 | 88000 | 11000 | 99000
9 | Supply and installation of flexbile duct connector for supply air duct only. | Rft | 200 | 200 | 100% | 650 | 80 | 130000 | 16000 | 146000
S. # | Description | Unit | Qty in contract | Qty Work done | Work done % | Material Rate | Labour Rate | Material Amount | Labour Amount | Total Amount
M.S SCH-40 Pipe and related material
10 | Providing and installation of temporary scaffolding for installation of chilled water riser (after completion of work removal of folding) | Job | 1 | 1 | 100% | 200000 | 75000 | 200000 | 75000 | 275000
11 | Installation of M.S Sch-40 Seamless chilled water pipe with comsumable material such as cutting discs, grinding disc, electrodes etc
i | 6" dia | Rft | 350 | 350 | 100% | 0 | 575 | 0 | 201250 | 201250
ii | 4" dia | Rft | 130 | 130 | 100% | 0 | 475 | 0 | 61750 | 61750
iii | 3" dia | Rft | 160 | 160 | 100% | 0 | 425 | 0 | 68000 | 68000
iv | 2-1/2" dia | Rft | 240 | 240 | 100% | 0 | 375 | 0 | 90000 | 90000
v | 2" dia | Rft | 400 | 400 | 100% | 0 | 325 | 0 | 130000 | 130000
vi | 1-1/2" dia | Rft | 200 | 200 | 100% | 0 | 275 | 0 | 55000 | 55000
vii | 1-1/4" dia | Rft | 320 | 320 | 100% | 0 | 250 | 0 | 80000 | 80000
viii | 1" dia | Rft | 180 | 180 | 100% | 0 | 225 | 0 | 40500 | 40500
ix | 3/4" dia | Rft | 200 | 200 | 100% | 0 | 175 | 0 | 35000 | 35000
12 | Providing and making of chilled water connection from main plant room for supply and return. | Job | 1 | 1 | 100% | 15000 | 20000 | 15000 | 20000 | 35000
13 | Supply and installation of related fittings for M.S SCH-40 Pipe fittings such as tee, elbow, reduser, gasket, nut washer etc. | Job | 1 | 1 | 100% | 400000 | 80000 | 400000 | 80000 | 480000
Premolded PU Insulation
14 | Supply and Intallation of premolded PU insulation over chilled water piping with 26 SWG G.I sheet metal cladding, kraft paper, canvas cloth etc complete in all respect.
Thickness 2"
i | 6" dia | Rft | 350 | 350 | 100% | 2580 | 285 | 903000 | 99750 | 1002750
ii | 4" dia | Rft | 130 | 130 | 100% | 2080 | 255 | 270400 | 33150 | 303550
iii | 3" dia | Rft | 160 | 160 | 100% | 1730 | 235 | 276800 | 37600 | 314400
iv | 2-1/2" dia | Rft | 240 | 240 | 100% | 1700 | 230 | 408000 | 55200 | 463200
v | 2" dia | Rft | 400 | 400 | 100% | 1250 | 225 | 500000 | 90000 | 590000
Thickness 1-1/2"
i | 1-1/2" dia | Rft | 200 | 200 | 100% | 1125 | 215 | 225000 | 43000 | 268000
ii | 1-1/4" dia | Rft | 320 | 320 | 100% | 980 | 200 | 313600 | 64000 | 377600
iii | 1" dia | Rft | 180 | 180 | 100% | 975 | 180 | 175500 | 32400 | 207900
iv | 3/4" dia | Rft | 200 | 200 | 100% | 700 | 170 | 140000 | 34000 | 174000
15 | Supply and installation of condensate drain with insulation.
i | 2" dia | Rft | 240 | 240 | 100% | 300 | 98 | 72000 | 23520 | 95520
ii | 1-1/2" dia | Rft | 220 | 220 | 100% | 220 | 70 | 48400 | 15400 | 63800
iii | 1" dia | Rft | 360 | 360 | 100% | 190 | 50 | 68400 | 18000 | 86400
16 | Supply and installation of Hanger & supports for chilled water piping. | Job | 1 | 1 | 100% | 300000 | 75000 | 300000 | 75000 | 375000
17 | Supply and installation of red oxide Paint on pipes. | Job | 1 | 1 | 100% | 70000 | 38000 | 70000 | 38000 | 108000 |  |  | 17930 | 13618780
18 | Removal of electrical cable trays | Job | 1 | 1 | 100% | 0 | 80000 | 0 | 80000 | 80000
Total Amount of Table A Rs | [9 empty] | 13600850 |  | 4435160 | 18036010
B
S. # | Description |  |  | Unit | Qty in contract | Qty Work done | Work done % | Rate | Billed Qty | Amount
Machine Made G.I Sheet metal Duct
1 | Supply, Installation, testing & Commissioning of medium/low Machine made pressure G.I. sheet metal ducting complete in all respect. |  |  | Sqft | 9500 |  |  | #REF! |  | #REF!
Fierglass insulation
2 | Supply and installation of 1 inch thick Fiber Glass Insulation of density 24 kg/m3 with Aluminum Foil, tape, Canvas Cloth & anti funguspaint complete in all respect. |  |  | Sqft | 9500 |  |  | #REF! |  | #REF!
Air devices
3 | Supply & Installation of Supply air diffuser. 15 x 15 |  |  | Nos | 124 |  |  | #REF! |  | #REF!
4 | Supply & Installation of Exhaust Air Register. | [6 empty] | #REF! |  | #REF!
i | 09 x 09 |  |  | Nos | 39 |  |  | #REF! |  | #REF!
ii | 12 x 12 |  |  | Nos | 22 |  |  | #REF! |  | #REF!
5 | Supply and installation of Exhaust Air Louver as per drawings.
i | 28 x 12 |  |  | No | 2 |  |  | #REF! |  | #REF!
ii | 30 x 12 |  |  | No | 2 |  |  | #REF! |  | #REF!
6 | Supply and installation of volume control damper
i | 38 x 16 |  |  | Nos | 7 |  |  | #REF! |  | #REF!
ii | 32 x 14 |  |  | Nos | 4 |  |  | #REF! |  | #REF!
7 | Supply and installation of Fire Damper
i | 38 x 16 |  |  | Nos | 7 |  |  | #REF! |  | #REF!
ii | 32 x 14 |  |  | Nos | 4 |  |  | #REF! |  | #REF!
8 | Supply and installation of access door for fire / split damper. Size 18 x 18 |  |  | Nos | 11 |  |  | #REF! |  | #REF!
9 | Supply and installation of flexbile duct connector for supply air duct only. |  |  | Rft | 200 |  |  | #REF! |  | #REF!
M.S SCH-40 Pipe and related material
10 | Providing and installation of temporary scaffolding for installation of chilled water riser (after completion of work removal of folding) |  |  | Job | 1 |  |  | #REF! |  | #REF!
iv | 2-1/2" dia |  |  | Rft | 650 |  |  | #REF! |  | #REF!
v | 2" dia |  |  | Rft | 400 |  |  | #REF! |  | #REF!
vi | 1-1/2" dia |  |  | Rft | 200 |  |  | #REF! |  | #REF!
vii | 1-1/4" dia |  |  | Rft | 320 |  |  | #REF! |  | #REF!
viii | 1" dia |  |  | Rft | 180 |  |  | #REF! |  | #REF!
ix | 3/4" dia |  |  | Rft | 200 |  |  | #REF! |  | #REF!
12 | Providing and making of chilled water connection from main plant room for supply and return. |  |  | Job | 1 |  |  | #REF! |  | #REF!
13 | Supply and installation of related fittings for M.S SCH-40 Pipe fittings such as tee, elbow, reduser, gasket, nut washer etc. |  |  | Job | 1 |  |  | #REF! |  | #REF!
Premolded PU Insulation
1 | MS pipe 6” Sch-40 SMLS |  |  | Rft | 160 | 160 | 100% | 5105 | 160 | 816800
2 | MS pipe 4” Sch-40 SMLS |  |  | Rft | 460 | 460 | 100% | 2605 | 460 | 1198300
3 | MS pipe 1” Sch-40 SMLS |  |  | Rft | 140 | 140 | 100% | 523 | 140 | 73220
4 | Installation of MS pipe 6” Sch-40 SMLS |  |  | Rft | 160 | 160 | 100% | 575 | 160 | 92000
5 | Installation of MS pipe 4” Sch-40 SMLS |  |  | Rft | 460 | 460 | 100% | 475 | 460 | 218500
6 | Supply & Installation of pre-molded PU insulation of 2” thickness density 50 kg/m3 for chilled water piping, bends, tees, unions, sockets, valves and on special, wrapped with 8 oz canvas cloth than painted with anti fugus paint with 26 SWG G.I sheet complete in all respect on 6” pipe |  |  | Rft | 160 | 160 | 100% | 2865 | 160 | 458400
7 | Supply & Installation of pre-molded PU insulation of 2” thickness density 50 kg/m3 for chilled water piping, bends, tees, unions, sockets, valves and on special, wrapped with 8 oz canvas cloth than painted with anti fugus paint with 26 SWG G.I sheet complete in all respect on 4” pipe |  |  | Rft | 460 | 460 | 100% | 2335 | 460 | 1074100
8 | Installation of Gate Valves With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc |  |  | Each | 44 | 44 | 100% | 4000 | 44 | 176000
9 | Installation of CFRV Valves With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc |  |  | Each | 22 | 22 | 100% | 4000 | 22 | 88000
10 | Installation of Motorized Valves With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc |  |  | Each | 13 | 13 | 100% | 4000 | 13 | 52000
11 | Installation of Strainers With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc |  |  | Each | 22 | 22 | 100% | 4000 | 22 | 88000
12 | Installation of Thermometer with syphon and High-Pressure Sockets |  |  | Each | 26 | 26 | 100% | 1920 | 26 | 49920
13 | Installation of Pressure Gauges with Gauge Cock and High-Pressure Sockets |  |  | Each | 26 | 26 | 100% | 1920 | 26 | 49920 |  |  | 21887922.07 |  | 21887922
Total Amount of Table B Rs | [9 empty] | 4435160 |  | 18036010
C
S.# | Description |  |  |  | Unit | Qty Increased | Qty work done | Work done % | Rate | Total Amount Work Done
1 | Ducting |  |  |  | SFT | 6403.86 | 6403.86 | 100% | 410 | 2625582.6
2 | Insulation |  |  |  | SFT | 5703.858 | 5703.858 | 100% | 215 | 1226329.47
* | TOTAL
3 | Piping | [7 empty] | 2352 RFT | 80%
Total Amount of Table C Rs | [9 empty] | 3851912.07
Grand Total Amount of Table A+ B + C | [9 empty] | 21887922.07 |  | 35488772.07 |  | 18036010
Total Received Amount Rs | [9 empty] | 17855650 |  | 31456500 |  | 180360.1
Payable Amount Rs | [9 empty] | 4032272.07 |  | 17633122.07 |  | 17855649.9
It is requested that Rs 4,032,272/= may please be released.
For PIONEER SERVICES
25739834.14
PIONEER SERVICES