## Fire
M/S Dawat-e-Hadiyah Burhani Mahal |  |  |  | Date | 2023-09-18
Mciver Road, Karachi |  |  |  | Invoice # | 322
|  |  |  | NTN # | 4312149-7
Invoice
Installation of Fire Fighting Material for Food Court - The North Walk Shopping Mall
S. # | Description | Unit | Qty | Labour Rate | Labour Amount
1 | Installation of ASTM A53 & A120 Schedule 40 MS piping with fittings & specials for fire protection system, including all cutting, fixing, laying through walls & roofs and making good complete in all respect as per drawings and specifications.
i | 25 mm (1 inch) Diameter | Rft | 126 | 150 | 18900
ii | 32 mm (1-1/4 inch) Diameter | Rft | 92 | 200 | 18400
iii | 38 mm (1-1/2 inch) Diameter | Rft | 140 | 225 | 31500
iv | 50 mm (2 inch) Diameter | Rft | 120 | 250 | 30000
2 | Installation of Gate Valve 1-1/4" dia | Nos | 8 | 1000 | 8000
3 | Installation of Fire hose cabinet (Single door, surface mounted type, complete mild steel) | Nos | 2 | 5000 | 10000
4 | Installation of (UL/FM) upright sprinkler | Nos | 24 | 500 | 12000
5 | Installation of Painting | Job | 1 | 20000 | 20000
6 | Installation of hangers & supports. | Job | 1 | 20000 | 20000
7 | Installation of Strainer 1" Dia | Nos | 2 | 1000 | 2000
8 | Installation of Ball Valve 1" Dia | Nos | 2 | 1000 | 2000
9 | Installation of PRV " Dia | Nos | 2 | 1000 | 2000
10 | Re location of Gate Valve 1-1/4" dia | Nos | 5 | 1000 | 5000
11 | Re location of M.S Pipe 2-1/2" dia | Rft | 24 | 350 | 8400
12 | Re location of M.S Pipe 2" dia | Rft | 68 | 250 | 17000
13 | Re location of M.S Pipe 1-1/4" dia | Rft | 22 | 200 | 4400
14 | Re location of M.S Pipe 1" dia | Rft | 18 | 150 | 2700
Total Amount Rs |  |  |  |  | 212300
SST Tax 13% |  |  |  |  | 27599
Total Amount Rs |  |  |  |  | 239899
For PIONEER SERVICES.
PIONEER SERVICES