## HVAC
M/S Dawat-e-Hadiyah Burhani Mahal |  |  |  |  | Date |  | 2023-06-22
Mciver Road, Karachi |  |  |  |  | Invoice # |  | 322
[5 empty] | NTN # |  | 4312149-7
Invoice
EXTRA / Additional work - The North Walk Shopping Mall
S. # | Description | Unit | Qty | Material Rate | Labor Rate | Material Amount | Labor Amount
1 | Removal of solar plates for installation of package unit, supply air duct an return air ducts and kept at basement as instructed. | Nos | 42 | 0 | 1000 | 0 | 42000
2 | Making of Openings CC walls & sandwich walls for supply return and exhaust air ducts including repairing. | Job | 1 | 0 | 10000 | 0 | 10000
3 | Water proofing of openings of supply and return air ducts including roof channels | Job | 1 | 0 | 15000 | 0 | 15000
4 | Aluminium made cable tray supply / install for re connection of solat panels including connection coupler | Job | 1 | 15000 | 15000 | 15000 | 15000
5 | Removal of M.S Checker plate platform for installation of supply / return air duct abd re installation of removed checker plate M.S frames. | Job | 1 | 0 | 40000 | 0 | 40000
6 | Supply and installation of angle iron checker plate for platform at roof. | Sqft | 80 | 700 | 200 | 56000 | 16000
7 | Painting of 02 coat primer then 2 coat epoxy as recommended and instruction received. | Job | 1 | 30000 | 20000 | 30000 | 20000
Sub- Total Amount Rs | [5 empty] | 101000 | 158000
SST Tax 13% | [5 empty] | 0 | 20540
Total Amount Rs | [5 empty] | 101000 | 178540
Grand Total Amount Rs | [5 empty] | 279730
For PIONEER SERVICES.
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
PIONEER SERVICES

## working
|  |  | Discount | 4.811%
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
Discount | 88065.0403 | 18198.9538
Sub Total Amount | 1742534.9597 | 360101.0462
SRB 13% on Labour | 0 | 46813.136
Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
SRB 13% on Labour | 0 | 49179
Total Amount | 1830600 | 427479
Discount | 88065.0403 | 20564.8177
Grand Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419