## SUMM
STANDARD CHARTERED BANK
S.NO | SUMMARY OF COST | Material | Labour | Deal Done
1 | HVAC (Ground Floor) | 4187248.267 | 890159.894 | 5077408.161
2 | HVAC (Mezz Floor) | 3793596.751 | 829598.263 | 4623195.014
3 | Variation amount (04 Nos) |  |  | 1119473.2
| Total Amount |  |  | 10820076.375

## Ground Floor
Bill of Quantities
ACMV Works
Standard Chartered Bank (Head Office) | [10 empty] | Rev.02
Ground Floor, Karachi. | [10 empty] | Date: 29-05-2023
[5 empty] | Material | Labour | Running Bill No 1
S. No. |  | Description | Unit | Qty | Rate | Rate | Bill Qty | Material Amount | Bill Qty | Labour Amount | Amount
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | GF-AC-01 | Nos. | 2 | 15378 | 8202 | 1 | 15378 | 1 | 8202 | 23580
| 1.2 | GF-AC-02 | Nos. | 2 | 15378 | 8202 | 0 | 0 | 0 | 0 | 0
| 1.3 | GF-AC-03 | No. | 1 | 18453 | 8202 | 2 | 36906 | 2 | 16404 | 53310
| 1.4 | GF-AC-04 | Nos. | 4 | 20504 | 10252 | 4 | 82016 | 4 | 41008 | 123024
| 1.5 | GF-CSU-01 | Nos. | 4 | 15378 | 8202 | 1 | 15378 | 1 | 8202 | 23580
| 1.6 | GF-CSU-02 | Nos. | 3 | 18453 | 8202 | 6 | 110718 | 6 | 49212 | 159930
| 1.7 | GF-FAHU-01 | No. | 1 | 35882 | 15378 | 1 | 35882 | 1 | 15378 | 51260
2 |  | Supply & installation of refrigerant pipes (liquid + gas) with 12mm thick expended rubber foam insulation, PVC tape wrapping + control wiring in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 2.1 | GF-AC-01 (Soft Pipes) | Rm | 30 | 4685 | 923 | 28.962 | 135686.97 | 28.962 | 26731.926 | 162418.896
| 2.2 | GF-AC-02 (Soft Pipes) | Rm | 42 | 4798 | 974 | 0 | 0 | 0 | 0 | 0
| 2.3 | GF-AC-03 (Soft Pipes) | Rm | 10 | 5490 | 1025 | 45.471 | 249635.79 | 45.471 | 46607.775 | 296243.565
| 2.4 | GF-AC-04 (Hard Pipes) | Rm | 125 | 7094 | 1051 | 196.29 | 1392481.26 | 196.29 | 206300.79 | 1598782.05
| 2.5 | GF-CSU-01 (Soft Pipes) | Rm | 90 | 4798 | 974 | 28.235 | 135471.53 | 28.235 | 27500.89 | 162972.42
| 2.6 | GF-CSU-02 (Soft Pipes) | Rm | 65 | 5490 | 1025 | 162.462 | 891916.38 | 162.462 | 166523.55 | 1058439.93
| 2.7 | GF-FAHU-01 (Hard Pipes) | Rm | 20 | 11513 | 2307 | 47.979 | 552382.227 | 47.979 | 110687.553 | 663069.78
3 |  | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 10 | 6766 | 677 | 5.48 | 37077.68 | 5.48 | 3709.96 | 40787.64
4 |  | Supply & installation of SCH-40 uPVC make class D pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 4.1 | 25mm dia | Rm | 165 | 1487 | 359 | 111.14 | 165265.18 | 111.14 | 39899.26 | 205164.44
| 4.2 | 32mm dia | Rm | 25 | 2025 | 359 | 36.41 | 73730.25 | 36.41 | 13071.19 | 86801.44
| 4.3 | 40mm dia | Rm | 5 | 2819 | 410 |  | 0 | 0 | 0 | 0
| 4.4 | 50mm dia | Rm | 10 | 3383 | 461 |  | 0 | 0 | 0 | 0
5 |  | Supply & installation of air curtains including, supports, electrical connection etc, complete in all respects ready to operate as per drawings, specification & as per instruction of consultant. | [5 empty] | 0 | 0 | 0 | 0
| 5.1 | 1.5m Length | Nos. | 2 | 98418 | 3076 | 1 | 98418 | 1 | 3076 | 101494
6 |  | Supply & installation of ventilation fans as per mentioned in schedule, including vibration isolator, flexible duct connection / connector, power wiring from isolation box to unit (4 to 5 meter radius), support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
| 6.1 | GF-EAF-01 (with uPVC Pipe & Fittings) | Nos. | 2 | 43058 | 3076 |  | 0 | 0 | 0 | 0
| 6.2 | GF-EAF-02 | No. | 1 | 63562 | 3076 |  | 0 | 0 | 0 | 0
| 6.3 | GF-EAF-03 | No. | 1 | 74839 | 3076 |  | 0 | 0 | 0 | 0
7 |  | Supply, fabrication and installation of pre-insulated ductwork of polyurethane foam panel with 52 Kg/m3 density, 20 mm thickness, coated on both sides with 80 micron thick aluminum foil complete with a 2 g/m2 layer for internal duct work including manufacturer's aluminum hardware glue, Hot Dipped galvanized hangers and supports, flexible duct connection, wooden frame, etc. Complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | Sqm | 40 | 6971 | 769 |  | 0 | 0 | 0 | 0
8 |  | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 8.1 | 100mm dia | Nos. | 2 | 5126 | 1025 |  | 0 | 0 | 0 | 0
| 8.2 | 200mm x 200mm | Nos. | 2 | 5126 | 1025 |  | 0 | 0 | 0 | 0
| 8.3 | 600mm x 200mm | No. | 1 | 9739 | 2050 |  | 0 | 0 | 0 | 0
9 |  | Supply & installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 9.1 | Supply & Return Air Grills / Registers
| i. | 1400mm x 150mm | No. | 1 | 13327 | 2050 |  | 0 | 0 | 0 | 0
| 9.2 | Exhaust Air Disc Valves
| i. | 150mm dia | Nos. | 10 | 3076 | 1025 |  | 0 | 0 | 0 | 0
10 |  | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 10.1 | 200mm x 100mm | No. | 1 | 3076 | 1025 |  | 0 | 0 | 0 | 0
| 10.2 | 200mm x 150mm | No. | 1 | 3281 | 1025 |  | 0 | 0 | 0 | 0
11 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Lot | 1 | 46134 | 15378 | 1 | 46134 | 1 | 15378 | 61512
12 |  | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 92267 | 71763 | 1 | 92267 | 1 | 71763 | 164030
13 |  | Making of Shop drawings on Auto CAD latest version with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Job. | 1 | 20504 | 20504 | 1 | 20504 | 1 | 20504 | 41008
|  | Total Cost of Works Rs. | [5 empty] | 4187248.267 |  | 890159.894 | 5077408.161
Cost of Owner Supplied VRF Units (Gree, China) Rs.
|  | Total Cost of Project | [8 empty] | 5077408.161
Note:
1) | Electric power wiring / supply to be provided at outdoor, indoor units & other HVAC equipment with isolation box by electrical contractor.
2) | The refrigerant pipes sized + quantity provided for reference only. The contractor / supplier shall calculate the refrigerant pipes, sized & length as per the drawing provided and shall submitted refrigerant piping layout to consultant for approval.
3) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
4) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## Mezz Floor
Bill of Quantities
ACMV Works
Standard Chartered Bank (Head Office) | [10 empty] | Rev.03
Mezzanine Floor, Karachi. | [10 empty] | Date: 03-07-2023
[5 empty] | Material | Labour | Running Bill No 1
S. No. |  | Description | Unit | Qty | Rate | Rate | Bill Qty | Material Amount | Bill Qty | Labour Amount | Amount
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | MF-AC-01 | Nos. | 5 | 15378 | 8202 | 4 | 61512 | 4 | 32808 | 94320
| 1.2 | MF-AC-02 | No. | 2 | 15378 | 8202 | 2 | 30756 | 2 | 16404 | 47160
| 1.3 | GF-CSU-01 | Nos. | 3 | 15378 | 8202 | 3 | 46134 | 3 | 24606 | 70740
| 1.4 | GF-CSU-02 | Nos. | 8 | 18453 | 8202 | 8 | 147624 | 8 | 65616 | 213240
2 |  | Supply & installation of refrigerant pipes (liquid + gas) with 12mm thick expended rubber foam insulation, PVC tape wrapping + control wiring in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 2.1 | GF-AC-01 (Soft Pipes) | Rm | 120 | 4685 | 923 | 159.03 | 745055.55 | 159.03 | 146784.69 | 891840.24
| 2.2 | GF-AC-02 (Soft Pipes) | Rm | 50 | 4798 | 974 | 81.582 | 391430.436 | 81.582 | 79460.868 | 470891.304
| 2.3 | GF-CSU-01 (Soft Pipes) | Rm | 70 | 4798 | 974 | 103.18 | 495057.64 | 103.18 | 100497.32 | 595554.96
| 2.4 | GF-CSU-02 (Soft Pipes) | Rm | 220 | 5490 | 1025 | 262.26 | 1439807.4 | 262.26 | 268816.5 | 1708623.9
3 |  | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 15 | 15890 | 769 | 9.07 | 144122.3 | 9.07 | 6974.83 | 151097.13
4 |  | Supply & installation of SCH-40 uPVC make class D pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 4.1 | 25mm dia | Rm | 130 | 1487 | 359 | 94.9 | 141116.3 | 94.9 | 34069.1 | 175185.4
| 4.2 | 32mm dia | Rm | 30 | 2025 | 359 | 49.245 | 99721.125 | 49.245 | 17678.955 | 117400.08
5 |  | Supply & installation of ventilation fans as per mentioned in schedule, including vibration isolator, flexible duct connection / connector, power wiring from isolation box to unit (4 to 5 meter radius), support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
| 5.1 | MZ-EAF-01 (with uPVC Pipe & Fittings) | No. | 1 | 49209 | 3076 |  | 0 | 0 | 0 | 0
6 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Lot | 1 | 35882 | 15378 | 1 | 35882 | 1 | 15378 | 51260
7 |  | Making of Shop drawings on Auto CAD latest version with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Job. | 1 | 15378 | 20504 | 1 | 15378 | 1 | 20504 | 35882
|  | Total Cost of Works Rs. | [5 empty] | 3793596.751 |  | 829598.263 | 4623195.014
Cost of Owner Supplied VRF Units (Gree, China) Rs.
|  | Total Cost of Project | [8 empty] | 4623195.014
Note:
1) | Electric power wiring / supply to be provided at outdoor, indoor units & other HVAC equipment with isolation box by electrical contractor.
2) | The refrigerant pipes sized + quantity provided for reference only. The contractor / supplier shall calculate the refrigerant pipes, sized & length as per the drawing provided and shall submitted refrigerant piping layout to consultant for approval.
3) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
4) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## Variation
Dated: | 2023-10-25
Project: | Construction of Standard Chartered bank at I.I Chundrigar Road karachi.
Variation No 3
Revised Rate Analysis for MS Cable Tray
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Supply of MS cable tray 6mm thickness size of 12''x 6'' | Sqft | 1 |  | 1 | 1750 | 1750
0
0
| Total. | [5 empty] | 1750 | 1750
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Installation of Ms cable tray including Ms sheet 6mm thickness bending and welding. | Sqft | 1 |  | 1 | 450 | 450
0
| Total. | [5 empty] | 450 | 2200
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | Sqft | 198 |  | 198 | 2200 | 435600 | 437800
| Total Rs. | [6 empty] | 437800
Sub-Contractor Margin: |  |  | 25% |  |  |  |  | 109450
Total Price | [7 empty] | 547250
Dated: | 2023-10-25
Project: | Construction of Standard Chartered bank at I.I Chundrigar Road karachi.
Variation No 4
Rate Analysis for Core Cutting
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Core Cutting dia of 4'' length=3' | Nos | 14 |  | 14 | 7500 | 105000
0
0
| Total. | [5 empty] | 105000 | 105000
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Core Cutting Removel of debris and cleaning . | Nos | 14 |  | 14 | 150 | 2100
0
| Total. | [5 empty] | 2100 | 107100
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [6 empty] | 107100
| Total Rs. | [6 empty] | 107100
Sub-Contractor Margin: |  |  | 25% |  |  |  |  | 26775
Total Price | [7 empty] | 133875
Dated: | 2023-11-03
Project: | Construction of Standard Chartered bank at I.I Chundrigar Road karachi.
Rate Analysis of Channel support For Outdoor unit plateform
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Supply of MS C-Channel support size of 3''x 1 1/2''. | Rft | 250 |  | 250 | 600 | 150000
2 | Supply of MS Angle iron support size of 2''x 2'' . | Rft | 126 |  | 126 | 308.56 | 38878.56
3 | Providing of Paint | Nos | 1 |  | 1 | 30000 | 30000
| Total. | [5 empty] | 218878.56 | 218878.56
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Installation of MS C-Channel support size of 3''x 1 1/2''. | Rft | 250 |  | 250 | 120 | 30000
2 | Installation of MS Angle iron support size of 2''x 2'' . | Rft | 126 |  | 126 | 100 | 12600
3 | Application of Painting | Job | 1 |  | 1 | 15000 | 15000
| Total. | [5 empty] | 57600 | 276478.56
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [5 empty] | 0 | 276478.56
| Total Rs. | [6 empty] | 276478.56
Sub-Contractor Margin: |  |  | 25% |  |  |  |  | 69119.64
Total Price | [7 empty] | 345598.2
Dated: | 2023-11-15
Project: | Construction of Standard Chartered bank at I.I Chundrigar Road karachi.
Rate Analysis of Exhaust Fans
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Supply of Exhaust fans | Nos | 14 |  | 14 | 4300 | 60200
| Total. | [5 empty] | 60200 | 60200
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Installation of Exhaust Fans | Nos | 14 |  | 14 | 1000 | 14000
| Total. | [5 empty] | 14000 | 74200
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [5 empty] | 0 | 74200
| Total Rs. | [6 empty] | 74200
Sub-Contractor Margin: |  |  | 25% |  |  |  |  | 18550
Total Price | [7 empty] | 92750
Grand Total Price | [7 empty] | 1119473.2