## Summary-OF Ground Floor
SUMMARY OF HVAC
STANDARD CHARTERED BANK HEAD OFFICE
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | MEZZANINE | ROOF | CURRANT TOTAL
1 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
1.1 | GF-AC-01 | Nos. | 1 |  |  |  | 1
1.2 | GF-AC-02 | Nos. | 0 |  |  |  | 0
1.3 | GF-AC-03 | Nos. | 2 |  |  |  | 2
1.4 | GF-AC-04 | Nos. | 4 |  |  |  | 4
1.5 | GF-CSU-01 | Nos. | 1 |  |  |  | 1
1.6 | GF-CSU-02 | Nos. | 6 |  |  |  | 6
1.7 | GF-FAHU-01 | No. | 1 |  |  |  | 1
2 | Supply & installation of refrigerant pipes (liquid + gas) with 12mm thick expended rubber foam insulation, PVC tape wrapping + control wiring in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
2.1 | GF-AC-01 (Soft Pipes) | Rm |  | 28.962 |  |  | 28.962
2.2 | GF-AC-02 (Soft Pipes) | Rm |  |  |  |  | 0
2.3 | GF-AC-03 (Soft Pipes) | Rm |  | 45.471 |  |  | 45.471
2.4 | GF-AC-04 (Hard Pipes) | Rm |  | 196.29 |  |  | 196.29
2.5 | GF-CSU-01 (Soft Pipes) | Rm |  | 28.235 |  |  | 28.235
2.6 | GF-CSU-02 (Soft Pipes) | Rm |  | 162.462 |  |  | 162.462
2.7 | GF-FAHU-01 (Hard Pipes) | Rm |  | 47.979 |  |  | 47.979
3 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm |  | 5.48 | 5.95 | 3.12 | 14.55
4 | Supply & installation of SCH-40 uPVC make class D pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
4.1 | 25mm dia | Rm |  | 111.14 |  |  | 111.14
4.2 | 32mm dia | Rm |  | 36.041 |  |  | 36.041
5 | Supply & installation of air curtains including, supports, electrical connection etc, complete in all respects ready to operate as per drawings, specification & as per instruction of consultant.
5.1 | 1.5m Length | Nos. |  |  |  |  | 0
6 | Supply & installation of ventilation fans as per mentioned in schedule, including vibration isolator, flexible duct connection / connector, power wiring from isolation box to unit (4 to 5 meter radius), support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
6.1 | GF-EAF-01 (with uPVC Pipe & Fittings) | Nos. |  |  |  |  | 0
6.2 | GF-EAF-02 | No. |  |  |  |  | 0
6.3 | GF-EAF-03 | No. |  |  |  |  | 0
8 | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
8.1 | 100mm dia | Nos. |  |  |  |  | 0
8.2 | 200mm x 200mm | Nos. |  |  |  |  | 0
8.3 | 600mm x 200mm | No. |  |  |  |  | 0
9 | Supply & installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
9.1 | Supply & Return Air Grills / Registers | [5 empty] | 0
i. | 1400mm x 150mm | No. |  |  |  |  | 0
9.2 | Exhaust Air Disc Valves | [5 empty] | 0
i. | 150mm dia | Nos. |  |  |  |  | 0

## Summary-OF Mezzanine
SUMMARY OF HVAC
STANDARD CHARTERED BANK HEAD OFFICE
BOQ NO. | DESCRIPTION | Unit | No. | MEZZANINE | CURRANT TOTAL
1 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
1.1 | MF-AC-01 | Nos. | 4 |  | 4
1.2 | MF-AC-02 | Nos. | 2 |  | 2
1.3 | GF-CSU-01 | Nos. | 3 |  | 3
1.4 | GF-CSU-02 | Nos. | 8 |  | 8
2 | Supply & installation of refrigerant pipes (liquid + gas) with 12mm thick expended rubber foam insulation, PVC tape wrapping + control wiring in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
2.1 | GF-AC-01 (Soft Pipes) | Rm |  | 159.03 | 159.03
2.2 | GF-AC-02 (Soft Pipes) | Rm |  | 81.582 | 81.582
2.3 | GF-CSU-01 (Soft Pipes) | Rm |  | 103.18 | 103.18
2.4 | GF-CSU-02 (Soft Pipes) | Rm |  | 262.026 | 262.026
3 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm |  |  | 0
4 | Supply & installation of SCH-40 uPVC make class D pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
4.1 | 25mm dia | Rm |  | 94.9 | 94.9
4.2 | 32mm dia | Rm |  | 49.245 | 49.245
5 | Supply & installation of ventilation fans as per mentioned in schedule, including vibration isolator, flexible duct connection / connector, power wiring from isolation box to unit (4 to 5 meter radius), support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
5.1 | MZ-EAF-01 (with uPVC Pipe & Fittings) | No |  |  | 0