## Summery 1st IPC (hidden)
1st Running Bill
Total Construction
CONSTRUCTION OF NEW SURGICAL ONCOLOGY COMPLEX AT JPMC , KARACHI
Civil Works |  | SUMMARY
S # | BOQ # | Description | Previous Bill Amount | Current Bill Amount | Total Amount ( Rs)
Demolition Works
A | 01-1C | Demolition Works | 0 | #REF! | #REF!
B |  | Earth Work
| 01-2C | Excavation | 0 | #REF! | #REF!
| 01-4C | Back Filling ( out side source ) | 0 | #REF! | #REF!
| 01-5C | Stone Soling | 0 | #REF! | #REF!
C |  | Termite Control Treatment
| 01-6C | Termite | 0 | #REF! | #REF!
D |  | Reinforcement
| 01-7C | Steel Grade 70 | 0 | #REF! | #REF!
E |  | SUB-STRUCTURE
| 01-8C | Class 'E' concrete ( Lean for Foundation ) | 0 | #REF! | #REF!
| 01-10C | Class 'B' concrete (Footing / Foundation) | 0 | #REF! | #REF!
| 01-11C | Class 'A' concrete (Column up to plinth) | 0 | #REF! | #REF!
F |  | Water Proofing & Built up Roofing.
| 01-40C | Bitumen coating grade 10/20 | 0 | #REF! | #REF!
| Total ( A+B+C+D+E+F ) = G |  | 0 | #REF! | #REF! | #REF!
| I | Deduction Against Rebate @ 2.64 % | 0 | #REF! | #REF!
| H= G-I | Work done Amount after Rebate | 0 | #REF! | #REF! | #REF!
Extra Works detail
|  | Relocation of Electrical cables | 0 | 222300 | 222300
|  | Work done Amount including Extra Woks | 0 | #REF! | #REF!
DEDUCTIONS
| I | Recovery of OFM
| ia | Deduction Against Steel 91.23 tons @ 85500 per tons | 0 | -7800250.5 | -7800250.5
| ib | Deduction Against Cement @ 550/= Per Bag ( OPC ) [ 4184 bags ] | 0 | -2301200 | -2301200
| I | Total Amount after OFM Deduction | 0 | #REF! | #REF!
| ja | 10 % Of Retention Mooney | 0 | #REF! | #REF!
| jb | Mobilization Advance | 0 | -2000000 | -2000000
| J | Total Amount After deduction of Retention & Mobilization | 0 | #REF! | #REF!
|  | Deduction Income tax @7.5 % | 0 | #REF! | #REF!
| K | Total Payable Amount after all deductions | 0 | #REF! | #REF!

## cost impact
ABSTRACT OF Cost
Total Construction
CONSTRUCTION OF NEW SURGICAL ONCOLOGY COMPLEX AT JPMC , KARACHI
1st Running Bill
Civil Works
Project | TriFit Gym
Com-1 Clifton karachi
Cost Impact For Cassette type unit Relocation in Cafeteria
2 Cassette Type Unit Relocate
BOQ Item # | Description | Time Impact | Unit | Quantity | Rate supply | Rate Labour | Total Amount | Remarks
5.4 | Supply and Installation of additional copper pipe |  | Rft | 20 | 2057 | 200 | 45140
2.4 | Dismentling and re installation of cassette type unit |  | Nos | 2 | 9000 | 8000 | 34000 | installation of these 2 unit in cafeteria.
7.1 | Supply and Installation of upvc Drain pipe Dia 1'' |  | Rft | 10 | 1120 | 136 | 12560
6 | Supply and installation of G.i cable tray |  | Sft | 15 | 650 | 160 | 12150
3 | Dismentling of copper pipe vrf unit |  | Rft | 13 |  | 400 | 5200
6 | Dismentling and Reinstallation of Gi cable tray |  | Sft | 10 |  | 160 | 1600
1 | Charging of Gas |  | job | 2 | 4000 |  | 8000
| TOTAL AMOUNT | [5 empty] | 118650