## Summary
DHL Office Frotune Center
Shahra faisal, KARACHI
FINAL BILL |  |  | Verified Bill
S.# | DESCRIPTION | TOTAL (Rs.) | TOTAL (Rs.)
1 | VRF Condensing Units | 5326200 | 5326200
2 | Duct Work | 774880 | 726456.8
3 | Copper Piping Work | 4822850 | 4270787.5
4 | Air conditioning units. | 270000 | 180000
| Total Amount (Rs.) | 13368257 | 10503444.3
5 | Discount Agreed 19% |  | 1995654.417
6 | Total Amount (Verified) |  | 8507789.883
7 | Variation Amount (06 Nos) | 2174327 | 2067598 | Under verification Process
8 | Grand Total Amount (Receivables) |  | 10575387.883
9 | Add 4.5% Tax amount |  | 475892.4547
10 | Total |  | 11051280.3377
11 | Received Amount |  | 8097014
12 | Retention 5% |  | 552564.0169
13 | Balance Receivables |  | 2401702.3208
Note: 1) The original Quoted BOQ was PKR 14,196,380/-. However, after discussions with Mr. Taha Ghaznavi, the final agreed amount was settled at PKR 11,500,000/-. This reflects a discount of approximately 19%.
2) In the variation scope, a 28% overhead is already included, of which you are entitled to 10%. Therefore, an additional 18% deduction on variations is not justified.
9094109
454705.45

## VRF condensing units
BILL OF QUANTITIES | [5 empty] | FINAL BILL |  |  |  |  | FINAL BILL
ITEM | DESCRIPTION | QTY | UNIT | SUPPLY RATE | LABOUR RATE | Billed Qty | Amount | UNIT | SUPPLY RATE | LABOUR RATE | Billed Qty | Amount
Supply,install,test,verify and commission the following plants and equipment. Tenderer is expected to be familiar with the specifed manufacturers and is to submit appropriate brochures of the specified items (or an equivalent product of another acceptable manufacturer as shall be agreed with the Client and Consultants.
Outdoor air-cooled VRF condensing units, capable of multiple indoor units and zone, with extended range refrigerant piping. Operating outdoor temperature . High COP. Refrigerant . E.g. Daikin, LG, or approved equal. Note that the capacities stated below are for the combined floor load and are not additions of the individual capacities of the indoor units. Chigo (A Carrier Company) - China
1 | VRF EKRV040 cap: 10 Ton | 1 | no |  | 85000 | 1 | 85000 | no |  | 85000 | 1 | 85000
2 | VRF EKRV040 cap: 10 Ton | 1 | no |  | 85000 | 1 | 85000 | no |  | 85000 | 1 | 85000
Indoor VRF Cassette Units (CAS)
Ceiling mounted cassette coil unit, matched to outdoor unit, with galvanised sheeting treated for corrosion, 3-speed fan, integral condensate pump, easily accessible and cleanable EU4 filter with anti-bacterial and mildew treatment, connections for remote control of fan and space temperature, all mounting and fixing accessories. Unit shall have port for BMS signal connection. Include for unit cabled remote control and wall mounted thermostat/controller.
1 | CAS 0-1 | 2 | no |  | 8000 | 3 | 24000 | no |  | 8000 | 3 | 24000
Cooling cap: 1.5 TON
2 | CAS 0-2 | 6 | no |  | 8000 | 8 | 64000 | no |  | 8000 | 8 | 64000
Cooling cap: 1 TON
3 | CAS 0-3 | 15 | no |  | 8000 | 8 | 64000 | no |  | 8000 | 8 | 64000
Cooling cap: 0.75 TON
Accessories
Supply and install accessories associated with the VRF units indicated above
1 | Remote control and thermostat unit incorporating 3-speed fan control. Allow for cabling
| - Cassette units | 1 | Lot |  | 45000 | 1 | 45000 | Lot |  | 45000 | 1 | 45000
Instrumentation and controls
2 | Supply and install system logic-based electrical and auto-control panel. Control unit to include for desktop PC and monitor (mounted in the 5th floor plant room). Panel shall allow for all electrical power protections - phase failure, under/over current, surge protection, etc. Include for step down transformer for controllers all to give a fully functional system (Auto Control System for VRF System is offered without computer system) | 1 | no |  | 190000 | 1 | 190000 | no |  | 190000 | 1 | 190000
3 | Allow for control cabling from all indoor units to outdoor units.
| Control Cabling | 1 | Lot | 375000 | 125000 | 1 | 500000 | Lot | 375000 | 125000 | 1 | 500000
| - ground floor units | 1 | Lot | 0 | 0 |  | 0 | Lot | 0 | 0 |  | 0
4 | Allow for power cabling to outdoor units. Include for outdoor mounted local isolators. (Power Cabling along with electrical DB box for outdoor units is included) | 1 | Lot | 895000 | 150000 | 1 | 1045000 | Lot | 895000 | 150000 | 1 | 1045000
[7 empty] | 0 |  |  |  |  | 0
5 | Allow for cable fixing, hangers, conduits, supports (G.I Cable Tray not included) | 1 | Lot | 290000 | 45000 | 1 | 335000 | Lot | 290000 | 45000 | 1 | 335000
Refrigerant piping
6 | Supply and install all refrigerant piping using copper (BS 2871). The tenderer shall submit computer based pipe sizing calculations appropriate to the product being tendered and a breakdown of the costings for each floor extended and totalled to the figures inserted in this BOQ. The refrigerant installation shall be from the roof mounted outdoor units to the indoor units on each floor. Rates shall include for all fittings and accessories (G.I Cable Tray not included)
| - 12th floor units | 1 | Lot | 1850000 | 250000 | 1 | 2100000 | Lot | 1850000 | 250000 | 1 | 2100000
7 | Supply and install insulations to all refrigerant piping using armaflex tubing (or approved equivalent) of appropriate thickness. Rates shall include for all fittings and accessories
| - 12th floor units | 1 | Lot | 550000 | 50000 | 1 | 600000 | Lot | 550000 | 50000 | 1 | 600000
8 | Condensate piping
Supply and install all condensate piping to the indoor units using HDPE piping. The layout shall be as indicated in the design drawings. Rates shall include for all fittings and accessories. Rates shall includes for 20mm thick armaflex (or approved equal) insulation tubing. (G.I Cable Tray not included)
Ac drain pipe
| 2mm dia (stack for entire installation and connection to drain channels) (G.I Cable Tray not included) | 72 | m | 1380 | 300 | 65 | 109200 | m | 1380 | 300 | 65 | 109200
9 | Allow for pipe fixing, brackets, hangers, supports (G.I Cable Tray not included) | 1 | Lot | 60000 | 20000 | 1 | 80000 | Lot | 60000 | 20000 | 1 | 80000
GRAND TOTAL (MATERIAL + LABOR) | [6 empty] | 5326200 |  |  |  |  | 5326200

## DuctWork
BILL OF QUANTITIES | [5 empty] | FINAL BILL |  |  |  |  | FINAL BILL
ITEM | DESCRIPTION | QTY | UNIT | SUPPLY RATE | LABOUR RATE | Billed Qty | Amount | UNIT | SUPPLY RATE | LABOUR RATE | Billed Qty | Amount
Supply,install,test,verify and commission the following (refer to drawing and specification for details). All air diffusion units shall be extruded aluminum (except otherwise indicated) and shall be to RAL colour to be approved by the architect
Ductwork
1 | Supply & Installation of Pre-insulated duct P3 type for fresh air. (20mm-PAL) | 962 | SFT | 480 | 80 | 948 | 530880 | SFT | 480 | 80 | 861.53 | 482456.8
2 | Supply & Installation of Centrifugal inline type Fresh air fan. (300 CFM) | 1 | No | 69000 | 5000 | 1 | 74000 | No | 69000 | 5000 | 1 | 74000
3 | Provided for internal thermal and acoustic duct sound liner to duct above using 12mm e.g. Armaflex/Armacell, KFlexUSA or approved equal. Include for fasterners, etc Insulations within plantrooms shall be internal. Also insulations up to 10m from (airhandling) AHUs shall be internal. | 420 | SFT | 390 | 70 | 0 | 0 | SFT | 390 | 70 | 0 | 0
4 | Supply Diffuser (SD) ceiling mounted. Units shall be square face adjustable multi-louvre type with round neck (or square neck) supply. Units shall be complete with iris (or opposed blade) damper. E.g. GDL, Trox or approved equivalent. Neck diameters are indicated below
| 150 dia | 12 | nos | 4000 | 500 | 12 | 54000 | nos | 4000 | 500 | 12 | 54000
5 | Return Grille (RG) ceiling mounted. Units shall be rectangular face adjustable egg crate type. Units shall be complete with opposed blade damper. E.g. GDL, Trox or approved equivalent
| 1200 x 600 | 1 | no | 29000 | 2000 | 1 | 31000 | no | 29000 | 2000 | 1 | 31000
6 | Flow control / Balancing Dampers single or multi leaf. E.g GDL, Trox or approved equivalent
| Allow for the provision of balancing dampers as indicated on drawing and/or specification and/or schedules | 1 | lot | 0 | 0 |  | 0 | lot | 0 | 0 |  | 0
7 | Allow for clean outs, test holes and access doors. | 1 | lot | 0 | 25000 | 1 | 25000 | lot | 0 | 25000 | 1 | 25000
8 | Allow for support, brackets, vibration dampers etc. | 1 | lot | 40000 | 20000 | 1 | 60000 | lot | 40000 | 20000 | 1 | 60000
9 | Allow for flexible duct connectors from duct to ceiling terminals. | 1 | lot | 0 | 0 | 1 | 0 | lot | 0 | 0 | 0 | 0
GRAND TOTAL (MATERIAL + LABOR) | [6 empty] | 774880 |  |  |  |  | 726456.8

## Copper
BILL OF QUANTITIES |  |  |  |  | FINAL BILL |  |  |  | FINAL BILL
S.N | DESCRIPTION | UNIT | QTY | RATE Rs. | Billed Qty | AMOUNT Rs. | QTY | RATE Rs. | Billed Qty | AMOUNT Rs.
1 | Piping and Control Wire (Cafeteria)
1.1 | Insulates copper pipe with control wire for Cassette A/C 2 TON haier ac | 210 | Rft | 2350 | 228 | 535800 | Rft | 2350 | 450.25 | 1058087.5
1.2 | AC drain pipe 25mm PVC for cassette ac with upper foam | 75 | Rft | 550 | 74 | 40700 | Rft | 550 | 65 | 35750
1.3 | installation cassette ac | 2 | Each | 5000 |  | 0 | Each | 5000 |  | 0
Total Amount | [5 empty] | 576500 |  |  |  | 1093837.5
1 | Piping and Control Wire (Multi Purpose)
1.1 | Insulates copper pipe with control wire for split A/C 2TON haier ac | 265 | Rft | 2350 | 167 | 392450 | Rft | 2350 | 83 | 195050
1.2 | AC drain pipe 25mm PVC for cassette ac with upper foam | 120 | Rft | 550 | 116 | 63800 | Rft | 550 | 774 | 425700
1.3 | installation cassette ac | 2 | Each | 5000 |  | 0 | Each | 5000 |  | 0
Total Amount | [5 empty] | 456250 |  |  |  | 620750
1 | Piping and Control Wire (Training Hall)
1.1 | Insulates copper pipe with control wire for Cassette A/C 2TON haier ac | 450 | Rft | 2350 | 231 | 542850 | Rft | 2350 | 87 | 204450
1.2 | AC drain pipe 25mm PVC for cassette ac with upper foam | 150 | Rft | 550 | 140 | 77000 | Rft | 550 | 245 | 134750
1.3 | installation split ac | 3 | Each | 5000 |  | 0 | Each | 5000 |  | 0
Total Amount | [5 empty] | 619850 |  |  |  | 339200
1 | Piping and Control Wire (Board Room)
1.1 | Insulates copper pipe with control wire for cassette A/C 2 TON haier ac | 410 | Rft | 2350 |  | 0 | Rft | 2350 |  | 0
1.2 | AC drain pipe 25mm PVC for cassette ac with upper foam | 250 | Rft | 550 |  | 0 | Rft | 550 |  | 0
1.3 | installation cassette ac | 2 | Each | 5000 |  | 0 | Each | 5000 |  | 0
Total Amount | [5 empty] | 0 |  |  |  | 0
1 | Piping and Control Wire (Hall)
1.1 | Insulates copper pipe with control wire for Cassette A/C 4 TON haier ac | 650 | Rft | 3250 | 479 | 1556750 | Rft | 3250 | 317 | 1030250
1.2 | AC drain pipe e class 25mmfor cassette ac with upper foam | 600 | Rft | 550 | 518 | 284900 | Rft | 550 |  | 0
1.3 | installation cassette ac | 8 | Each | 10000 |  | 0 | Each | 10000 |  | 0
1.1 | Insulates copper pipe with control wire for Floor standing A/C 2 TON haier ac | 400 | Rft | 2350 | 212 | 498200 | Rft | 2350 | 169 | 397150
1 | Piping and Control Wire (Male and female room) |  |  |  |  | 0 |  |  |  | 0
1.1 | Insulates copper pipe with control wire for1.5 ton split ac | 400 | Rft | 1600 | 519 | 830400 | Rft | 1600 | 493.5 | 789600
1.2 | AC drain pipe 25mm PVC for1.5 ton split ac | 100 | Rft | 485 |  | 0 | Rft | 485 |  | 0
1.3 | installation split ac | 2 | Each | 5000 |  | 0 | Each | 5000 |  | 0
Total Amount | [5 empty] | 3170250 |  |  |  | 2217000
GRAND TOTAL | [5 empty] | 4822850 |  |  |  | 4270787.5

## ac cost
BILL OF QUANTITIES |  |  |  |  | FINAL BILL |  |  | FINAL BILL
S.N | DESCRIPTION | UNIT | QTY | RATE Rs. | Billed Qty | AMOUNT Rs. | RATE Rs. | Billed Qty | AMOUNT Rs.
Electronic Item,s
1 | Haier 2 ton cassette invertet 24HE | No,s | 11 | 10000 | 10 | 100000 | 10000 | 11 | 110000
2 | Haier 4 ton cassette 48E | No,s | 7 | 10000 | 17 | 170000 | 10000 | 7 | 70000
3 | Split ac 1.5 Ton 18HFC | No,s |  |  |  | 0 |  |  | 0
4 | Split ac 2 Ton 24HFC | No,s |  |  |  | 0 |  |  | 0
5 | 55" LED Smart tcl | No,s | 4 | 10000 |  | 0 | 10000 |  | 0
Total Amount | [5 empty] | 270000 |  |  | 180000