## Table 1
Final Bill
Fire Suppression Services
Bank Al Habib Limited
Ground Floor, Center Point Tower, Karachi. | [9 empty] | Date: 15-05-2025
BILL OF QUANTITIES (Contract Amount) | [8 empty] | FINAL BILL
S.No. | Description | Unit | Qty | Rate |  | Amount |  | Total | Bill Qty | Material Amount | Labour Amount | Total Amount
|  |  |  | Material | Labour | Material | Labour | Amount Rs.
FIRE FIGHTING SERVICES
Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of consultants.
1 | MS Sch-40 seamless pipes including all specials M.I & D.I threaded & welded joint fittings UL listed FM approved, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
1.1 | Dia. 1" (Threaded fitting) | Rft. | 300 | 572 | 200 | 171600 | 60000 | 231600 | 260 | 148720 | 52000 | 200720
1.2 | Dia. 4" (Welded joints fitting) | Rft. | 40 | 3021 | 400 | 120840 | 16000 | 136840 | 55 | 166155 | 22000 | 188155
1.3 | Dia. 6" (Welded joints fitting) | Rft. | 30 | 5288 | 500 | 158640 | 15000 | 173640 | 22 | 116336 | 11000 | 127336
1.4 | Dia. 8" (Welded joints fitting) | Rft. | 330 | 7626 | 700 | 2516580 | 231000 | 2747580 | 325 | 2478450 | 227500 | 2705950
2 | OS & Y Gate valves with matching flanges. |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
2.1 | Dia. 4" | No. | 1 | 114406 | 5000 | 114406 | 5000 | 119406 | 1 | 114406 | 5000 | 119406
2.2 | Dia. 6" | Nos. | 2 | 162309 | 6000 | 324618 | 12000 | 336618 | 2 | 324618 | 12000 | 336618
2.3 | Dia. 8" | No. | 1 | 224915 | 8000 | 224915 | 8000 | 232915 | 1 | 224915 | 8000 | 232915
3 | Lock Shield Valves. |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
3.1 | Dia. 1" | Nos. | 55 | 8262 | 1000 | 454410 | 55000 | 509410 | 53 | 437886 | 53000 | 490886
4 | Pressure Regulating Valves. (PRV) |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
4.1 | Dia. 1" | Nos. | 55 | 14703 | 1500 | 808665 | 82500 | 891165 | 53 | 779259 | 79500 | 858759
5 | Supply & installation of fire stop material (for passive fire fighting / smoke barrier) in all openings and penetrations, either in slab or wall, complete in all respects, ready to operate as per fire stopper recommended material, and as per instruction of Consultant. | Job. | 1 | 50847 | 20000 | 50847 | 20000 | 70847 | 1 | 50847 | 20000 | 70847
6 | Making of As-Built & Shop Drawings on AutoCAD 2018 or latest version with sectional details complete in all respects as per instructions of consultant. | Job. | 1 | 12711 | 20000 | 12711 | 20000 | 32711 | 1 | 12711 | 20000 | 32711
7 | Painting, identification and tagging to the installations and equipments. | Job. | 1 | 127118 | 100000 | 127118 | 100000 | 227118 | 1 | 127118 | 100000 | 227118
8 | Flushing of entire fire pipe work according to (NFPA-13). | Job. | 1 | 16949 | 30000 | 16949 | 30000 | 46949 | 1 | 16949 | 30000 | 46949
9 | Testing, and commissioning of entire fire fighting installation as per Consultant's approval. | Job. | 1 | 0 | 200000 | 0 | 200000 | 200000 | 1 | 0 | 200000 | 200000
| Total Amount of Bill |  |  |  |  | 5102299 | 854500 | 5956799 |  | 4998370 | 840000 | 5838370
| Total Discount 3.960% on Material & 7.8514% on Labour |  |  |  | 3.96% | 202045.9381 | 67090.213 | 269136.1511 |  | 197935.452 | 65951.76 | 263887.212
| Discounted Cost Excluding Taxes |  |  |  |  | 4900253.0619 | 787409.787 | 5687662.8489 |  | 4800434.548 | 774048.24 | 5574482.788
| Add 15% SST | [6 empty] | 853149.4273 |  |  |  | 836172.4182
| Total Fixed Amount Including Taxes | [6 empty] | 6540812.2762 |  |  |  | 6410655.2062
Payment Terms
1) 20% advance / Mobilization
2) 40% after completion of 50% work.
3) 30% after completion of remaining 50% work.
4) 10% after successful testing & commissioning.