## SUMMARY 01
Project: | ENGRO, THF, 3RD Floor | Date: |  | Date:
Consultant: S Mehboob & Company |  | Drawing No. |  | Drawing No. M04.07
Contractor: National Engineers Co. |  | Sheet # of |  | Sheet # 01 of 01
SUMMARY OF G. I. SHEET METAL DUCT WORK
B.O.Q | Description |  |  | SQFT
Item No. |  |  |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00
1 | Sheet No 1 |  |  | 260.5278 | 357.1806 | 0
2 | Sheet No 2 |  |  | 0 | 222.5417 | 288.25
3 | Sheet No 3 |  |  | 0 | 46.6944 | 585.4583
4 | Sheet No 4 |  |  | 0 | 0 | 275.125
5 | Sheet No 5 |  |  | - | - | 163.8889
6 | Sheet No 6 |  |  | - | - | 153.8611
7 | Sheet No 7 |  |  | - | 7.1667 | 341.6667
8 | Sheet No 8 |  |  | - | 3.5 | 233.6111
9 | Sheet No 9 |  |  | - | - | 227.2222
10 | Sheet No 10 |  |  | - | - | 181
11 | Sheet No 11 |  |  | 124.9167 | 216.5833 | 90
12 | Sheet No 12 |  |  | 6.5 | 374.1667 | 358.0556
13 | Sheet No 13 |  |  | 0 | 244.5556 | 169.8056
14 | Sheet No 14 |  |  | 0 | 0 | 202.8056
15 | Sheet No 15 |  |  | - | 0 | 119.9722
16 | Sheet No 16 |  |  | - | - | 458.6667
17 | Sheet No 17 |  |  | - | - | 187.3333
18 | Sheet No 18 |  |  | - | - | 74.5
19 | Sheet No 19 |  |  | - | - | 873.2778
20 | Sheet No 20 |  |  | - | - | 90.5943
A | TOTAL SQFT (20 Gauge Duct is Adjusted in 22 Gauge Duct in BOQ) |  |  | 391.9444 | 1472.3889 | 5075.0943
Contractor's P.M / Site Engineer |  |  | Consultant's P.M / Site Engineer
Signature: |  |  | Signature:
Name: | RAZA |  | Name:

## 1
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 01 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
1 | Supply Air Duct Plenum | 72 | x | 33 |  | 66 |  | 1 | 96.25
2 | End Cap | 72 | x | 33 |  |  |  | 1 | 16.5
3 | Supply Air Duct Neck | 62 | x | 18 |  | 6 |  | 1 | 6.6667
4 | Supply Air Duct Offset | 62 | x | 18 |  | 48 |  | 1 | 53.3333
5 | Supply Air Duct (G.P) | 62 | x | 18 |  | 21 |  | 1 | 23.3333
6 | Supply Air Duct Elbow | 62 | x | 18 |  | 43 |  | 1 | 47.7778
7 | Supply Air Duct (G.P) | 62 | x | 18 |  | 15 |  | 1 | 16.6667
8 | Supply Air Duct | 34 | x | 18 |  | 45 |  | 1 |  | 32.5
9 | Supply Air Duct Offset | 34 | x | 18 |  | 55 |  | 1 |  | 39.7222
10 | Supply Air Duct | 34 | x | 18 |  | 48 |  | 1 |  | 34.6667
11 | Supply Air Duct | 34 | x | 18 |  | 48 |  | 1 |  | 34.6667
12 | Supply Air Duct | 34 | x | 18 |  | 48 |  | 1 |  | 34.6667
13 | Supply Air Duct Reducer | 34 | x | 18 |  | 27 |  | 1 |  | 20.625
|  | 44 | x | 14
14 | Supply Air Duct | 44 | x | 14 |  | 48 |  | 1 |  | 38.6667
15 | Supply Air Duct | 44 | x | 14 |  | 48 |  | 1 |  | 38.6667
16 | Supply Air Duct Round Square | 44 | x | 20 |  | 15 |  | 1 |  | 13.3333
17 | Supply Air Duct Round Square | 44 | x | 20 |  | 15 |  | 1 |  | 13.3333
18 | Supply Air Duct | 38 | x | 14 |  | 30 |  | 1 |  | 21.6667
19 | Supply Air Duct | 38 | x | 14 |  | 48 |  | 1 |  | 34.6667
| TOTAL SQFT | [7 empty] | 260.5278 | 357.1806 | 0

## 1 (2)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 02 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
20 | Supply Air Duct Reducer | 38 | x | 14 |  | 18 |  | 1 |  | 12.5
|  | 38 | x | 10
21 | Supply Air Duct | 38 | x | 10 |  | 60 |  | 1 |  | 40
22 | Supply Air Duct Elbow | 38 | x | 10 |  | 68 |  | 1 |  | 45.3333
23 | Supply Air Duct | 38 | x | 10 |  | 48 |  | 1 |  | 32
24 | Supply Air Duct Elbow | 38 | x | 10 |  | 68 |  | 1 |  | 45.3333
25 | Supply Air Duct | 38 | x | 10 |  | 48 |  | 1 |  | 32
26 | Supply Air Duct Reducer | 38 | x | 10 |  | 27 |  | 1 |  | 15.375
|  | 24 | x | 10
27 | Supply Air Duct | 24 | x | 10 |  | 39 |  | 1 |  |  | 18.4167
28 | Supply Air Duct | 24 | x | 10 |  | 48 |  | 1 |  |  | 22.6667
29 | Supply Air Duct | 24 | x | 10 |  | 48 |  | 1 |  |  | 22.6667
30 | Supply Air Duct | 24 | x | 10 |  | 48 |  | 1 |  |  | 22.6667
31 | Supply Air Duct Offset | 24 | x | 10 |  | 99 |  | 1 |  |  | 46.75
32 | Supply Air Duct | 24 | x | 10 |  | 200 |  | 1 |  |  | 94.4444
33 | Supply Air Duct Elbow | 24 | x | 10 |  | 15 |  | 1 |  |  | 7.0833
34 | Supply Air Duct | 24 | x | 10 |  | 88 |  | 1 |  |  | 41.5556
35 | Supply Air Duct Reducer | 24 | x | 10 |  | 27 |  | 1 |  |  | 12
|  | 20 | x | 10
| TOTAL SQFT | [7 empty] | 0 | 222.5417 | 288.25

## 1 (3)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 03 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
36 | Supply Air Duct Elbow | 20 | x | 10 |  | 49 |  | 1 |  |  | 20.4167
37 | Supply Air Duct | 20 | x | 10 |  | 205 |  | 1 |  |  | 85.4167
38 | Supply Air Duct Elbow | 24 | x | 18 |  | 84 |  | 1 |  |  | 49
39 | Supply Air Duct (G.P) | 24 | x | 18 |  | 6 |  | 1 |  |  | 3.5
40 | Supply Air Duct | 24 | x | 18 |  | 48 |  | 1 |  |  | 28
41 | Supply Air Duct | 24 | x | 18 |  | 48 |  | 1 |  |  | 28
42 | Supply Air Duct | 24 | x | 18 |  | 48 |  | 1 |  |  | 28
43 | Supply Air Duct Reducer | 24 | x | 18 |  | 27 |  | 1 |  |  | 14.625
|  | 24 | x | 12
44 | Supply Air Duct Offset | 24 | x | 12 |  | 48 |  | 1 |  |  | 24
45 | Supply Air Duct Elbow | 24 | x | 12 |  | 55 |  | 1 |  |  | 27.5
46 | Supply Air Duct | 24 | x | 12 |  | 125 |  | 1 |  |  | 62.5
47 | Supply Air Duct Offset | 24 | x | 12 |  | 43 |  | 1 |  |  | 21.5
48 | Supply Air Duct | 24 | x | 12 |  | 304 |  | 1 |  |  | 152
49 | Supply Air Duct Reducer | 24 | x | 12 |  | 18 |  | 1 |  | 10.25
|  | 38 | x | 8
50 | Supply Air Duct (G.P) | 38 | x | 8 |  | 41 |  | 1 |  | 26.1944
51 | Supply Air Duct Reducer | 38 | x | 8 |  | 18 |  | 1 |  | 10.25
|  | 24 | x | 12
52 | Supply Air Duct Elbow | 24 | x | 12 |  | 55 |  | 1 |  |  | 27.5
53 | Supply Air Duct | 24 | x | 12 |  | 27 |  | 1 |  |  | 13.5
| TOTAL SQFT | [7 empty] | 0 | 46.6944 | 585.4583

## 1 (4)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 04 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
54 | Supply Air Duct (G.P) | 24 | x | 12 |  | 33 |  | 1 |  |  | 16.5
55 | Supply Air Duct Elbow | 24 | x | 12 |  | 45 |  | 1 |  |  | 22.5
56 | Supply Air Duct (G.P) | 24 | x | 12 |  | 13 |  | 1 |  |  | 6.5
57 | Supply Air Duct | 24 | x | 12 |  | 48 |  | 1 |  |  | 24
58 | Supply Air Duct | 24 | x | 12 |  | 48 |  | 1 |  |  | 24
59 | Supply Air Duct Reducer | 24 | x | 12 |  | 27 |  | 1 |  |  | 12.375
|  | 20 | x | 10
60 | Supply Air Duct | 20 | x | 10 |  | 48 |  | 1 |  |  | 20
61 | Supply Air Duct | 20 | x | 10 |  | 48 |  | 1 |  |  | 20
62 | Supply Air Duct | 20 | x | 10 |  | 48 |  | 1 |  |  | 20
63 | Supply Air Duct | 20 | x | 10 |  | 27 |  | 1 |  |  | 11.25
64 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
65 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
66 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
67 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
68 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
69 | Supply Air Duct Elbow | 16 | x | 8 |  | 37 |  | 1 |  |  | 12.3333
70 | Supply Air Duct | 16 | x | 8 |  | 17 |  | 1 |  |  | 5.6667
| TOTAL SQFT | [7 empty] | 0 | 0 | 275.125

## 1 (5)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 05 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
71 | Supply Air Duct Elbow | 16 | x | 8 |  | 37 |  | 1 |  |  | 12.3333
72 | Supply Air Duct Round Square | 16 | x | 8 |  | 15 |  | 1 |  |  | 5
73 | Supply Air Duct Round Square | 16 | x | 8 |  | 15 |  | 1 |  |  | 5
74 | Supply Air Duct | 16 |  | 8 |  | 48 |  | 1 |  |  | 16
75 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
76 | Supply Air Duct Round Square | 16 | x | 8 |  | 15 |  | 1 |  |  | 5
77 | Supply Air Duct Round Square | 16 | x | 8 |  | 15 |  | 1 |  |  | 5
78 | Supply Air Duct | 16 | x | 8 |  | 48 |  | 1 |  |  | 16
BRANCH 1
1 | Supply Air Duct Neck | 16 | x | 8 |  | 6 |  | 1 |  |  | 2
2 | Supply Air Duct (G.P) | 8 | x | 8 |  | 27 |  | 1 |  |  | 6
3 | Supply Air Duct Round Square | 12 | x | 12 |  | 15 |  | 1 |  |  | 5
4 | Supply Air Duct Round Square | 12 | x | 12 |  | 15 |  | 1 |  |  | 5
5 | Supply Air Duct Elbow | 8 | x | 8 |  | 27 |  | 1 |  |  | 6
6 | Supply Air Duct | 8 | x | 8 |  | 48 |  | 1 |  |  | 10.6667
7 | Supply Air Duct | 8 | x | 8 |  | 48 |  | 1 |  |  | 10.6667
8 | Supply Air Duct | 8 | x | 8 |  | 38 |  | 1 |  |  | 8.4444
9 | End Cap | 8 | x | 8 |  |  |  | 1 |  |  | 0.44444
BRANCH 2
1 | Supply Air Duct Neck | 16 | x | 8 |  | 6 |  | 1 |  |  | 2
2 | Supply Air Duct (G.P) | 8 | x | 8 |  | 39 |  | 1 |  |  | 8.6667
3 | Supply Air Duct Round Square | 12 | x | 12 |  | 15 |  | 1 |  |  | 5
4 | Supply Air Duct Round Square | 12 | x | 12 |  | 15 |  | 1 |  |  | 5
5 | Supply Air Duct | 8 | x | 8 |  | 39 |  | 1 |  |  | 8.6667
| TOTAL SQFT | [7 empty] | 0 | 0 | 163.8889

## 1 (6)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 06 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
6 | End Cap | 8 | x | 8 |  |  |  | 2 |  |  | 0.44444
BRANCH 3
1 | Supply Air Duct Neck | 16 | x | 8 |  | 6 |  | 1 |  |  | 2
2 | Supply Air Duct (G.P) | 8 | x | 8 |  | 39 |  | 1 |  |  | 8.6667
3 | Supply Air Duct Round Square | 12 | x | 12 |  | 15 |  | 1 |  |  | 5
4 | Supply Air Duct Round Square | 12 | x | 12 |  | 15 |  | 1 |  |  | 5
5 | Supply Air Duct | 8 | x | 8 |  | 39 |  | 1 |  |  | 8.6667
6 | End Cap | 8 | x | 8 |  |  |  | 1 |  |  | 0.44444
BRANCH 4
1 | Supply Air Duct Neck | 26 | x | 10 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 |  |  | 18.6667
3 | Supply Air Duct | 18 | x | 10 |  | 42 |  | 1 |  |  | 16.3333
4 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 |  |  | 3.3333
5 | Supply Air Duct | 14 | x | 10 |  | 41 |  | 1 |  |  | 13.6667
6 | Supply Air Duct | 14 | x | 10 |  | 41 |  | 1 |  |  | 13.6667
7 | Supply Air Duct | 14 | x | 10 |  | 48 |  | 1 |  |  | 16
8 | End Cap | 14 | x | 10 |  |  |  | 2 |  |  | 0.97222
BRANCH 5
1 | Supply Air Duct Neck | 26 | x | 10 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 |  |  | 18.6667
3 | Supply Air Duct | 18 | x | 10 |  | 42 |  | 1 |  |  | 16.3333
| TOTAL SQFT | [7 empty] | 0 | 0 | 153.8611

## 1 (7)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 07 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
BRANCH 5
4 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 |  | 3.3333
5 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 |  |  | 18.6667
6 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 |  |  | 18.6667
7 | Supply Air Duct | 18 | x | 10 |  | 27 |  | 1 |  |  | 10.5
8 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 |  |  | 18.6667
9 | End Cap | 18 | x | 10 |  |  |  | 2 |  |  | 1.25
BRANCH 6
1 | Supply Air Duct Neck | 36 | x | 10 |  | 6 |  | 1 |  | 3.8333
2 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
3 | Supply Air Duct | 28 | x | 10 |  | 40 |  | 1 |  |  | 21.1111
4 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
5 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
6 | Supply Air Duct Elbow | 28 | x | 10 |  | 41 |  | 1 |  |  | 21.6389
7 | Supply Air Duct | 28 | x | 10 |  | 27 |  | 1 |  |  | 14.25
8 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
9 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
10 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
11 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
12 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
13 | Supply Air Duct | 28 | x | 10 |  | 27 |  | 1 |  |  | 14.25
| TOTAL SQFT | [7 empty] | 0 | 7.1667 | 341.6667

## 1 (8)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 08 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
14 | Supply Air Duct | 28 | x | 10 |  | 48 |  | 1 |  |  | 25.3333
15 | End Cap | 28 | x | 10 |  |  |  | 2 |  |  | 1.9444
BRANCH 7
1 | Supply Air Duct Neck | 18 | x | 10 |  | 6 |  | 1 |  |  | 2.3333
2 | Supply Air Duct | 10 | x | 10 |  | 135 |  | 1 |  |  | 37.5
3 | Supply Air Duct | 10 | x | 10 |  | 88 |  | 1 |  |  | 24.4444
4 | End Cap | 10 | x | 10 |  |  |  | 2 |  |  | 0.69444
BRANCH 8
1 | Supply Air Duct Neck | 32 | x | 10 |  | 6 |  | 1 |  | 3.5
2 | Supply Air Duct | 24 |  | 10 |  | 42 |  | 1 |  |  | 19.8333
3 | Supply Air Duct Round Square | 24 |  | 10 |  | 15 |  | 1 |  |  | 7.0833
4 | Supply Air Duct Round Square | 24 |  | 10 |  | 15 |  | 1 |  |  | 7.0833
5 | Supply Air Duct | 24 |  | 10 |  | 48 |  | 1 |  |  | 22.6667
6 | Supply Air Duct Elbow | 24 |  | 10 |  | 58 |  | 1 |  |  | 27.3889
7 | Supply Air Duct | 24 |  | 10 |  | 24 |  | 1 |  |  | 11.3333
8 | Supply Air Duct | 24 |  | 10 |  | 15 |  | 1 |  |  | 7.0833
BRANCH 9
1 | Supply Air Duct Elbow | 10 |  | 10 |  | 29 |  | 1 |  |  | 8.0556
2 | Supply Air Duct | 10 |  | 10 |  | 15 |  | 1 |  |  | 4.1667
3 | Supply Air Duct | 10 |  | 10 |  | 48 |  | 1 |  |  | 13.3333
4 | Supply Air Duct | 10 |  | 10 |  | 48 |  | 1 |  |  | 13.3333
| TOTAL SQFT | [7 empty] | 0 | 3.5 | 233.6111

## 1 (9)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 09 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
5 | End Cap | 10 | x | 10 |  |  |  | 1 |  |  | 0.69444
BRANCH 10
1 | Supply Air Duct Elbow | 18 |  | 10 |  | 49 |  | 1 |  |  | 19.0556
2 | Supply Air Duct | 18 |  | 10 |  | 35 |  | 1 |  |  | 13.6111
3 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 |  |  | 18.6667
4 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 |  |  | 18.6667
5 | Supply Air Duct | 18 |  | 10 |  | 39 |  | 2 |  |  | 15.1667
6 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 |  |  | 18.6667
7 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 |  |  | 18.6667
8 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 |  |  | 18.6667
9 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 |  |  | 18.6667
10 | End Cap | 18 |  | 10 |  |  |  | 1 |  |  | 1.25
BRANCH 11
1 | Supply Air Duct Neck | 20 |  | 10 |  | 6 |  | 1 |  |  | 2.5
2 | Supply Air Duct | 12 |  | 10 |  | 48 |  | 1 |  |  | 14.6667
3 | Supply Air Duct | 12 |  | 10 |  | 48 |  | 1 |  |  | 14.6667
4 | Supply Air Duct | 12 |  | 10 |  | 27 |  | 1 |  |  | 8.25
5 | Supply Air Duct Elbow | 12 |  | 10 |  | 15 |  | 1 |  |  | 4.5833
6 | Supply Air Duct | 12 |  | 10 |  | 27 |  | 1 |  |  | 8.25
7 | Supply Air Duct Elbow | 12 |  | 10 |  | 26 |  | 1 |  |  | 7.9444
8 | Supply Air Duct Round Square | 12 |  | 10 |  | 15 |  | 1 |  |  | 4.5833
| TOTAL SQFT | [7 empty] | 0 | 0 | 227.2222

## 1 (10)
Project: | ENGRO, THF, 3RD Floor |  |  |  |  | Date: | Date:
Consultant: S Mehboob & Company | [5 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [5 empty] | Sheet # of | Sheet # 10 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [5 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 01
BRANCH 11
9 | Supply Air Duct Round Square | 12 | 10 |  | 15 |  | 1 |  |  | 4.5833
10 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
11 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
12 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
13 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
14 | End Cap | 12 | 10 |  |  |  | 1 |  |  | 0.83333
BRANCH 12
1 | Supply Air Duct Neck | 20 | 10 |  | 6 |  | 1 |  |  | 2.5
2 | Supply Air Duct Elbow | 12 | 10 |  | 33 |  | 1 |  |  | 10.0833
3 | Supply Air Duct Round Square | 12 | 10 |  | 15 |  | 1 |  |  | 4.5833
4 | Supply Air Duct Round Square | 12 | 10 |  | 15 |  | 1 |  |  | 4.5833
5 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
6 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
7 | Supply Air Duct | 12 | 10 |  | 48 |  | 1 |  |  | 14.6667
8 | Supply Air Duct | 12 | 10 |  | 27 |  | 1 |  |  | 8.25
9 | Supply Air Duct Elbow | 12 | 10 |  | 33 |  | 1 |  |  | 10.0833
10 | Supply Air Duct | 12 | 10 |  | 51 |  | 1 |  |  | 15.5833
11 | Supply Air Duct | 12 | 10 |  | 51 |  | 1 |  |  | 15.5833
12 | End Cap | 12 | 10 |  |  |  | 2 |  |  | 1.6667
| TOTAL SQFT | [6 empty] | 0 | 0 | 181
|  | 12 | 10

## 1 (11)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 11 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
1 | Supply Air Duct Reducer | 68 | x | 18 |  | 18 |  | 1 | 20.75
|  | 62 | x | 18
2 | Supply Air Duct | 62 | x | 18 |  | 69 |  | 1 | 76.6667
3 | Supply Air Duct Reducer | 62 | x | 18 |  | 30 |  | 1 | 27.5
|  | 38 | x | 14
4 | Supply Air Duct Offset | 38 | x | 14 |  | 39 |  | 1 |  | 28.1667
5 | Supply Air Duct | 38 | x | 14 |  | 48 |  | 1 |  | 34.6667
6 | Supply Air Duct | 38 | x | 14 |  | 48 |  | 1 |  | 34.6667
7 | Supply Air Duct | 38 | x | 14 |  | 33 |  | 1 |  | 23.8333
8 | Supply Air Duct | 38 | x | 14 |  | 48 |  | 1 |  | 34.6667
9 | Supply Air Duct Reducer | 38 | x | 14 |  | 30 |  | 1 |  | 18.3333
|  | 24 | x | 12
10 | Supply Air Duct Round Square | 24 | x | 12 |  | 15 |  | 1 |  |  | 7.5
11 | Supply Air Duct Round Square | 24 | x | 12 |  | 15 |  | 1 |  |  | 7.5
12 | Supply Air Duct | 24 | x | 12 |  | 99 |  | 1 |  |  | 49.5
13 | Supply Air Duct Reducer | 24 | x | 12 |  | 18 |  | 1 |  | 9.75
|  | 36 | x | 6
14 | Supply Air Duct | 36 | x | 6 |  | 39 |  | 1 |  | 22.75
15 | Supply Air Duct Reducer | 36 | x | 6 |  | 18 |  | 1 |  | 9.75
|  | 24 | x | 12
16 | Supply Air Duct | 24 | x | 12 |  | 51 |  | 1 |  |  | 25.5
| TOTAL SQFT | [7 empty] | 124.9167 | 216.5833 | 90
|  | 12 |  | 10

## 1 (12)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 12 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
17 | Supply Air Duct | 16 | x | 12 |  | 155 |  | 1 |  |  | 60.2778
18 | Supply Air Duct | 16 | x | 12 |  | 124 |  | 1 |  |  | 48.2222
19 | Supply Air Duct Elbow | 16 | x | 12 |  | 24 |  | 1 |  |  | 9.3333
20 | Supply Air Duct | 16 | x | 12 |  | 196 |  | 1 |  |  | 76.2222
21 | Supply Air Duct Elbow | 16 | x | 12 |  | 42 |  | 1 |  |  | 16.3333
22 | Supply Air Duct | 16 | x | 12 |  | 150 |  | 1 |  |  | 58.3333
23 | End Cap | 16 | x | 12 |  |  |  | 2 |  |  | 2.6667
24 | Supply Air Duct Neck | 64 | x | 14 |  | 6 |  | 1 | 6.5
25 | Supply Air Duct Offset | 56 | x | 14 |  | 62 |  | 1 |  | 60.2778
26 | Supply Air Duct | 56 | x | 14 |  | 54 |  | 1 |  | 52.5
28 | Supply Air Duct Elbow | 56 | x | 14 |  | 105 |  | 1 |  | 102.0833
29 | Supply Air Duct | 56 | x | 14 |  | 48 |  | 1 |  | 46.6667
30 | Supply Air Duct | 56 | x | 14 |  | 94 |  | 1 |  | 91.3889
31 | Supply Air Duct Reducer | 56 | x | 14 |  | 30 |  | 1 |  | 21.25
|  | 18 | x | 14
32 | Supply Air Duct | 18 | x | 14 |  | 63 |  | 1 |  |  | 28
33 | Supply Air Duct Elbow | 18 | x | 14 |  | 12 |  | 1 |  |  | 5.3333
34 | Supply Air Duct | 18 | x | 14 |  | 75 |  | 1 |  |  | 33.3333
35 | Supply Air Duct Elbow | 18 | x | 14 |  | 15 |  | 1 |  |  | 6.6667
36 | Supply Air Duct Round Square | 18 | x | 14 |  | 15 |  | 1 |  |  | 6.6667
37 | Supply Air Duct Round Square | 18 | x | 14 |  | 15 |  | 1 |  |  | 6.6667
| TOTAL SQFT | [7 empty] | 6.5 | 374.1667 | 358.0556
|  | 12 |  | 10

## 1 (13)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 13 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
38 | Supply Air Duct | 18 | x | 14 |  | 48 |  | 1 |  |  | 21.3333
39 | End Cap | 18 | x | 14 |  |  |  | 1 |  |  | 1.75
40 | Supply Air Duct Neck | 52 | x | 12 |  | 6 |  | 1 |  | 5.3333
41 | Supply Air Duct | 44 | x | 12 |  | 18 |  | 1 |  | 14
42 | Supply Air Duct | 44 | x | 12 |  | 48 |  | 1 |  | 37.3333
43 | Supply Air Duct Reducer | 44 | x | 12 |  | 30 |  | 1 |  | 22.5
|  | 40 | x | 12
44 | Supply Air Duct | 40 | x | 12 |  | 48 |  | 1 |  | 34.6667
45 | Supply Air Duct | 40 | x | 12 |  | 48 |  | 1 |  | 34.6667
46 | Supply Air Duct Elbow | 40 | x | 12 |  | 70 |  | 1 |  | 50.5556
47 | Supply Air Duct | 40 | x | 12 |  | 48 |  | 1 |  | 34.6667
48 | Supply Air Duct | 40 | x | 12 |  | 15 |  | 1 |  | 10.8333
49 | Supply Air Duct Elbow | 28 | x | 16 |  | 62 |  | 1 |  |  | 37.8889
50 | Supply Air Duct Elbow | 28 | x | 16 |  | 46 |  | 1 |  |  | 28.1111
51 | Supply Air Duct Round Square | 28 | x | 16 |  | 15 |  | 1 |  |  | 9.1667
52 | Supply Air Duct Round Square | 28 | x | 16 |  | 15 |  | 1 |  |  | 9.1667
53 | Supply Air Duct | 28 | x | 16 |  | 27 |  | 1 |  |  | 16.5
54 | Supply Air Duct | 28 | x | 16 |  | 22 |  | 1 |  |  | 13.4444
55 | Supply Air Duct | 28 | x | 16 |  | 48 |  | 1 |  |  | 29.3333
56 | End Cap | 28 | x | 16 |  |  |  | 1 |  |  | 3.1111
| TOTAL SQFT | [7 empty] | 0 | 244.5556 | 169.8056
|  | 12 |  | 10

## 1 (14)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 14 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
BRANCH 1
1 | Supply Air Duct Neck | 24 |  | 14 |  | 6 |  | 1 |  |  | 3.1667
2 | Supply Air Duct Round Square | 16 |  | 14 |  | 15 |  | 1 |  |  | 6.25
3 | Supply Air Duct Round Square | 16 |  | 14 |  | 15 |  | 1 |  |  | 6.25
4 | Supply Air Duct Neck | 30 |  | 14 |  | 6 |  | 1 |  |  | 3.6667
5 | Supply Air Duct | 16 |  | 14 |  | 225 |  | 1 |  |  | 93.75
6 | End Cap | 16 |  | 14 |  |  |  | 2 |  |  | 1.5556
| BRANCH 2 | [6 empty] | 1
1 | Supply Air Duct Neck | 16 |  | 12 |  | 6 |  | 1 |  |  | 2.3333
2 | Supply Air Duct | 8 |  | 12 |  | 46 |  | 1 |  |  | 12.7778
3 | Supply Air Duct Elbow | 8 |  | 12 |  | 33 |  | 1 |  |  | 9.1667
4 | Supply Air Duct | 8 |  | 12 |  | 88 |  | 1 |  |  | 24.4444
5 | End Cap | 8 |  | 12 |  |  |  | 1 |  |  | 0.66667
| BRANCH 3 | [6 empty] | 1
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 23 |  | 1 |  |  | 8.9444
| BRANCH 4 | [6 empty] | 1
1 | Supply Air Duct Neck | 24 |  | 12 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 16 |  | 12 |  | 39 |  | 1 |  |  | 15.1667
3 | Supply Air Duct Reducer | 16 | x | 12 |  | 24 |  | 1 |  |  | 8.6667
|  | 12 | x | 12
| TOTAL SQFT | [7 empty] | 0 | 0 | 202.8056
|  | 12 |  | 10

## 1 (15)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 15 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
BRANCH 4
4 | Supply Air Duct | 12 |  | 12 |  | 63 |  | 1 |  |  | 21
5 | Supply Air Duct Reducer | 12 | x | 12 |  | 18 |  | 1 |  |  | 5.5
|  | 8 | x | 12
6 | Supply Air Duct | 8 | x | 12 |  | 39 |  | 1 |  |  | 10.8333
7 | End Cap | 8 | x | 12 |  |  |  | 1 |  |  | 0.66667
BRANCH 5
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
| BRANCH 6 | [6 empty] | 1
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
| BRANCH 7 | [6 empty] | 1
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
| BRANCH 8 | [6 empty] | 1
1 | Supply Air Duct Neck | 24 |  | 10 |  | 6 |  | 1 |  |  | 2.8333
2 | Supply Air Duct | 16 |  | 10 |  | 27 |  | 1 |  |  | 9.75
3 | Supply Air Duct Elbow | 16 |  | 10 |  | 42 |  | 1 |  |  | 15.1667
4 | Supply Air Duct Offset | 16 |  | 10 |  | 23 |  | 1 |  |  | 8.3056
5 | Supply Air Duct Round Square | 16 |  | 10 |  | 15 |  | 1 |  |  | 5.4167
| TOTAL SQFT | [7 empty] | 0 | 0 | 119.9722
|  | 12 |  | 10

## 1 (16)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 16 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
BRANCH 8
6 | Supply Air Duct Round Square | 16 | x | 10 |  | 15 |  | 1 |  |  | 5.4167
7 | Supply Air Duct | 16 | x | 10 |  | 99 |  | 1 |  |  | 35.75
8 | End Cap | 16 | x | 10 |  |  |  | 1 |  |  | 1.1111
BRANCH 9
1 | Supply Air Duct | 14 |  | 12 |  | 39 |  | 1 |  |  | 14.0833
2 | Supply Air Duct Elbow | 14 |  | 12 |  | 38 |  | 1 |  |  | 13.7222
3 | Supply Air Duct Elbow | 14 |  | 12 |  | 38 |  | 1 |  |  | 13.7222
4 | Supply Air Duct | 14 |  | 12 |  | 291 |  | 1 |  |  | 105.0833
5 | Supply Air Duct Bridge Piece | 14 |  | 12 |  | 44 |  | 1 |  |  | 15.8889
6 | Supply Air Duct Elbow | 14 |  | 12 |  | 38 |  | 1 |  |  | 13.7222
7 | Supply Air Duct | 14 |  | 12 |  | 27 |  | 1 |  |  | 9.75
8 | Supply Air Duct Round Square | 14 |  | 12 |  | 15 |  | 1 |  |  | 5.4167
9 | Supply Air Duct Round Square | 14 |  | 12 |  | 15 |  | 1 |  |  | 5.4167
10 | Supply Air Duct | 14 |  | 12 |  | 147 |  | 1 |  |  | 53.0833
11 | End Cap | 14 |  | 12 |  |  |  | 1 |  |  | 1.1667
BRANCH 10
1 | Supply Air Duct Neck | 20 |  | 12 |  | 6 |  | 1 |  |  | 2.6667
2 | Supply Air Duct | 20 |  | 12 |  | 89 |  | 1 |  |  | 39.5556
3 | Supply Air Duct | 20 |  | 12 |  | 244 |  | 1 |  |  | 108.4444
4 | Supply Air Duct Elbow | 20 |  | 12 |  | 33 |  | 1 |  |  | 14.6667
| TOTAL SQFT | [7 empty] | 0 | 0 | 458.6667
|  | 12 |  | 10

## 1 (17)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 17 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
BRANCH 10
5 | Supply Air Duct | 20 | x | 12 |  | 195 |  | 1 |  |  | 86.6667
6 | End Cap | 20 | x | 12 |  |  |  | 1 |  |  | 1.6667
BRANCH 11
1 | Supply Air Duct Neck | 16 | x | 12 |  | 6 |  | 2 |  |  | 2.3333
2 | Supply Air Duct | 8 | x | 12 |  | 111 |  | 1 |  |  | 30.8333
3 | End Cap | 8 | x | 12 |  |  |  | 1 |  |  | 0.66667
4 | Supply Air Duct Neck | 28 | x | 8 |  | 6 |  | 1 |  |  | 3
5 | Supply Air Duct | 20 | x | 8 |  | 6 |  | 1 |  |  | 2.3333
BRANCH 12
1 | Supply Air Duct Neck | 28 | x | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 | x | 8 |  | 27 |  | 1 |  |  | 10.5
BRANCH 13
1 | Supply Air Duct | 12 | x | 12 |  | 48 |  | 1 |  |  | 16
2 | Supply Air Duct Reducer | 12 | x | 12 |  | 24 |  | 1 |  |  | 7.3333
|  | 8 | x | 12
3 | Supply Air Duct | 8 | x | 12 |  | 48 |  | 1 |  |  | 13.3333
4 | End Cap | 8 | x | 12 |  |  |  | 1 |  |  | 0.66667
BRANCH 14
1 | Supply Air Duct | 12 | x | 12 |  | 27 |  | 1 |  |  | 9
| TOTAL SQFT | [7 empty] | 0 | 0 | 187.3333
|  | 12 |  | 10

## 1 (18)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 18 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | AHU 02
BRANCH 14
2 | Supply Air Duct Reducer | 12 | x | 12 |  | 24 |  | 1 |  |  | 7.3333
|  | 8 | x | 12
3 | Supply Air Duct | 8 | x | 12 |  | 45 |  | 1 |  |  | 12.5
4 | End Cap | 8 | x | 12 |  |  |  | 1 |  |  | 0.66667
BRANCH 15
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
BRANCH 16
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
BRANCH 17
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
BRANCH 18
1 | Supply Air Duct Neck | 28 |  | 8 |  | 6 |  | 1 |  |  | 3
2 | Supply Air Duct | 20 |  | 8 |  | 27 |  | 1 |  |  | 10.5
| TOTAL SQFT | [7 empty] | 0 | 0 | 74.5
|  | 12 |  | 10

## 1 (19)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 19 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [6 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00
1 | Plenum Box | 12 | x | 10 |  | 36 |  | 1 |  |  | 11
2 | Plenum Box | 12 | x | 10 |  | 102 |  | 1 |  |  | 31.1667
3 | Plenum Box | 12 | x | 10 |  | 36 |  | 1 |  |  | 11
4 | Plenum Box | 12 | x | 10 |  | 36 |  | 1 |  |  | 11
5 | Plenum Box | 12 | x | 10 |  | 174 |  | 1 |  |  | 53.1667
6 | Plenum Box | 12 | x | 10 |  | 198 |  | 1 |  |  | 60.5
7 | Plenum Box | 12 | x | 10 |  | 282 |  | 1 |  |  | 86.1667
8 | Plenum Box | 12 | x | 10 |  | 90 |  | 1 |  |  | 27.5
9 | Plenum Box | 12 | x | 10 |  | 126 |  | 1 |  |  | 38.5
10 | Plenum Box | 12 | x | 10 |  | 102 |  | 1 |  |  | 31.1667
11 | Plenum Box | 12 | x | 10 |  | 102 |  | 1 |  |  | 31.1667
12 | Plenum Box | 12 | x | 10 |  | 78 |  | 1 |  |  | 23.8333
13 | Plenum Box | 12 | x | 10 |  | 174 |  | 1 |  |  | 53.1667
14 | Plenum Box | 12 | x | 10 |  | 54 |  | 1 |  |  | 16.5
15 | Plenum Box | 12 | x | 10 |  | 106 |  | 1 |  |  | 32.3889
16 | Plenum Box | 12 | x | 10 |  | 106 |  | 1 |  |  | 32.3889
17 | Plenum Box | 12 | x | 10 |  | 114 |  | 1 |  |  | 34.8333
18 | Plenum Box | 12 | x | 10 |  | 234 |  | 1 |  |  | 71.5
19 | Plenum Box | 12 | x | 10 |  | 150 |  | 1 |  |  | 45.8333
20 | Plenum Box | 12 | x | 10 |  | 150 |  | 1 |  |  | 45.8333
21 | Plenum Box | 12 | x | 10 |  | 150 |  | 1 |  |  | 45.8333
22 | Plenum Box | 12 | x | 10 |  | 174 |  | 1 |  |  | 53.1667
23 | Plenum Box End Caps | 12 | x | 10 |  |  |  | 44 |  |  | 36.6667
| TOTAL SQFT | [7 empty] | 0 | 0 | 873.2778
|  | 12 |  | 10

## 1 (20)
Project: | ENGRO, THF, 3RD Floor |  |  |  |  | Date: | Date:
Consultant: S Mehboob & Company | [5 empty] | Drawing No. | Drawing No. |  |  | RCP.07
Contractor: I.K ASSOCIATES | [5 empty] | Sheet # of | Sheet # 20 of |  |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  | Length (Inch) | Length (Inch) |  | Nos | SQFT
Item No. | [5 empty] | sqft. |  | 20 Gauge | 22 Gauge | 24 Gauge
23 31 00 | PLENUM NECKS
1 | Round Neck | 6 | Dia. |  | 6 |  | 2 |  |  | 1.571
2 | Round Neck | 6 | Dia. |  | 6 |  | 4 |  |  | 3.142
3 | Round Neck | 6 | Dia. |  | 6 |  | 2 |  |  | 1.571
4 | Round Neck | 6 | Dia. |  | 6 |  | 1 |  |  | 0.7855
5 | Round Neck | 8 | Dia. |  | 6 |  | 4 |  |  | 4.1893
6 | Round Neck | 8 | Dia. |  | 6 |  | 6 |  |  | 6.284
7 | Round Neck | 8 | Dia. |  | 6 |  | 8 |  |  | 8.3787
8 | Round Neck | 8 | Dia. |  | 6 |  | 3 |  |  | 3.142
9 | Round Neck | 8 | Dia. |  | 6 |  | 4 |  |  | 4.1893
10 | Round Neck | 8 | Dia. |  | 6 |  | 3 |  |  | 3.142
11 | Round Neck | 8 | Dia. |  | 6 |  | 3 |  |  | 3.142
12 | Round Neck | 6 | Dia. |  | 6 |  | 3 |  |  | 2.3565
13 | Round Neck | 8 | Dia. |  | 6 |  | 4 |  |  | 4.1893
14 | Round Neck | 8 | Dia. |  | 6 |  | 2 |  |  | 2.0947
15 | Round Neck | 8 | Dia. |  | 6 |  | 4 |  |  | 4.1893
16 | Round Neck | 8 | Dia. |  | 6 |  | 4 |  |  | 4.1893
17 | Round Neck | 8 | Dia. |  | 6 |  | 3 |  |  | 3.142
18 | Round Neck | 8 | Dia. |  | 6 |  | 8 |  |  | 8.3787
19 | Round Neck | 8 | Dia. |  | 6 |  | 6 |  |  | 6.284
20 | Round Neck | 8 | Dia. |  | 6 |  | 6 |  |  | 6.284
21 | Round Neck | 8 | Dia. |  | 6 |  | 5 |  |  | 5.2367
22 | Round Neck | 8 | Dia. |  | 6 |  | 6 |  |  | 6.284
| TOTAL SQFT | [6 empty] | 0 | 0 | 90.5943
|  | 12 | 10