## Variation 2
M/S IK ASSOCIATES | [6 empty] | 2024-09-23
Project: ENGRO - THF Karachi
Variation Order No 2
Variation order for Extra Work - For Third Floor ENGRO Office - THF Karachi
S. # | Description | Material Rate | Labour Rate | Unit | Qty | Total Rate | Amount
1 | Dismantling of G.I Sheet Metal Duct of 24 Gauge with accessories. |  | 77 | Sqft | 486.86 | 77 | 37488.22
2 | Supply of G.I Sheet Metal Duct of 24 Gauge. (BOQ Rate) | 405 | 77 | Sqft | 93 | 482 | 44826
3 | Supply, Installation of Closed cell elastromeric Insulation for above G.I Ducts. (BOQ Rate) | 594 | 63 | Sqft | 93 | 657 | 61101
4 | Re-Installation of G.I Sheet Metal Duct of 24 Gauge with accessories. |  | 77 | Sqft | 486.86 | 77 | 37488.22
5 | Repairing of Insulation of above G.I sheet metal duct. |  | 25000 | Job. | 1 | 25000 | 25000
6 | Repairing of G.I Sheet Metal Duct Work Due to Addition of Supply Air Registers. |  | 15000 | Job. | 1 | 15000 | 15000
7 | Dismantling of VAV's |  | 6750 | Nos. | 2 | 6750 | 13500
8 | Re-instllation of VAV's |  | 6750 | Nos. | 2 | 6750 | 13500
9 | Supply of Linear Slot Diffusers. (becomes useless due to design change)
10 | Supply Air Linear Slot Diffuser S.A.L.S.D
i. | 2/1"/96" (BOQ Rate) | 12600 |  | No. | 1 | 12600 | 12600
ii. | 3/1"/228" (BOQ Rate) | 26100 |  | No. | 1 | 26100 | 26100
iii. | 2/1"/54" (BOQ Rate) | 10800 |  | No. | 1 | 10800 | 10800
iv. | 2/1"/168" (BOQ Rate) | 18000 |  | No. | 1 | 18000 | 18000
11 | Return Air Linear Slot Diffuser R.A.L.S.D
i. | 2/1"/96" (BOQ Rate) | 10710 |  | No. | 1 | 10710 | 10710
ii. | 3/1"/228" (BOQ Rate) | 25650 |  | No. | 1 | 25650 | 25650
iii. | 3/1"/228" (BOQ Rate) | 25650 |  | No. | 1 | 25650 | 25650
12 | Dismantling of Concealed Pendent Sprinkler with Paint Finish (Quick Response) |  | 675 | No. | 7 | 675 | 4725
13 | Dismantling of Corrugated Stainless Steel Flexible Connector 1inch x 3ft (ULFM) |  | 900 | No. | 7 | 900 | 6300
14 | Dismantling of M.S Pipe of 1" Dia. |  | 189 | Rft. | 34 | 189 | 6426
15 | Re-Installation of M.S Pipe of 1" Dia. |  | 189 | Rft. | 34 | 189 | 6426
16 | Supply and installation of Mild Steel Schedule 40 pipe including all special fittings.
i. | 1" Dia. (BOQ Rate) For changing of sprinkler from concealed pendent to pendent sprinklers. | 711 | 189 | Rft. | 18 | 900 | 16200
ii. | 2-1/2" Dia. (BOQ Rate) For Fire Hose Cabinet | 1980 | 405 | Rft. | 60 | 2385 | 143100
17 | Painting of above M.S Piping Work | 20000 | 5000 | Job. | 1 | 25000 | 25000
18 | Installation of Fire Hose Cabinet |  | 18000 | No. | 1 | 18000 | 18000
19 | Making of Shop Drawings due to change in design |  | 45000 | Job. | 1 | 45000 | 45000
20 | Installation & Dismantling of UPVC Pipes for Drainage work for Mock up as per requirement of Architect |  | 45000 | Job. | 1 | 45000 | 45000
Total Amount Rs. | [6 empty] | 693590.44
For PIONEER ENGINEERING SERVICES.