## Summary
|  |  | Date | 02 July 2024
|  |  | Invoice # | 02
M/S DWP TECHNOLOGIES PVT LTD |  |  | NTN # | 4312149-7
5 – Zafar Ali Road Gulberg V, Lahore
NTN # 1547417-8
Project: PAF AIR WAR COLLEGE, KARACHI
Invoice
SUMMARY: FINAL BILL
S# | Description | Material Amount | Labour Amount | Total Amount
1 | HVAC Ground Floor | #REF! | #REF! | #REF!
2 | HVAC 1st Floor | #REF! | #REF! | #REF!
3 | HVAC 2nd Floor | #REF! | #REF! | #REF!
4 | HVAC 3rd Floor | #REF! | #REF! | #REF!
TOTAL AMOUNT |  | #REF! | #REF! | #REF!
SST 13% |  | 0 | 0 | #REF!
GRAND TOTAL AMOUNT |  | 0 | 0 | #REF!
Less Received 40% Adv (incl WHT) |  | 0 | 0 | 9063626
Payable Amount |  | 0 | 0 | #REF!
for PIONEER SERVICES

## Ground Duct
Ground Floor
ITEM NO. | DESCRIPTION | QTY | UNIT | Material |  |  | Labour
|  |  |  | 1st Bill Qty | 2nd Bill Qty | Total Qty | 1st Bill Qty | 2nd Bill Qty | Total Qty
AIR CONDITIONING WORK
1 | G.I. Duct & Allied Works
i | Supply & Installation of Duct 24 swg | 1830 | Sq. Ft | 1830 |  | 1830 | 1830 |  | 1830 | 1.269 | 543.7352 | 141.844
ii | Supply & Installation of Duct 22 swg | 700 | Sq. Ft | 700 |  | 700 | 700 |  | 700
iii | Supply & Isnt: Glass Wool Insulation on Ducts | 2530 | Sq. Ft | 2530 |  | 2530 | 2530 |  | 2530 | 1.269 | 189.1253 | 89.8345
iv | Flexible Duct Connector | 100 | RFt | 0 | 25 | 25 | 0 | 25 | 25 | 1.269 | 1576.0441 | 472.8132
2 | Air Devices
i | VCDs | 25 | Sq. Ft | 0 | 25 | 25 | 0 | 25 | 25 | 1.269 | 5200.9456 | 1134.7518
ii | Supply Air Diffusers (15" x 15") 42 qty | 66 | Sq. Ft | 66 |  | 66 | 0 | 46.88 | 46.88 | 1.269 | 5910.1655 | 945.6265
iii | Return Air Diffusers (15" x 15") 38 qty | 60 | Sq. Ft | 60 |  | 60 | 0 | 37.5 | 37.5 | 1.269 | 6698.1875 | 945.6265
iv | Return Air Grill (9" x 9") 20 qty | 12 | Sq. Ft | 12 |  | 12 | 0 |  | 0 | 1.269 | 5910.1655 | 945.6265
v | Exhaust Air Louver (as per drawings) | 1 | Job | 0 | 0 | 0 | 0 |  | 0 | 1.269 | 5910.1655 | 945.6265
vi | Testing of Ducts. | 1 | 0 |  |  | 0 |  | 1 | 1 | 1.269 | 0 | 51221.4342

## First Duct
1st Floor
ITEM NO. | DESCRIPTION | QTY | UNIT | Material |  |  | Labour
|  |  |  | 1st Bill Qty | 2nd Bill Qty | Total Qty | 1st Bill Qty | 2nd Bill Qty | Total Qty
1 | G.I. Duct & Allied Works
i | Supply & Installation of Duct 24 swg | 1893.76 | Sq. Ft | 1894 |  | 1894 | 1894 |  | 1894 | 1.269 | 543.7352 | 141.844
ii | Supply & Installation of Duct 22 swg | 2797.6 | Sq. Ft | 2798 |  | 2798 | 2798 |  | 2798
iii | Supply & Isnt: Glass Wool Insulation on Ducts | 4691 | Sq. Ft | 4691 |  | 4691 | 4691 |  | 4691 | 1.269 | 189.1253 | 89.8345
a | Flexible Duct Connector | 250 | RFt | 0 | 130 | 130 | 0 | 130 | 130 | 1.269 | 1576.0441 | 472.8132
2 | Air Devices
i | VCDs | 40 | Sq. Ft | 40 |  | 40 |  | 40 | 40 | 1.269 | 5200.9456 | 1134.7518
ii | Supply Air Diffusers (15" x 15") 63 qty | 97.8 | Sq. Ft | 98 |  | 98 | 0 | 92.2 | 92.2 | 1.269 | 5910.1655 | 945.6265
iii | Return Air Diffusers (15" x 15") 49 qty | 76.07 | Sq. Ft | 76 |  | 76 | 0 | 85.94 | 85.94 | 1.269 | 6698.1875 | 945.6265
iv | Return Air Grill 9" x 9" 14 qty | 84.68 | Sq. Ft | 85 |  | 85 | 0 | 85 | 85 | 1.269 | 5910.1655 | 945.6265
v | Testing of Ducts. | 1 | Job |  |  |  | 0 | 1 | 1 | 1.269 | 0 | 51221.4342

## Second Duct
Second Floor
ITEM NO. | DESCRIPTION | QTY | UNIT | Material |  |  | Labour
|  |  |  | 1st Bill Qty | 2nd Bill Qty | Total Qty | 1st Bill Qty | 2nd Bill Qty | Total Qty
1 | G.I. Duct & Allied Works
i | Supply & Installation of Duct 24 swg | 1205.12 | Sq. Ft | 1205 |  | 1205 | 1205 | 0 | 1205 | 1.269 | 543.7352 | 141.844
ii | Supply & Installation of Duct 22 swg | 7639.6 | Sq. Ft | 7640 |  | 7640 | 7640 | 0 | 7640
iii | Supply & Isnt: Glass Wool Insulation on Ducts | 8845 | Sq. Ft | 8845 |  | 8845 | 8845 | 0 | 8845 | 1.269 | 189.1253 | 89.8345
iv | Flexible Duct Connector | 700 | RFt | 0 | 260 | 260 | 0 | 260 | 260 | 1.269 | 1576.0441 | 472.8132
2 | Air Devices
i | VCDs | 75 | Sq. Ft | 0 | 75 | 75 | 0 | 75 | 75 | 1.269 | 5200.9456 | 1134.7518
ii | Supply Air Diffusers (12" x 12") 2 Qty (15" x 15") 174 qty | 272.98 | Sq. Ft | 273 |  | 273 | 0 | 262.5 | 262.5 | 1.269 | 5910.1655 | 945.6265
iii | Return Air Diffusers (15" x 15") 134 qty | 215.2 | Sq. Ft | 215 |  | 215 | 0 | 246.9 | 246.9 | 1.269 | 6698.1875 | 945.6265
iv | Return Air Grill 9" x 9" 22 qty | 12.37 | Sq. Ft | 12 |  | 12 | 0 |  | 0 | 1.269 | 5910.1655 | 945.6265
v | Testing of Ducts. | 1 | Job |  |  |  |  | 1 | 1 | 1.269 | 0 | 51221.4342

## Third Duct
Third Floor
ITEM NO. | DESCRIPTION | QTY | UNIT | Material |  |  | Labour
|  |  |  | 1st Bill Qty | 2nd Bill Qty | Total Qty | 1st Bill Qty | 2nd Bill Qty | Total Qty
1 | G.I. Duct & Allied Works
i | Supply & Installation of Duct 24 swg | 2603.92 | Sq. Ft | 2604 |  | 2604 | 2604 | 0 | 2604 | 1.269 | 543.7352 | 141.844
ii | Supply & Installation of Duct 22 swg | 3507.76 | Sq. Ft | 3508 |  | 3508 | 3508 | 0 | 3508
iii | Supply & Installation of Flexible duct connector minimum 3" wide as shown in the drawings and directed by the engineer in charge.
iv | Flexible Duct Connector | 50 | RFt | 0 | 50 | 50 | 0 | 50 | 50 | 1.269 | 1576.0441 | 472.8132
2 | Air Devices
i | VCDs | 75 | Sq. Ft | 0 | 75 | 75 | 0 | 75 | 75 | 1.269 | 5200.9456 | 1134.7518
ii | Supply Air Diffusers (12" x 12") 16 qty (15 x 15 ) 100 qty | 172.16 | Sq. Ft | 90 | 51 | 141 | 0 | 153 | 153 | 1.269 | 5910.1655 | 945.6265
iii | Return Air Diffusers (12" x 12") 16 qty (15" x 15") 85 qty | 150.64 | Sq. Ft | 90 | 37.224 | 127.224 | 0 | 134 | 134 | 1.269 | 6698.1875 | 945.6265
iv | Return Air Grill 9" x 9" 11 qty | 5.7 | Sq. Ft | 6 |  | 6 | 0 | 6 | 6 | 1.269 | 5910.1655 | 945.6265
v | Testing of Ducts. | 1 | Job | 0 | 1 | 1 | 0 | 1 | 1 | 1.269 | 0 | 51221.4342

## Vairation
Variation Amount
ITEM NO. | DESCRIPTION | QTY | UNIT | Material |  |  | Labour
|  |  |  | 1st Bill Qty | 2nd Bill Qty | Total Qty | 1st Bill Qty | 2nd Bill Qty | Total Qty
AIR CONDITIONING WORK
i | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | 13000 | Sqft | 9023 | 3977 | 13000 | 9023 | 3977 | 13000 | 1.269 | 543.7352 | 141.844
ii | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | 13000 | Sqft | 9023 | 3977 | 13000 | 9023 | 3977 | 13000
iii | Supply & installation of Pre-insulated flexible duct 8" Dia. | 300 | Rft | 275 | 25 | 300 | 275 | 25 | 300 | 1.269 | 189.1253 | 89.8345
iv | Providing and installation Jubilee clamp 10" for flexible duct. | 120 | Nos | 84 | 36 | 120 | 84 | 36 | 120 | 1.269 | 5910.1655 | 945.6265
v | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | 120 | Nos | 84 | 36 | 120 | 84 | 36 | 120 | 1.269 | 6698.1875 | 945.6265
vu | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | 60 | Nos | 42 | 18 | 60 | 42 | 18 | 60 | 1.269 | 5910.1655 | 945.6265
vii | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | 60 | Nos | 42 | 18 | 60 | 42 | 18 | 60 | 1.269 | 5910.1655 | 945.6265