## Table 1
Final Bill
Bank Al Habib Limited
Replace of overhead fill PPRC pipe | [9 empty] | Date: 10-06-2025
BILL OF QUANTITIES (Contract Amount) | [8 empty] | Executed work done
S.No. | Description | Unit | Qty | Rate |  | Amount |  | Total | Bill Qty | Material Amount | Labour Amount | Total Amount
|  |  |  | Material | Labour | Material | Labour | Amount Rs.
Replace of overhead fill PPRC pipe
1 | Supply and installation of Polypropylene Random PP-R pipes PN 20 and fittings with fusion jointing along with all types of unions, tees, bends, sockets, clamps, lindapter supports hangers, sleeves, masking plates, chiseling, making holes making good, excavation, bedding backfilling as required complete in all respect, ready to operate as per instruction of Consultant. Dia. OD 110 mm | RM | 140 | 15085 | 1000 | 2111900 | 140000 | 2251900 | 138 | 2081730 | 138000 | 2219730
2 | Cutting dismantling and shifting of the existing MS pipe 4 inch dia of the mentioned length (140 M - Approx) as per instruction of consultant, including cleaning the site and shifting the dismantled pipe to suitable place given by client complete in all respects
| Total Amount of Bill |  |  |  |  | 2111900 | 140000 | 2251900 |  | 2081730 | 138000 | 2219730
| Add 15% SST |  |  |  |  | 316785 | 21000 | 337785 |  | 312259.5 | 20700 | 332959.5
| Total Fixed Amount Including Taxes |  |  |  |  | 2428685 | 161000 | 2589685 |  | 2393989.5 | 158700 | 2552689.5
| Received amount | [8 empty] | 498408.4 | 32200 | 530608.4
| Payable Amount | [8 empty] | 1895581.1 | 126500 | 2022081.1
Payment Terms
1) 20% advance / Mobilization
2) 40% after completion of 50% work.
3) 30% after completion of remaining 50% work.
4) 10% after successful testing & commissioning.