## Grand Summary
Rehmat Shipping
| Divisions | Description of Work | Amounts
| 1 | ACMV | 5000000
| 2 | Variation for cable tray | 139008
|  | Grand Total (in PKR): | 5139008
|  | ADD 4.5% Tax | 231255.36
|  | GRAND TOTAL | 5370263.36
|  | Received | #VALUE!
|  | Remaining | #VALUE!

## HVAC
SECTION II: BILL OF QUANTITIES FOR MECHANICAL WORKS
1 | 2 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 2 | 3 | 4 | 5 | 5 x 3 | 7 | 7 x 3 | 6 + 8
All Air Conditioning, Mechanical Ventilation Works shall be completed, tested and commissioned as per drawings,specifications, ready to operate and as per the instruction of Client/Consultant.
1 | 23 81 29 | Unloading, rigging, lifting, placement at respective location, installation, testing and commissioning of (VRF) multi split type air conditioning units (Owner Supplied) of different capacities (as per mentioned in schedule) complete in all respects, ready to operate. Including supply of supports, brackets, flexible duct connection, rubber isolator, flashing, gas charging, control wiring & power wiring (connection) in G.I. for external / PVC for internal from outdoor unit to indoor unit complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
a |  | Mini VRF Indoor Units
i |  | EF-CT-WORKSTATION-01 | 2 | No. | 15000 | 30000 | 7000 | 14000 | 44000
ii |  | EF-CT-WORKSTATION-02 | 2 | Nos. | 15000 | 30000 | 7000 | 14000 | 44000
iii |  | EF-CT-WORKSTATION-03 | 2 | No. | 15000 | 30000 | 7000 | 14000 | 44000
iv |  | EF-CT-WORKSTATION-04 | 1 | No. | 15000 | 15000 | 7000 | 7000 | 22000
v |  | EF-CT-WORKSTATION-05 | 2 | No. | 15000 | 30000 | 7000 | 14000 | 44000
vi |  | EF-CT-WORKSTATION-06 | 2 | No. | 15000 | 30000 | 7000 | 14000 | 44000
vii |  | EF-AC-MANAGER-01 | 1 | No. | 10000 | 10000 | 7000 | 7000 | 17000
viii |  | EF-AC-MANAGER-02 | 1 | No. | 12000 | 12000 | 7000 | 7000 | 19000
ix |  | EF-AC-MANAGER-03 | 1 | No. | 10000 | 10000 | 7000 | 7000 | 17000
x |  | EF-CT-LOUNGE | 1 | No. | 7000 | 7000 | 7000 | 7000 | 14000
xi |  | EF-CT-RECEPTION | 2 | No. | 7000 | 14000 | 7000 | 14000 | 28000
xii |  | EF-CT-CONFERENCE | 2 | No. | 10000 | 20000 | 7000 | 14000 | 34000
xiii |  | EF-AC-MEETING ROOM | 1 | No. | 10000 | 10000 | 7000 | 7000 | 17000
xiv |  | EF-CT-LOUNGE | 1 | No. | 10000 | 10000 | 7000 | 7000 | 17000
xvii |  | EF-CT-MEETING-01 | 1 | No. | 7000 | 7000 | 7000 | 7000 | 14000
SECTION II: BILL OF QUANTITIES FOR MECHANICAL WORKS |  | EF-CT-MEETING-02 | 1 | No. | 10000 | 10000 | 7000 | 7000 | 17000
xix |  | EF-CT-MEETING-03 | 1 | No. | 10000 | 10000 | 7000 | 7000 | 17000
b |  | MINI VRF Condensing Units
i |  | CU-01 (Side Discharge) | 1 | No. | 15000 | 15000 | 15000 | 15000 | 30000
ii |  | CU-02 (Side Discharge) | 1 | No. | 15000 | 15000 | 15000 | 15000 | 30000
iii |  | CU-03 (Side Discharge) | 1 | No. | 15000 | 15000 | 15000 | 15000 | 30000
iv |  | CU-04 (Side Discharge) | 1 |  | 18000 | 18000 | 15000 | 15000 | 33000
2 |  | Installation & Commissioning of Heat Recovery Ventilator Units as per drawing and specificaiton complete with all respect ready to operate.
i |  | EF-HRV-01 | 1 | No. | 15000 | 15000 | 15000 | 15000 | 30000
ii |  | EF-HRV-02 | 1 | No. | 15000 | 15000 | 15000 | 15000 | 30000
3 | 23 81 29 | Supply, installation, testing and commissioning of refrigerant pipes (liquid + gas) with hangers and supports including 19mm thick expended rubber foam insulation, PVC tape wrapping + control wiring from indoor to outdoor including Gas charging if required and installation of branch distributor (supplied with units) complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. (Hard pipe shall be used before Y-branch and soft pipe shall be used after Y-branch. Supplier shall extract refrigerant piping based on his respective equipment selections)
i |  | Ø1/4 | 160 | Rft | 740 | 118400 | 250 | 40000 | 158400
ii |  | Ø3/8 | 360 | Rft | 780 | 280800 | 250 | 90000 | 370800
iii |  | Ø1/2 | 410 | Rft | 1100 | 451000 | 250 | 102500 | 553500
iv |  | Ø5/8 | 260 | Rft | 1480 | 384800 | 250 | 65000 | 449800
v |  | Ø3/4 | 145 | Rft | 1660 | 240700 | 250 | 36250 | 276950
vi |  | Ø1 | 150 | Rft | 3200 | 480000 | 250 | 37500 | 517500
vii |  | Ø1-1/8 | 185 | Rft | 3360 | 621600 | 250 | 46250 | 667850
4 | 23 21 14 | Supply, Installation & Commissioning of U-PVC piping condensate drain including all cutting, fixing fitting, laying, cleaning and making good with 20mm thick Pre-moulded closed cell pipe insulation of 25-30kg/cum density, mean K value 0.035 , Fire class O as per BS-467 (Fire spread of flame) and propagation FSI<25 & SDI<30, as per ASTM E84, for drain water piping . The insulation material shall have water absorption less than 0.06% after 24 hours as per ASTM c209:1998. The joints shall be properly sealed with manufacturer recommended solution and tape on circumferential joints and on longitudinal joints. The insulation to be continuous as per good installation practice. The insulation shall be with Alupet foil protection. Rigid polymeric Cellular foam inserts of density 170-330 kg/m3, compression strength 20 kg/cm2 shall be used for pipe hangers and supports. complete in all respect as per drawings and specifications.
i |  | 3/4" Diameter | 350 | RFT | 600 | 210000 | 100 | 35000 | 245000
ii |  | 1" Diameter | 450 | RFT | 770 | 346500 | 100 | 45000 | 391500
5 | 23 31 00 | Supply, fabrication and installation of Pre-Insulated internal Ductwork of Polyurethane foam panel with 52 Kg/m3 density, 20 mm thickness, coated on both sides with 80 micron thick aluminum foil complete with a 2 g/m2 layer for internal duct work including manufacturer's aluminum hardware glue, Hot Dipped galvanized hangers and supports, flexible duct connection, wooden frame, etc.complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | 600 | Sq.ft | 560 | 336000 | 95 | 57000 | 393000
6 | 23 37 13 | Supply, Installation and Commissioning of Supply Air Devices including connections with air ducts and supports arrangements, as follows:
a |  | Fresh Air Grill (F.A.G)
i |  | 22"x 8" | 2 | No. | 4500 | 9000 | 1000 | 2000 | 11000
b |  | Exhaust Air Louver (E.A.L)
i |  | 20"x8" | 2 | Nos. | 3800 | 7600 | 1000 | 2000 | 9600
c |  | Fresh Air Louver (F.A.L)
i |  | 22"x 8" | 2 | Nos. | 5500 | 11000 | 1000 | 2000 | 13000
d |  | DISK VALVE (D.V)
i |  | Ø6" | 12 | No. | 3200 | 38400 | 700 | 8400 | 46800
7 |  | MISCELLANEOUS
i |  | Supply, Installation & commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 10000 | 10000 | 10000 | 10000 | 20000
ii |  | Supply, Installation & commissioning of foundation for pipes and equipment including all noise and Vibration controller as per drawings and specifications. | 1 | Job | 20000 | 20000 | 20000 | 20000 | 40000
iii | 23 05 29 | Supply, Installation & commissioning of hangers and supports for pipes, ducts and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 117000 | 117000 | 35000 | 35000 | 152000
iv |  | Civil Work wall cutting, core cutting, cheiseling etc. as per drawings and as per instructions of Client / Consultant. | 1 | Job | 0 | 0 | 0 | 0 | 0
v |  | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 15000 | 15000 | 7000 | 7000 | 22000
vi |  | Supply, installation and commisioning of MCC | 1 | Job |  | 0 | 15000 | 15000 | 15000
8 |  | Drawings
i |  | Shop Drawings and As-built Drawings as per specifications. | 1 | Job | 12000 | 12000 | 12000 | 12000 | 24000
9 | 23 05 93 | Testing & Commissioning
i |  | HVAC System. | 1 | Job |  | 0 | 125000 | 125000 | 125000
10 |  | Sundries
i |  | Supply, installtion and commissioning of items Listed or not listed in BOQ but required. (Contractor to specify the list of missing items if there is any.) | 1 | Job |  | 0 |  | 0 | 0
Grand Total for HVAC Works | [8 empty] | 5138700
[8 empty] | Approved | 5000000