## Summary
|  |  | Date | 26 Sept 2023
|  |  | Invoice # | 02
M/S DWP Technologies PVT Ltd |  |  | NTN # | 4312149-7
Suit No. 102, First Floor, Fortune Center,
Shahrah-e-Faisal, Karachi.
NTN # 1547417-8
Project: PAF AIR WAR COLLEGE, KARACHI
Invoice
SUMMARY: FINAL BILL
S# | Description | Material Amount | Labour Amount | Total Amount
1 | HVAC Ground Floor | 126300 | 45406 | 171706
2 | HVAC 1st Floor | 120000 | 78276 | 198276
3 | HVAC 2nd Floor | 570900 | 150988 | 721888
4 | HVAC 3rd Floor | 814106.4 | 106657.44 | 920763.84
TOTAL AMOUNT |  | 1631306.4 | 381327.44 | 2012633.84
SST 13% |  | 0 | 0 | 261642.3992
GRAND TOTAL AMOUNT |  | 0 | 0 | 2274275
Less Received 40% Adv (incl WHT) |  | 0 | 0 | 9063626
Payable Amount |  | 0 | 0 | -6789351
for PIONEER SERVICES
PIONEER SERVICES

## Ground Duct
PAF AIR WAR COLLEGE, KARACHI
BILL OF QUANTITIES (Ground Floor) | [5 empty] | FINAL BILL
ITEM NO. | DESCRIPTION | QTY | UNIT | Rates |  | Material |  |  |  | Labour |  |  |  | Bill Amount
|  |  |  | Material | Labour | Prv Qty | Billed Qty | Total Qty | Amount | Prv Qty | Billed Qty | Total Qty | Amount
2 | G.I. Duct & Allied Works
2.1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal including hanger & supports and all tees, bends, reducers, elbows, turning vanes, and splitter etc. complete as specified in the specifications, shown on the layout drawing and standards drawing. Following Gauge chart shall be followed as per below mentioned sizes:
a | Supply & Installation of Duct 24 swg | 1830 | Sq. Ft | 270 | 70 | 1830 |  | 1830 | 0 | 1830 |  | 1830 | 0 | 0 | 1.269 | 543.7352 | 141.844
b | Supply & Installation of Duct 22 swg | 700 | Sq. Ft | 270 | 70 | 700 |  | 700 | 0 | 700 |  | 700 | 0 | 0
2.2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping with antifungal paint around duct with adhesive. All longitudinal and circumferential joints shall be sealed with 2” wide adhesive tape as specified in the specifications and shown on the drawing.
a | Supply & Isnt: Glass Wool Insulation on Ducts | 2530 | Sq. Ft | 127 | 65 | 2530 |  | 2530 | 0 | 2530 |  | 2530 | 0 | 0 | 1.269 | 189.1253 | 89.8345
2.4 | Supply & Installation of Flexible duct connector minimum 3" wide as shown in the drawings and directed by the engineer in charge.
a | Flexible Duct Connector | 100 | RFt | 480 | 40 | 0 | 100 | 100 | 48000 | 0 | 100 | 100 | 4000 | 52000 | 1.269 | 1576.0441 | 472.8132
3 | Air Devices
3.1 | Supply & Installation of opposed blade Volume Control Dampers made from 16 SWG. G.I sheets as specified in the specifications, shown on the drawings.
a | VCDs | 25 | Sq. Ft | 3132 | 162 | 0 | 25 | 25 | 78300 | 0 | 25 | 25 | 4050 | 82350 | 1.269 | 5200.9456 | 1134.7518
3.2 | Supply & installation of Supply Air Diffusers / Return Air Grills powder coated complete as specified in the specifications, shown on the drawing. | [10 empty] | 0
a | Supply Air Diffusers (15" x 15") 42 qty | 66 | Sq. Ft | 3888 | 162 | 66 |  | 66 | 0 | 0 | 66 | 66 | 10692 | 10692 | 1.269 | 5910.1655 | 945.6265
b | Return Air Diffusers (15" x 15") 38 qty | 60 | Sq. Ft | 3888 | 162 | 60 |  | 60 | 0 | 0 | 60 | 60 | 9720 | 9720 | 1.269 | 6698.1875 | 945.6265
c | Return Air Grill (9" x 9") 20 qty | 12 | Sq. Ft | 3888 | 162 | 12 |  | 12 | 0 | 0 | 12 | 12 | 1944 | 1944 | 1.269 | 5910.1655 | 945.6265
d | Exhaust Air Louver (as per drawings) | 1 | Job |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1.269 | 5910.1655 | 945.6265
b
Testing and Balancing
c | Testing of Ducts. | 1 | 0 | 0 | 15000 |  |  | 0 | 0 |  | 1 | 1 | 15000 | 15000 | 1.269 | 0 | 51221.4342
Total Amout Rs | [8 empty] | 126300 |  |  |  | 45406 | 171706 |  |  |  | 36374947.8708 | -36203241.8708
0.0075973
[5 empty] | 22601000 | [8 empty] | #REF!
0

## First Duct
PAF AIR WAR COLLEGE, KARACHI
BILL OF QUANTITIES (1st Floor) | [5 empty] | FINAL BILL
ITEM NO. | DESCRIPTION | QTY | UNIT | Rates |  | Material |  |  |  | Labour |  |  |  | Total Amount
|  |  |  | Material | Labour | Prv Qty | Billed Qty | Total Qty | Amount | Prv Qty | Billed Qty | Total Qty | Amount
AIR CONDITIONING WORK
2 | G.I. Duct & Allied Works
2.1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal including hanger & supports and all tees, bends, reducers, elbows, turning vanes, and splitter etc. complete as specified in the specifications, shown on the layout drawing and standards drawing. Following Gauge chart shall be followed as per below mentioned sizes:
a | Supply & Installation of Duct 24 swg | 1893.76 | Sq. Ft | 270 | 70 | 1894 |  | 1894 | 0 | 1894 |  | 1894 | 0 | 0 | 1.269 | 543.7352 | 141.844
b | Supply & Installation of Duct 22 swg | 2797.6 | Sq. Ft | 270 | 70 | 2798 |  | 2798 | 0 | 2798 |  | 2798 | 0 | 0
2.2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping with antifungal paint around duct with adhesive. All longitudinal and circumferential joints shall be sealed with 2” wide adhesive tape as specified in the specifications and shown on the drawing.
a | Supply & Isnt: Glass Wool Insulation on Ducts | 4691 | Sq. Ft | 127 | 65 | 4691 |  | 4691 | 0 | 4691 |  | 4691 | 0 | 0 | 1.269 | 189.1253 | 89.8345
2.3 | Supply & Installation of 1” thick, 24 kg/m3 density Sound Liner in supply ducts up 5’ from fan discharge with 100% surface applied with adhesive and mechanical fastness with washes 1.25 dia on the inner side of the duct at 12” centre to centre complete in all respect as specified in the specifications.
2.4 | Supply & Installation of Flexible duct connector minimum 3" wide as shown in the drawings and directed by the engineer in charge.
a | Flexible Duct Connector | 250 | RFt | 480 | 40 | 0 | 250 | 250 | 120000 | 0 | 250 | 250 | 10000 | 130000 | 1.269 | 1576.0441 | 472.8132
3 | Air Devices
3.1 | Supply & Installation of opposed blade Volume Control Dampers made from 16 SWG. G.I sheets as specified in the specifications, shown on the drawings.
a | VCDs | 40 | Sq. Ft | 3132 | 162 | 40 |  | 40 | 0 |  | 40 | 40 | 6480 | 6480 | 1.269 | 5200.9456 | 1134.7518
3.2 | Supply & installation of Supply Air Diffusers / Return Air Grills powder coated complete as specified in the specifications, shown on the drawing. | [6 empty] | 0 |  |  |  | 0
a | Supply Air Diffusers (15" x 15") 63 qty | 97.8 | Sq. Ft | 3888 | 162 | 98 |  | 98 | 0 | 0 | 98 | 98 | 15876 | 15876 | 1.269 | 5910.1655 | 945.6265
b | Return Air Diffusers (15" x 15") 49 qty | 76.07 | Sq. Ft | 3888 | 162 | 76 |  | 76 | 0 | 0 | 76 | 76 | 12312 | 12312 | 1.269 | 6698.1875 | 945.6265
4.2 | Return Air Grill 9" x 9" 14 qty | 84.68 | Sq. Ft | 3888 | 162 | 85 |  | 85 | 0 | 0 | 84 | 84 | 13608 | 13608 | 1.269 | 5910.1655 | 945.6265
a
9 | Testing and Balancing
| Testing of Ducts. | 1 | Job |  | 20000 |  |  |  | 0 | 0 | 1 | 1 | 20000 | 20000 | 1.269 | 0 | 51221.4342
Total Amout Rs | [8 empty] | 120000 |  |  |  | 78276 | 198276 | 10.152 | 26028.3688 | 55897.5571 | 0 | 0
Note: 1. If required additional work or material except above then it will be charge additionally. 2. Electrical Wiring/DB/MCC is not included in the scope of wrok 3. BMS connectivity and cabling is not included in the scope work 4. Any other item didn't mentioned above will be cahgred additionally 5. Above mentioned quantities may vary as per the approved design of consultant
0.0034634
[5 empty] | 22601000 | [7 empty] | #REF!
0

## Second Duct
PAF AIR WAR COLLEGE, KARACHI
BILL OF QUANTITIES (2nd Floor) | [5 empty] | FINAL BILL
ITEM NO. | DESCRIPTION | QTY | UNIT | Rates |  | Material |  |  |  | Labour |  |  |  | Total Amount
|  |  |  | Material | Labour | Prv Qty | Billed Qty | Total Qty | Amount | Prv Qty | Billed Qty | Total Qty | Amount
AIR CONDITIONING WORK
2 | G.I. Duct & Allied Works
2.1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal including hanger & supports and all tees, bends, reducers, elbows, turning vanes, and splitter etc. complete as specified in the specifications, shown on the layout drawing and standards drawing. Following Gauge chart shall be followed as per below mentioned sizes:
a | Supply & Installation of Duct 24 swg | 1205.12 | Sq. Ft | 270 | 70 | 1205 |  | 1205 | 0 | 1205 | 0 | 1205 | 0 | 0 | 1.269 | 543.7352 | 141.844
b | Supply & Installation of Duct 22 swg | 7639.6 | Sq. Ft | 270 | 70 | 7640 |  | 7640 | 0 | 7640 | 0 | 7640 | 0 | 0
2.2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping with antifungal paint around duct with adhesive. All longitudinal and circumferential joints shall be sealed with 2” wide adhesive tape as specified in the specifications and shown on the drawing.
a | Supply & Isnt: Glass Wool Insulation on Ducts | 8845 | Sq. Ft | 127 | 65 | 8845 |  | 8845 | 0 | 8845 | 0 | 8845 | 0 | 0 | 1.269 | 189.1253 | 89.8345
2.3 | Supply & Installation of 1” thick, 24 kg/m3 density Sound Liner in supply ducts up 5’ from fan discharge with 100% surface applied with adhesive and mechanical fastness with washes 1.25 dia on the inner side of the duct at 12” centre to centre complete in all respect as specified in the specifications.
2.4 | Supply & Installation of Flexible duct connector minimum 3" wide as shown in the drawings and directed by the engineer in charge.
a | Flexible Duct Connector | 700 | RFt | 480 | 40 | 0 | 700 | 700 | 336000 | 0 | 700 | 700 | 28000 | 364000 | 1.269 | 1576.0441 | 472.8132
3 | Air Devices
3.1 | Supply & Installation of opposed blade Volume Control Dampers made from 16 SWG. G.I sheets as specified in the specifications, shown on the drawings.
a | VCDs | 75 | Sq. Ft | 3132 | 162 | 0 | 75 | 75 | 234900 | 0 | 75 | 75 | 12150 | 247050 | 1.269 | 5200.9456 | 1134.7518
3.2 | Supply & installation of Supply Air Diffusers / Return Air Grills powder coated complete as specified in the specifications, shown on the drawing.
a | Supply Air Diffusers (12" x 12") 2 Qty (15" x 15") 174 qty | 272.98 | Sq. Ft | 3888 | 162 | 273 |  | 273 | 0 | 0 | 272 | 272 | 44064 | 44064 | 1.269 | 5910.1655 | 945.6265
b | Return Air Diffusers (15" x 15") 134 qty | 215.2 | Sq. Ft | 3888 | 162 | 215 |  | 215 | 0 | 0 | 215 | 215 | 34830 | 34830 | 1.269 | 6698.1875 | 945.6265
4.2 | Return Air Grill 9" x 9" 22 qty | 12.37 | Sq. Ft | 3888 | 162 | 12 |  | 12 | 0 | 0 | 12 | 12 | 1944 | 1944 | 1.269 | 5910.1655 | 945.6265
a
9 | Testing and Balancing
| Testing of Ducts. | 1 | Job |  | 30000 |  |  |  | 0 |  | 1 | 1 | 30000 | 30000 | 1.269 | 0 | 51221.4342
Total Amout Rs | [8 empty] | 570900 |  |  |  | 150988 | 721888 |  |  |  | 36374947.8708 | -36223959.8708
Note: 1. If required additional work or material except above then it will be charge additionally. 2. Electrical Wiring/DB/MCC is not included in the scope of wrok 3. BMS connectivity and cabling is not included in the scope work 4. Any other item didn't mentioned above will be cahgred additionally 5. Above mentioned quantities may vary as per the approved design of consultant
0.0066806
[5 empty] | 22601000 | [7 empty] | #REF!
0

## Third Duct
PAF AIR WAR COLLEGE, KARACHI
BILL OF QUANTITIES (3rd Floor) | [5 empty] | FINAL BILL
ITEM NO. | DESCRIPTION | QTY | UNIT | Rates |  | Material |  |  |  | Labour |  |  |  | Total Amount
|  |  |  | Material | Labour | Prv Qty | Billed Qty | Total Qty | Amount | Prv Qty | Billed Qty | Total Qty | Amount
AIR CONDITIONING WORK
2 | G.I. Duct & Allied Works
2.1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal including hanger & supports and all tees, bends, reducers, elbows, turning vanes, and splitter etc. complete as specified in the specifications, shown on the layout drawing and standards drawing. Following Gauge chart shall be followed as per below mentioned sizes:
a | Supply & Installation of Duct 24 swg | 2603.92 | Sq. Ft | 270 | 70 | 2604 |  | 2604 | 0 | 2604 | 0 | 2604 | 0 | 0 | 1.269 | 543.7352 | 141.844
b | Supply & Installation of Duct 22 swg | 3507.76 | Sq. Ft | 270 | 70 | 3508 |  | 3508 | 0 | 3508 | 0 | 3508 | 0 | 0
c | Supply & Installation of Duct 20 swg | 3389.4 | Sq. Ft | 300 | 70 | 3389 |  | 3389 | 0 | 3389 | 0 | 3389 | 0 | 0
2.2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping with antifungal paint around duct with adhesive. All longitudinal and circumferential joints shall be sealed with 2” wide adhesive tape as specified in the specifications and shown on the drawing.
a | Supply & Isnt: Glass Wool Insulation on Ducts | 9501 | Sq. Ft | 127 | 65 | 9501 |  | 9501 | 0 | 9501 | 0 | 9501 | 0 | 0 | 1.269 | 189.1253 | 89.8345
2.4 | Supply & Installation of Flexible duct connector minimum 3" wide as shown in the drawings and directed by the engineer in charge.
a | Flexible Duct Connector | 50 | RFt | 480 | 40 | 0 | 50 | 50 | 24000 | 0 | 50 | 50 | 2000 | 26000 | 1.269 | 1576.0441 | 472.8132
3 | Air Devices
3.1 | Supply & Installation of opposed blade Volume Control Dampers made from 16 SWG. G.I sheets as specified in the specifications, shown on the drawings.
a | VCDs | 75 | Sq. Ft | 3132 | 162 | 0 | 75 | 75 | 234900 | 0 | 75 | 75 | 12150 | 247050 | 1.269 | 5200.9456 | 1134.7518
3.2 | Supply & installation of Supply Air Diffusers / Return Air Grills powder coated complete as specified in the specifications, shown on the drawing.
a | Supply Air Diffusers (12" x 12") 16 qty (15 x 15 ) 100 qty | 172.16 | Sq. Ft | 3888 | 162 | 90 | 82.16 | 172.16 | 319438.08 | 0 | 171 | 171 | 27702 | 347140.08 | 1.269 | 5910.1655 | 945.6265
b | Return Air Diffusers (12" x 12") 16 qty (15" x 15") 85 qty | 150.64 | Sq. Ft | 3888 | 162 | 90 | 60.64 | 150.64 | 235768.32 | 0 | 147.12 | 147.12 | 23833.44 | 259601.76 | 1.269 | 6698.1875 | 945.6265
4.2 | Return Air Grill 9" x 9" 11 qty | 5.7 | Sq. Ft | 3888 | 162 | 6 |  | 6 | 0 | 0 | 6 | 6 | 972 | 972 | 1.269 | 5910.1655 | 945.6265
a | [8 empty] | 0
9 | Testing and Balancing
| Testing of Ducts. | 1 | Job |  | 40000 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 40000 | 40000 | 1.269 | 0 | 51221.4342
Total Amout Rs | [8 empty] | 814106.4 |  |  |  | 106657.44 | 920763.84 | 10.152 | 26028.3688 | 55897.5571 | 0 | 0
Note: 1. If required additional work or material except above then it will be charge additionally. 2. Electrical Wiring/DB/MCC is not included in the scope of wrok 3. BMS connectivity and cabling is not included in the scope work 4. Any other item didn't mentioned above will be cahgred additionally 5. Above mentioned quantities may vary as per the approved design of consultant
0.0047191
[5 empty] | 22601000 | [7 empty] | #REF!
0