## Sheet1
[7 empty] | Date | 18 April 2023
[7 empty] | Invoice # | 071
[7 empty] | NTN # | 4312149-7
M/S DWP Technologies PVT Ltd
Suit No. 102, First Floor, Fortune Center,
Shahrah-e-Faisal, Karachi.
NTN # 1547417-8
Mr. M. Ali Siddiqui
Attn: Mr. Farooq Tarmezi.
INVOICE
Supply and Installation of G.I Shet Metal duct & insulation - Air War College.
S. # | Particulars | Unit | Approx Qty | Material rate | Labour rate | Work Completed | Mateial Amount | Labour Amount
1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | Sqft | 13000 | 325 | 80 | 53% | 2239250 | 551200 | 70
2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | Sqft | 13000 | 185 | 70 | 53% | 1274650 | 482300 | 70
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 350 | 100 | 20% | 21000 | 6000 | 20
4 | Providing and installation Jubilee clamp 10" for flexible duct. | Nos | 120 | 300 | 25 | 20% | 7200 | 600 | 20
5 | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | Nos | 120 | 400 | 100 | 20% | 9600 | 2400 | 20
6 | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | Nos | 60 | 1600 | 300 | 20% | 19200 | 3600 | 20
7 | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | Nos | 60 | 1400 | 200 | 20% | 16800 | 2400 | 20
Sub Total Amount | [6 empty] | 3587700 | 1048500
Total Amount | [6 empty] | 4636200 |  |  | 6999000 | 2025000
SST 13% | [6 empty] | 602706
Grand Total Amount | [6 empty] | 5238906 |  |  |  | 9024000
Best Regards, | [10 empty] | 1173120
For Pioneer Services | [10 empty] | 10197120
5098560
5302502.4
PIONEER SERVICES

## Sheet2
Attn: Mr. Farooq Tarmezi.
Comparison
|  |  |  | NASTP |  |  |  |  | Pioneer
S. # | Particulars | Unit | Approx Qty | Material rate | Labour rate | Mateial Amount | Labour Amount | Total Amount | Material rate | Labour rate | Mateial Amount | Labour Amount | Labour Amount
1 | G.I Duct | Sqft | 13000 | 310 | 80 | 4030000 | 1040000 | 5070000 | 350 | 80 | 4550000 | 1040000 | 5590000
2 | Insulation | Sqft | 13000 | 165 | 55 | 2145000 | 715000 | 2860000 | 210 | 70 | 2730000 | 910000 | 3640000
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 650 | 220 | 195000 | 66000 | 261000 | 350 | 100 | 105000 | 30000 | 135000
4 | Jubilee clamp | Nos | 120 | 850 | 100 | 102000 | 12000 | 114000 | 300 | 25 | 36000 | 3000 | 39000
5 | Round Neck | Nos | 120 | 1200 | 250 | 144000 | 30000 | 174000 | 400 | 100 | 48000 | 12000 | 60000
6 | Plenum | Nos | 60 | 3300 | 600 | 198000 | 36000 | 234000 | 1600 | 300 | 96000 | 18000 | 114000
7 | Plenum insulation | Nos | 60 | 650 | 250 | 39000 | 15000 | 54000 | 1400 | 200 | 84000 | 12000 | 96000
[8 empty] | 8767000 |  |  |  |  | 9674000