## Sheet1
S. No | Description | Unit | Qty | BOQ Rate |  | Running Bill
|  |  |  | Material | Labour | Billed Qty | Material amount | Labour amount | Total Amount
PART-A FIRE FIGHTING SYSTEM
1 | Supply, installation, testing & commissioning of Fire Pump Skid Mounted Package set complete with Diesel & Jockey pump including Bacnet Control pane!, fuel tank all special fitting. Painting and hangers complete in all respects as per drawing (500GPM & 10BAR) | Set | 1 | 8408750 | 271250 | 0 | 0 | 0 | 0
2 | Supply & Installation of of Fire Hose Cabinets including automatic 25mm diameter Hose Reel, Nozzel 25mm lock shield valve, 25mm pressure reducing valve Complete in all respects as shown on drawings & specification. | Nos | 6 | 208863 | 10742 | 6 | 1253178 | 64452 | 1317630
3 | Supply, installation, testing & conunissioning of 4-way Fire Department Connection Including all accessories complete in all respects as shown on Drawings / Specifications | Nos | 1 | 113383 | 17903 | 1 | 113383 | 17903 | 131286
4 | Supply, installation, of OS & Y Gate valve Including all accessories complete in all respects as shown on Drawings / Specifications.
| Dia 2-1/2" | Nos | 6 | 89513 | 5968 | 2 | 179026 | 11936 | 190962
| Check Valve Dia 6" | Nos | 1 | 65643 | 5968 | 1 | 65643 | 5968 | 71611
5 | Supply, installation and commission of seamless M.S. ASTM grade B, schedule 40 Fire piping including all special fitting, Painting and hangers complete in all respects shown on Drawings / Specifications.
i) | Dia 6" | Rft | 20 | 2327 | 310 | 30 | 69810 | 9300 | 79110
ii) | Dia 4" | Rft | 450 | 1778 | 286 | 106 | 188468 | 30316 | 218784
iii) | Dia 2-1/2" | Rft | 150 | 1540 | 263 | 0 | 0 | 0 | 0
6 | Motor Coritrol Center-1 (M.C.C. 20 KW, 40 AMP TPN with 2 earthing points) for Fire Pump. | Nos | 1 | 813750 | 70525 | 0 | 0 | 0 | 0
7 | Supply & Installation of Wall Mounted Fire Extinguisher with hangers as per drawing and specification.
i) | 6 Kg Dry Powder Extinguishe | Nos | 14 | 16709 | 3581 | 0 | 0 | 0 | 0
ii) | 6 Kg CO2 Fire Extinguishe | Nos | 14 | 16112 | 3581 | 0 | 0 | 0 | 0
PART-B PLUMBING SYSTEM
1 | Supply and installation of O.H.Transfer pumps complete with accessories as per drawings and specifications. (50gpm, 70ft Head) | Nos | 2 | 340148 | 5968 | 2 | 680296 | 11936 | 692232
2 | Supply and inst:iliation of Submersible pumps complet with accessories as per drawings and specifications. (5gpm, 20ft Head) | Nos | 2 | 173058 | 5968 | 2 | 346116 | 11936 | 358052
3 | Supply and installation of Water closets European style with close coupled cistern, cistern fittings acrylic seat cover complete with all respect. | Nos | 20 | 33418 | 3581 |  | 0 | 0 | 0
4 | Supply & lnstallation of counter top Wash Basin with Waste, Bottle Trap & Tee Stop- cocks complete with all respect. | Nos | 15 | 23273 | 3581 | 3 | 69819 | 10743 | 80562
5 | Supply & Installation of Wash Basin Single Lever mixer complete in all respect. | Nos | 15 | 14919 | 3581 | 3 | 44757 | 10743 | 55500
6 | Supply & Installation of S.S Sink Single Lever Mixer complete with all respect | Nos | 5 | 38192 | 2387 | 1 | 38192 | 2387 | 40579
7 | Supply & Installatio of Towel Dispenser (SS body) complete with all respect | Nos | 15 | 7758 | 1194 | 0 | 0 | 0 | 0
8 | Supply & Installation of WC Hand Operated Shower With Angle Valve complete with all respect. | Nos | 20 | 5848 | 1432 | 3 | 17544 | 4296 | 21840
9 | Supply & Installation of Sanitizer -Automatic. | Nos | 15 | 10145 | 2029 | 0 | 0 | 0 | 0
10 | Supply & Installation of SS Sink, Waste, Bottle Trap and Tee-Stop Cocks complete with all respect | Nos | 5 | 7161 | 1432 | 1 | 7161 | 1432 | 8593
11 | Supply & Installation of Toilet Roll Holder. | Nos | 20 | 2268 | 835 | 0 | 0 | 0 | 0
12 | Supply & Installation of soap dispenser | Nos | 20 | 2268 | 1074 | 0 | 0 | 0 | 0
13 | Supply & Installation of hand dryer | Nos | 10 | 14919 | 3581 | 0 | 0 | 0 | 0
14 | Supply & Installation of S.Steel Robe hooks. | Nos | 20 | 1671 | 716 | 0 | 0 | 0 | 0
15 | Supply and inscallatiqn of C.P Tee valves, for cistern water inlet CP connectors with nuts and fittings. | Nos | 55 | 1731 | 239 | 10 | 17310 | 2390 | 19700
16 | WATER DISTRIBUTION SYSTEM
a | Supply and installation of PPR PN 20 piping for cold & Hot water system with fittings. specialties, including all cutting, fitting, fixing and cleaning, wall and slab sleeves/Core Cutting, CP clamps. hangers and supports, making connection with fixtures, valves with specialties, chiseling, making wall an floor openings and making good pressure testing at a pressure of 250 psig, painting of exposed piping in occupied areas with primer and coats of approved painting approved color complete in all respect.
i) | Dia 3" | Rft | 80 | 406 | 107 | 75 | 30450 | 8025 | 38475
ii) | Dia 2" | Rft | 80 | 334 | 107 | 96 | 32064 | 10272 | 42336
iii) | Dia 1-1/2" | Rft | 20 | 310 | 107 | 247 | 76570 | 26429 | 102999
iv) | Dia 1-1/4" | Rft | 40 | 286 | 107 | 56 | 16016 | 5992 | 22008
v) | Dia 1" | Rft | 40 | 251 | 107 | 100 | 25100 | 10700 | 35800
vi) | Dia 3/4" | Rft | 375 | 203 | 107 | 509 | 103327 | 54463 | 157790
Gate Valve
i) | Dia 3" | Nos | 3 | 20290 | 1790 | 1 | 20290 | 1790 | 22080
ii) | Dia 2" | Nos | 4 | 15516 | 1790 | 5 | 77580 | 8950 | 86530
iii) | Dia 1-1/2" | Nos | 5 | 8951 | 2387 | 5 | 44755 | 11935 | 56690
Y- Strainer
i) | Dia 2" | Nos | 2 | 12478 | 2170 | 2 | 24956 | 4340 | 29296
Float Valve
i) | Dia 2" | Nos | 1 | 18445 | 2170 | 0 | 0 | 0 | 0
Foot Valve
i) | Dia 2" | Nos | 1 | 9765 | 2170 | 4 | 39060 | 8680 | 47740
17 | SOIL, WASTE AND VENT SYSTEM
Supply and installation of UPVC Class D piping including all fittings, sockets, hangers and specials for soil. waste & vent stacks and horizontal runs buried in ground or above false ceiling. in shafts exposed or concealed in floors and walls and connecting to manholes, Including cutting. fitting. chiseling, wall and slab sleeves / Core Cutting, making good. fixing and cleaning. wall and slab openings complete in all respect.
i) | Dia 6" | Rft | 20 | 1085 | 217 | 41 | 44485 | 8897 | 53382
ii) | Dia 4" | Rft | 170 | 857 | 109 | 211 | 180827 | 22999 | 203826
iii) | Dia 3" | Rft | 160 | 749 | 109 | 443 | 331807 | 48287 | 380094
iv) | Dia 2" | Rft | 215 | 369 | 109 | 389 | 143541 | 42401 | 185942
v) | Dia 1-1/2" | Rft | 135 | 326 | 109 | 0 | 0 | 0 | 0
18 | Supply & installation of Vent cowl complete with all respect as per drawing & specification | Nos | 3 | 2713 | 543 | 4 | 10852 | 2172 | 13024
19 | Supply & installation of Floor Drain with Trap complete in all respect.
i) | 2" dia (Balcony Drain) | Nos | 8 | 3255 | 1085 | 0 | 0 | 0 | 0
ii) | Dia 3" | Nos | 35 | 3798 | 1085 | 30 | 113940 | 32550 | 146490
iii) | 4" dia (ROOF DRA!N) | Nos | 2 | 4340 | 1085 | 0 | 0 | 0 | 0
20 | Supply & installation of Clean Out complete in all respect
i) | Dia 3" | Nos | 6 | 3255 | 543 | 21 | 68355 | 11403 | 79758
ii) | Dia 4" | Nos | 6 | 3798 | 760 | 5 | 18990 | 3800 | 22790
21 | Supply & installation of M.H. complete with all respect as per drawing & specificaiton. | Nos | 2 | 29295 | 7595 | 2 | 58590 | 15190 | 73780
22 | Supply & installation of Floor Gully with Trap complete with all respect as per drawmg | Nos | 2 | 13020 | 5425 | 2 | 26040 | 10850 | 36890
23 | Stainless steel grease trap for kitchen below on Floor (Size 12" L x 18" W x 18"H) | Nos | 5 | 81375 | 5425 | 0 | 0 | 0 | 0
24 | Excavation and back filling for the sewerage and plumbing pipes as per drawings and specification | Lot | 1 | 135625 | 27125 | 1 | 135625 | 27125 | 162750
PART-C NATURAL GAS SUPPLY SYSTEM
1 | Supply & Installation of M.S Piping Schedule- 40 for Natural Gas System complete with Specialties, wall and slab sleeves/Core Cutting, fitting & hanger supports etc. as per drawings. | Rft | 70 | 2387 | 543 |  | 0 | 0 | 0
| Dia 3/4" | Rft | 65 | 217 | 152 | 0 | 0 | 0 | 0
2 | Gas Cock/Plug Valves
| Dia 3/4" | Nos | 5 | 1628 | 543 | 0 | 0 | 0 | 0
PART-D GENERAL ITEMS
1 | Equipment foundation, lifting & shifting charges from Ground floor to foundation pads as per specification and drawings. | Job | 1 | 81375 | 5425 | 1 | 81375 | 5425 | 86800
2 | Stencilling. Painting & Finishing as per specification. | Job | 1 | 48825 | 7595 | 1 | 48825 | 7595 | 56420
3 | M&P Services Shop drawings & As Built Drawings Color Copies. (Minimum scale 1-1/8") Hard Copy and Soft Copy in Autocad format in CD. | Set | 4 | 10850 | 3255 | 4 | 43400 | 13020 | 56420
4 | Fire Stoping of Walls & Structure Openings (For Small Openings - Hilti FS-ONE or (Approved Equivalent) | Job | 1 | 59675 | 5425 | 0 | 0 | 0 | 0
5 | Cost of testing, starting up, commissioning. balancing. adjusting and handling over of the complete plant. | Job | 1 | 83545 | 7595 | 1 | 83545 | 7595 | 91140
Total Amount Rs | [8 empty] | 5577691
Less Rebate 6% | [8 empty] | 334661.46
Net Total Amount Rs | [8 empty] | 5243029.54

## VO
PES/AH/003/08/21 | [8 empty] | 2021-08-23
Attn: Mr. Amin Ashraf
Variation Order for Wall Hung Comode & Flush Tank for Al-Hamd International.
S. # | Description | Material Rate | Installation rate | Intallation rate | Over head Profit 25% | Unit | Qty | Material Amount | Installation amount | Total amount
1 | Suppply and installation of wall hung Comode - PORTA (HD427WH) | 15400 | 0 | 4000 | 4850 | No | 1 | #REF! |  | 24250
2 | Suppply and installation of wall hung Comode) - PORTA (HD350WH) | 10750 | 0 | 4000 | 3687.5 | Nos | 2 | #REF! |  | 36875
3 | Suppply and installation of Concealed Flush tank PORTA (G3004A) | 27000 | 0 | 4000 | 7750 | Nos | 3 | #REF! |  | 116250
Sub Total Amount Rs: | [9 empty] | 177375
Thanking You,
Sincerely yours,
For PIONEER ENGINEERING SERVICES.
M. Bilal Habib

## summary
Summary of Bill
Fire Fighting & Plumbing Works at Al-Hamd International Karachi.
Sr # | DESCRIPTION | AMOUNT (PKR)
1 | Running Bill | 5243029.54
2 | Variation Order for Wall Hung Comode & Flush Tank | 177375
Total Cost of Bill |  | 5420404.54
Rupees in Words: Five million Four hundred twenty thousand, four Hundred Five Only