## orignal
Pioneer Engineering Services
Measurement Sheet For the bill.
BAI TUL SUKOON HOSPITAL KARACHI.
27-08-2021
BOQ ITEM | Grid | FLOOR HVAC PLAN (SUPPLY,RETURN & EXHAUST AIR DUCT ) DWG NO…..
|  | Description | Width inch | Height inch | Length ft | Area Sq.ft.
| AHU | Reducer | 22 | 10 | 1 | 7.5
| UG01 |  | 46 | 12 |  |  |  |  | gr | 587 | 3rd | 620 | 2nd | 540 | 1st | 401
|  | Supply Air Duct | 46 | 12 | 7 | 67.6667 |  |  |  | 23 |  | 446 |  | 436 |  | 369
|  | Reducer | 46 | 12 | 1 | 8.8333 |  |  |  | 74 |  | 11 |  | 207 |  | 183
|  |  | 36 | 12 | [7 empty] | 334 |  | 164 |  | 166
|  | Supply Air Duct | 36 | 12 | 8 | 64 | [5 empty] | 295 |  | 503 |  | 67
|  | Reducer | 36 | 12 | 1 | 7.5 | [5 empty] | 186 |  | 19 |  | 489
|  |  | 32 | 10 | [5 empty] | 684 |  | 1892 |  | 1869 |  | 1675 | 6120
|  | Supply Air Duct | 32 | 10 | 3.91 | 27.37
|  | Reducer | 32 | 10 | 1 | 5.8333
|  |  | 18 | 10
|  | Supply Air Duct | 18 | 10 | 21.66 | 101.08
|  | End Cap | 18 | 10 |  | 1.25
|  | Supply Air Duct | 16 | 12 | 9.75 | 45.5
|  | Reducer | 16 | 12 | 1 | 4.3333
|  |  | 16 | 8
|  | Supply Air Duct | 16 | 8 | 15.41 | 61.64
|  | End Cap | 16 | 8 |  | 0.88889
|  | Supply Air Duct | 16 | 8 | 7.91 | 31.64
|  | End Cap | 16 | 8 |  | 0.88889
|  | Supply Air Duct | 18 | 10 | 0 | 0 |  | sad | 12*12 | 2
|  | End Cap | 18 | 10 |  | 1.25 |  | sad | 15*15 | 3
|  | Supply Air Duct | 18 | 10 | 0 | 0 |  | rad | 9*9 | 2
|  | End Cap | 18 | 10 |  | 1.25 |  | rad | 18*18 | 2
|  | Supply Air Duct | 8 | 4 | 49.33 | 98.66 |  | sad | 6*6 | 1
|  | End Cap | 8 | 4 |  | 0.22222 |  | rad | 6*6 | 1
| 2NOS | Drop Neck | 6 | 6 | 4.16 | 8.32 |  | fail | 12*12 | 1
| 2NOS | Drop Neck | 12 | 12 | 1.25 | 10 |  | vcd | 18*10 | 3
| 3NOS | Drop Neck | 15 | 15 | 2.5 |  |  | vcd | 16*12 | 1
|  | Plenum Box | 41 | 15 | 5.16 | 48.16 |  | vcd | 16*8 | 2
|  | End Cap | 41 | 15 |  | 4.2708 |  | vcd | 12*8 | 1
|  | Return Air Duct | 30 | 10 | 4.16
|  | Return Air Duct | 8 | 4 | 8.5 | 17
|  | End Cap | 8 | 4 |  | 0.22222
|  | Fresh Air Duct | 12 | 8 | 16.33 | 54.4333
|  | Plenum Box | 12 | 12 | 1.08 | 4.32
TOTAL | [5 empty] | 684.0331
| AHU | Reducer | 22 | 10 | 1 | 5.8333
| FF01 |  | 26 | 12
|  | Supply Air Duct | 26 | 12 | 23.41 | 148.2633
|  | Reducer | 26 | 12 | 1.5 | 9
|  |  | 24 | 10
|  | Supply Air Duct | 24 | 10 | 9.08 | 51.4533
|  | Reducer | 24 | 10 | 1.5 | 7.5 |  | sad | 15*15 | 3
|  |  | 18 | 8 |  |  |  | rad | 15*15 | 3
|  | Supply Air Duct | 18 | 8 | 5.91 | 25.61 |  | fail | 12*12 | 1
|  | End Cap | 18 | 8 |  | 1 |  | vcd | 18*8 | 3
|  | Supply Air Duct | 18 | 8 | 3.75 | 16.25 |  | vcd | 12*8 | 1
|  | End Cap | 18 | 8 |  | 1 |  | vcd | 24*10 | 1
|  | Supply Air Duct | 18 | 8 | 3.5 | 15.1667
|  | End Cap | 18 | 8 |  | 1
| 3NOS | Drop Neck | 15 | 15 | 0.66 | 9.9
|  | Plenum Box | 40 | 15 | 2.5 | 22.9167
|  | End Cap | 40 | 15 |  | 4.1667
|  | Return Air Duct | 30 | 14 | 1 | 7.3333
|  | Return Air Duct | 24 | 10 | 13.75 | 77.9167
TOTAL | [5 empty] | 404.31
| AHU | Reducer | 22 | 10 | 1.5 | 7.75
| FF02 |  | 20 | 10
|  | Supply Air Duct | 20 | 10 | 31.25 | 156.25
|  | Reducer | 20 | 10 | 1.5 | 7 |  | sad | 12*12 | 2
|  |  | 16 | 10 |  |  |  | rad | 9*9 | 2
|  | Supply Air Duct | 16 | 10 | 7 | 30.3333 |  | vcd | 16*10 | 2
|  | End Cap | 16 | 10 |  | 1.1111
|  | Supply Air Duct | 16 | 10 | 5 | 21.6667
|  | End Cap | 16 | 10 |  | 1.1111
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4
|  | Plenum Box | 25 | 13 | 1.5 | 9.5
|  | End Cap | 25 | 13 |  | 2.2569
|  | Return Air Duct | 20 | 10 | 2.5 | 12.5
|  | Return Air Duct | 18 | 6 | 33.66 | 134.64
TOTAL | [5 empty] | 388.1192
| AHU | Supply Air Duct | 25 | 16 | 1.66 | 11.3433
| FF03 | Supply Air Duct | 20 | 10 | 9 | 45 |  | sad | 12*12 | 2
|  | Reducer | 20 | 10 | 1.5 | 7 |  | rad | 9*9 | 2
|  |  | 16 | 10 |  |  |  | vcd | 16*10 | 1
|  | Supply Air Duct | 16 | 10 | 12.16 | 52.6933
|  | End Cap | 16 | 10 |  | 1.1111
| 2NOS | Drop Neck | 12 | 12 | 1 | 8
|  | Plenum Box | 32 | 14 | 1.83 | 14.03
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 16 | 10 | 11.5 | 49.8333
TOTAL | [5 empty] | 192.1222
| AHU | Reducer | 22 | 10 | 1.5 | 6.75
| FF04 |  | 14 | 8
|  | Supply Air Duct | 14 | 8 | 7.16 | 26.2533
|  | Reducer | 14 | 8 | 1 | 3.3333 |  | sad | 6*6 | 1
|  |  | 12 | 6 |  |  |  | sad | 9*9 | 2
|  | Supply Air Duct | 12 | 6 | 12 | 36 |  | rad | 9*9 | 2
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd | 12*6 | 2
|  | Supply Air Duct | 12 | 6 | 4.83 | 14.49
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd failover | 20*10 | 1
|  | Supply Air Duct | 8 | 4 | 17 | 34 |  | vcd failover | 8*6 | 1
|  | End Cap | 8 | 4 |  | 0.22222 |  | vcd failover | 12*6 | 1
| 2NOS | Drop Neck | 9 | 9 | 1 | 6 |  | vcd failover | 12*8 | 1
| 1NOS | Drop Neck | 6 | 6 | 1 | 2 |  | vcd failover | 16*8 | 1
|  | Plenum Box | 32 | 14 | 1.66 | 12.7267
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 25 | 16 | 3.75 | 25.625
|  | Return Air Duct | 12 | 8 | 1 | 3.3333
|  | Fresh Air Duct | 20 | 10 | 83.75 | 418.75
|  | Fresh Air Duct | 16 | 8 | 6.91 | 27.64 | [7 empty] | 404.31
|  | Fresh Air Duct | 12 | 8 | 16.66 | 55.5333 | [7 empty] | 388.12
|  | Fresh Air Duct | 12 | 8 | 48.5 | 161.6667 | [7 empty] | 192.12
|  | Fresh Air Duct | 8 | 6 | 7 | 16.3333 | [7 empty] | 859.77
|  | Plenum Box | 20 | 10 | 1 | 5 | [7 empty] | 1844.32
TOTAL | [5 empty] | 859.7683 | 1844.3197
| AHU | Reducer | 22 | 10 | 1.5 | 10
| SF01 |  | 36 | 12
|  | Supply Air Duct | 36 | 12 | 29.16 | 233.28
|  | Reducer | 36 | 12 | 1.5 | 10.75
|  |  | 26 | 12
|  | Supply Air Duct | 26 | 12 | 7.91 | 50.0967
|  | Reducer | 26 | 12 | 1.5 | 8.5
|  |  | 22 | 8 |  |  |  | sad | 18*18 | 3
|  | Supply Air Duct | 22 | 8 | 18.83 | 94.15 |  | rad | 12*12 | 3
| 3NOS | End Cap | 22 | 8 |  | 3.6667 |  | vcd | 22*8 | 3
|  | Supply Air Duct | 22 | 8 | 10.16 | 50.8 |  | vcd | 30*12 | 1
|  | End Cap | 22 | 8 |  | 1.2222
|  | Supply Air Duct | 22 | 8 | 9 | 45
|  | End Cap | 22 | 8 |  | 1.2222
| 3NOS | Drop Neck | 18 | 18 | 0.83 | 14.94
|  | Plenum Box | 40 | 15 | 3.16 | 28.9667
|  | End Cap | 40 | 15 |  | 4.1667
|  | Return Air Duct | 30 | 12 | 15.25 | 106.75
TOTAL | [5 empty] | 663.5111
| AHU | Reducer | 22 | 10 | 1.5 | 8.25
| SF02 |  | 24 | 10
|  | Supply Air Duct | 24 | 10 | 32.5 | 184.1667
|  | Reducer | 24 | 10 | 1.5 | 7.5 |  | sad | 15*15 | 2
|  |  | 16 | 10 |  |  |  | rad | 12*12 | 2
|  | Supply Air Duct | 16 | 10 | 12.5 | 54.1667 |  | vcd | 16*10 | 2
|  | End Cap | 16 | 10 |  | 1.1111
|  | Supply Air Duct | 16 | 10 | 4.5 | 19.5
|  | End Cap | 16 | 10 |  | 1.1111
| 2NOS | Drop Neck | 15 | 15 | 1.16 | 11.6
|  | Plenum Box | 25 | 12 | 2 | 12.3333
|  | End Cap | 25 | 12 |  | 2.0833
|  | Return Air Duct | 18 | 10 | 32.75 | 152.8333
TOTAL | [5 empty] | 454.6556
| AHU | Supply Air Duct | 25 | 15 | 3.5 | 23.3333
| SF03 | Supply Air Duct | 18 | 10 | 9 | 42 |  | sad | 12*12 | 2
|  | Reducer | 18 | 10 | 1 | 4.1667 |  | rad | 12*12 | 2
|  |  | 14 | 8 |  |  |  | vcd | 14*8 | 1
|  | Supply Air Duct | 14 | 8 | 10.66 | 39.0867
|  | End Cap | 14 | 8 |  | 0.77778
| 2NOS | Drop Neck | 12 | 12 | 0.66 | 5.28
|  | Plenum Box | 32 | 14 | 1.83 | 14.03
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 16 | 10 | 18.91 | 81.9433
|  | Return Air Duct | 25 | 15 | 3.33 | 22.2
TOTAL | [5 empty] | 235.9289
| AHU | Supply Air Duct | 25 | 16 | 3.5 | 23.9167
| SF04 | Supply Air Duct | 14 | 10 | 7.08 | 28.32
|  | Reducer | 14 | 10 | 1 | 3.5 |  | sad | 6*6 | 1
|  |  | 12 | 6 |  |  |  | sad | 12*12 | 2
|  | Supply Air Duct | 12 | 6 | 12 | 36 |  | rad | 9*9 | 2
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd | 12*6 | 2
|  | Supply Air Duct | 12 | 6 | 4.83 | 14.49
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd failover | 20*10 | 1
|  | Supply Air Duct | 8 | 4 | 15.41 | 30.82 |  | vcd failover | 8*6 | 1
|  | End Cap | 8 | 4 |  | 0.22222 |  | vcd failover | 12*6 | 1
| 2NOS | Drop Neck | 12 | 12 | 0.75 | 6 |  | vcd failover | 12*8 | 1
| 1NOS | Drop Neck | 6 | 6 | 1 | 2 |  | vcd failover | 16*8 | 1
|  | Plenum Box | 32 | 14 | 1.66 | 12.7267
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 12 | 8 | 8 | 26.6667
|  | Fresh Air Duct | 20 | 10 | 82.66 | 413.3
|  | Fresh Air Duct | 16 | 8 | 6.91 | 27.64
|  | Fresh Air Duct | 12 | 8 | 16.66 | 55.5333
|  | Fresh Air Duct | 12 | 8 | 48.5 | 161.6667
|  | Fresh Air Duct | 8 | 6 | 7 | 16.3333
|  | Plenum Box | 20 | 10 | 1 | 5 | [5 empty] | 663.51
TOTAL | [5 empty] | 868.2467 | 2222.3422 |  |  |  |  | 454.66
| AHU | Plenum Box | 21 | 14 | 1.5 | 8.75 | [5 empty] | 235.93
| TF01 | Supply Air Duct | 16 | 12 | 5.25 | 24.5 | [5 empty] | 868.25
|  | Reducer | 16 | 12 | 1 | 4.3333 | [5 empty] | 2222.35
|  |  | 14 | 10
|  | Supply Air Duct | 14 | 10 | 3.75 | 15
|  | End Cap | 14 | 10 |  | 0.97222
|  | Supply Air Duct | 14 | 6 | 20.75 | 69.1667 |  | sad | 12*12 | 1
|  | End Cap | 14 | 6 |  | 0.58333 |  | sad | 9*9 | 3
|  | Supply Air Duct | 14 | 6 | 16.41 | 54.7 |  | rad | 9*9 | 3
|  | End Cap | 14 | 6 |  | 0.58333 |  | vcd | 14*6 | 2
| 3NOS | Drop Neck | 9 | 9 | 0.5 | 4.5 |  | vcd | 14*10 | 1
| 1NOS | Drop Neck | 12 | 12 | 3.75 | 15
|  | Plenum Box | 25 | 13 | 1.66 | 10.5133
|  | End Cap | 25 | 13 |  | 2.2569
|  | Return Air Duct | 14 | 10 | 27.66 | 110.64
|  | Reducer | 14 | 10 | 1 | 3.3333
|  |  | 12 | 4
|  | Supply Air Duct | 12 | 4 | 13.75 | 36.6667
|  | End Cap | 12 | 4 |  | 0.33333
|  | Supply Air Duct | 12 | 4 | 3.75 | 10
|  | End Cap | 12 | 4 |  | 0.33333
|  | Supply Air Duct | 12 | 4 | 3.75 | 10
|  | End Cap | 12 | 4 |  | 0.33333
TOTAL | [5 empty] | 382.4992
| AHU | Plenum Box | 21 | 14 | 2 | 11.6667
| TF02 | Supply Air Duct | 14 | 8 | 26.5 | 97.1667
|  | End Cap | 14 | 8 |  | 0.77778
|  | Supply Air Duct | 12 | 6 | 7.75 | 23.25 |  | sad | 12*12 | 2
|  | End Cap | 12 | 6 |  | 0.5 |  | rad | 9*9 | 2
| 2NOS | Drop Neck | 12 | 12 | 0.66 | 5.28 |  | vcd | 14*8 | 1
| 2NOS | Drop Neck | 9 | 9 | 0.83 | 4.98
|  | Plenum Box | 25 | 13 | 1.66 | 10.5133
|  | End Cap | 25 | 13 |  | 2.2569
|  | Return Air Duct | 12 | 8 | 32.5 | 108.3333
|  | Reducer | 12 | 8 | 1 | 3
|  |  | 10 | 6
|  | Supply Air Duct | 10 | 6 | 5.41 | 14.4267
|  | End Cap | 10 | 6 |  | 0.41667
|  | Supply Air Duct | 10 | 6 | 5.91 | 15.76
|  | End Cap | 10 | 6 |  | 0.41667
TOTAL | [5 empty] | 298.7447
| AHU | Reducer | 20 | 12 | 1.5 | 8.75
| TF03 |  | 26 | 12
|  | Supply Air Duct | 26 | 12 | 36 | 228 |  | sad | 12*12 | 5
|  | Reducer | 26 | 12 | 1.5 | 8 |  | rad | 9*9 | 3
|  |  | 16 | 10 |  |  |  | vcd | 26*12 | 1
|  | Supply Air Duct | 16 | 10 | 12.75 | 55.25 |  | vcd | 16*10 | 1
|  | Reducer | 16 | 10 | 1 | 3.8333
|  |  | 12 | 8
|  | Supply Air Duct | 12 | 8 | 5.5 | 18.3333
|  | End Cap | 12 | 8 |  | 0.66667
|  | Supply Air Duct | 16 | 10 | 5 | 21.6667
|  | Reducer | 16 | 10 | 1 | 3.8333
|  |  | 12 | 8
|  | Supply Air Duct | 12 | 8 | 11 | 36.6667
|  | End Cap | 12 | 8 |  | 0.66667
| 5NOS | Drop Neck | 12 | 12 | 0.66 | 13.2
| 3NOS | Drop Neck | 9 | 9 | 0.5 | 4.5
|  | Plenum Box | 37 | 16 | 3 | 26.5
|  | End Cap | 37 | 16 |  | 4.1111
|  | Return Air Duct | 22 | 12 | 27.58 | 156.2867
|  | Reducer | 22 | 12 | 1 | 5
|  |  | 16 | 10
|  | Supply Air Duct | 16 | 10 | 15 | 65
|  | Reducer | 16 | 10 | 1 | 3.8333
|  |  | 12 | 8 | [5 empty] | 382.51
|  | Supply Air Duct | 12 | 8 | 5 | 16.6667 |  |  |  | 298.74
|  | End Cap | 12 | 8 |  | 0.66667 |  |  |  | 681.43
TOTAL | [5 empty] | 681.4311 |  |  |  | 1362.68
| EF | Exhaust Air Duct | 12 | 8 | 13 | 43.3333
| TF01 | Exhaust Air Duct | 14 | 11 | 1 | 4.1667 |  | ead | 12*12 | 1
| 1NOS | Drop Neck | 12 | 12 | 1 | 4 |  | exlover | 14*11 | 1
TOTAL | [5 empty] | 51.5
| VF | Reducer | 12 | 12 | 4.16 | 15.2533
| TF01 |  | 12 | 8
|  | Fresh Air Duct | 12 | 8 | 4 | 13.3333
|  | Reducer | 12 | 8 | 1 | 2.8333
|  |  | 8 | 6
|  | Fresh Air Duct | 8 | 6 | 7.5 | 17.5 |  | FAF lover | 12*12 | 1
|  | Fresh Air Duct | 8 | 6 | 19 | 44.3333
| 1NOS | Fresh Air Duct | 12 | 12 | 1 | 4
TOTAL | [5 empty] | 97.2533 | 1511.4283 |  |  | 6113.37
TOTAL DUCTS QUANTITIES SUMMARY (SQ.FT.) | [6 empty] | fad | 1571.9033
Duct Insulation |  |  |  | 6113.38
Upper Ground Floor Ducting |  |  |  |  | 684.03
First Floor Ducting |  |  |  |  | 1844.32
Second Floor Ducting |  |  |  |  | 2222.35
Third Floor Ducting |  |  |  |  | 1362.68
Exhaust Air Duct |  |  |  |  | 51.5
Fresh Air Duct |  |  |  |  | 97.25
GRAND TOTAL OF DUCT WORKS. |  |  |  |  | 6262.13
|  | Supply Air Duct | 26 | 16 | 2.5 | 17.5
|  | Supply Air Duct | 26 | 16 | 9.66 | 67.62
|  | Supply Air Duct | 26 | 16 | 5.5 | 38.5
|  | Supply Air Duct | 26 | 16 | 4.66 | 32.62
|  | Supply Air Duct | 26 | 16 | 0.25 | 1.75
157.99
|  | Reducer | 23 | 23 | 2.5 | 19.1667
|  |  | 30 | 16
|  | Supply Air Duct | 30 | 16 | 12 | 92
|  | Supply Air Duct | 26 | 16 | 7.16 | 50.12
|  | Supply Air Duct | 26 | 16 | 9.66 | 67.62
|  | Supply Air Duct | 26 | 16 | 2.83 | 19.81
248.7167

## GROUND
Pioneer Engineering Services
Measurement Sheet For Running Bill.
BAI TUL SUKOON HOSPITAL KARACHI.
15-07-2021
BOQ | Grid | FLOOR HVAC PLAN (SUPPLY,RETURN & EXHAUST AIR DUCT ) DWG NO…..
ITEM |  | Description | Width inch | Height inch | Length ft | Area Sq.ft. |  | copper pipe |  | rft | rft | rft | rft
| AHU | Reducer | 48.5 | 9.5 | 2 | 15.5 |  | upper gr | 1"-5-8 | 75
| UG01 |  | 25.5 | 9.5 |  |  |  | ff | 3-4"-1-2 | 1)82 | 2)34 | 3)34 | 4)41
|  | Supply Air Duct | 46 | 12 | 8.16 | 78.88 |  | sf | 3-4"-1-2 | 1)98 | 2)42 | 3)45 | 4)52
|  | Reducer | 46 | 12 | 2 | 17.6667 |  | third floor | 5-8"-3-8" | 25 | 25
|  |  | 36 | 12
|  | Supply Air Duct | 36 | 12 | 16.83 | 134.64
|  | Reducer | 36 | 12 | 1.5 | 11.25 |  | drain pipe |  | rft |  | rft
|  |  | 32 | 10 |  |  |  | upper gr | 3-4" | 36 | 1" | 15
|  | Supply Air Duct | 32 | 10 | 11.16 | 78.12 |  | ff | 1" | 1)9 | 2)30 | 3)43-3-4" | 4)60-3-4"
|  | Reducer | 32 | 10 | 1.5 | 8.75 |  | sf | 1" | 1)9 | 2)31 | 3)38-3-4" | 4)72-3-4"
|  |  | 18 | 10 |  |  |  | thrd | 1" | 1)10-1" | 2)38-1"
|  | Supply Air Duct | 18 | 10 | 32.66 | 152.4133 |  | roof | 3-4" | 26 | 1" | 14
|  | End Cap | 18 | 10 |  | 1.25
|  | Supply Air Duct | 16 | 12 | 16.25 | 75.8333
|  | Reducer | 16 | 12 | 1 | 4.3333
|  |  | 16 | 8
|  | Supply Air Duct | 16 | 8 | 12 | 48
|  | End Cap | 16 | 8 |  | 0.88889
|  | Supply Air Duct | 16 | 8 | 13.08 | 52.32
|  | End Cap | 16 | 8 |  | 0.88889
|  | Supply Air Duct | 18 | 10 | 5.16 | 24.08 |  | sad | 12*12 | 2
|  | End Cap | 18 | 10 |  | 1.25 |  | sad | 15*15 | 3
|  | Supply Air Duct | 18 | 10 | 13.75 | 64.1667 |  | rad | 9*9 | 2
|  | End Cap | 18 | 10 |  | 1.25 |  | rad | 18*18 | 2
|  | Supply Air Duct | 8 | 4 | 63 | 126 |  | sad | 6*6 | 1
|  | End Cap | 8 | 4 |  | 0.22222 |  | rad | 6*6 | 1
| 2NOS | Drop Neck | 6 | 6 | 0.5 | 2 |  | fail | 12*12 | 1
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4 |  | vcd | 18*10 | 3
| 3NOS | Drop Neck | 15 | 15 | 0.5 | 7.5 |  | vcd | 16*12 | 1
|  | Plenum Box | 41 | 15 | 5.16 | 48.16 |  | vcd | 16*8 | 2
|  | End Cap | 41 | 15 |  | 4.2708 |  | vcd | 12*8 | 1
|  | Return Air Duct | 30 | 10 | 5.66 | 37.7333
|  | Return Air Duct | 8 | 4 | 33 | 66
|  | End Cap | 8 | 4 |  | 0.22222
|  | Fresh Air Duct | 12 | 8 | 47 | 156.6667
|  | Plenum Box | 12 | 12 | 1 | 4
TOTAL | [5 empty] | 1228.2564
| AHU | Reducer | 20 | 12 | 1.5 | 8.75
| FF01 |  | 26 | 12
|  | Supply Air Duct | 26 | 12 | 43.58 | 276.0067
|  | Reducer | 26 | 12 | 1.5 | 9
|  |  | 24 | 10
|  | Supply Air Duct | 24 | 10 | 16.83 | 95.37
|  | Reducer | 24 | 10 | 1.5 | 7.5 |  | sad | 15*15 | 3
|  |  | 18 | 8 |  |  |  | rad | 15*15 | 3
|  | Supply Air Duct | 18 | 8 | 24.75 | 107.25 |  | fail | 12*12 | 1
|  | End Cap | 18 | 8 |  | 1 |  | vcd | 18*8 | 3
|  | Supply Air Duct | 18 | 8 | 10.16 | 44.0267 |  | vcd | 12*8 | 1
|  | End Cap | 18 | 8 |  | 1 |  | vcd | 24*10 | 1
|  | Supply Air Duct | 18 | 8 | 9 | 39
|  | End Cap | 18 | 8 |  | 1
| 3NOS | Drop Neck | 15 | 15 | 0.5 | 7.5
|  | Plenum Box | 40 | 15 | 3 | 27.5
|  | End Cap | 40 | 15 |  | 4.1667
|  | Return Air Duct | 24 | 12 | 19.25 | 115.5
TOTAL | [5 empty] | 744.57
| AHU | Reducer | 20 | 12 | 1.5 | 7.75
| FF02 |  | 20 | 10
|  | Supply Air Duct | 20 | 10 | 54.25 | 271.25
|  | Reducer | 20 | 10 | 1.5 | 7 |  | sad | 12*12 | 2
|  |  | 16 | 10 |  |  |  | rad | 9*9 | 2
|  | Supply Air Duct | 16 | 10 | 21.83 | 94.5967 |  | vcd | 16*10 | 2
|  | End Cap | 16 | 10 |  | 1.1111
|  | Supply Air Duct | 16 | 10 | 4.75 | 20.5833
|  | End Cap | 16 | 10 |  | 1.1111
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4
|  | Plenum Box | 32 | 14 | 1.66 | 12.7267
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 18 | 6 | 48 | 192
TOTAL | [5 empty] | 615.24
| AHU | Reducer | 20 | 12 | 1.5 | 7.75
| FF03 |  | 20 | 10
|  | Supply Air Duct | 20 | 10 | 14.5 | 72.5 |  | sad | 12*12 | 2
|  | Reducer | 20 | 10 | 1.5 | 7 |  | rad | 9*9 | 2
|  |  | 16 | 10 |  |  |  | vcd | 16*10 | 1
|  | Supply Air Duct | 16 | 10 | 20 | 86.6667
|  | End Cap | 16 | 10 |  | 1.1111
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4
|  | Plenum Box | 32 | 14 | 1.83 | 14.03
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 16 | 10 | 15.5 | 67.1667
TOTAL | [5 empty] | 263.3356
| AHU | Reducer | 20 | 12 | 1.5 | 6.75
| FF04 |  | 14 | 8
|  | Supply Air Duct | 14 | 8 | 9.5 | 34.8333
|  | Reducer | 14 | 8 | 1 | 3.3333 |  | sad | 6*6 | 1
|  |  | 12 | 6 |  |  |  | sad | 9*9 | 2
|  | Supply Air Duct | 12 | 6 | 9 | 27 |  | rad | 9*9 | 2
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd | 12*6 | 2
|  | Supply Air Duct | 12 | 6 | 21.16 | 63.48
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd failover | 20*10 | 1
|  | Supply Air Duct | 8 | 4 | 27 | 54 |  | vcd failover | 8*6 | 1
|  | End Cap | 8 | 4 |  | 0.22222 |  | vcd failover | 12*6 | 1
| 2NOS | Drop Neck | 9 | 9 | 0.5 | 3 |  | vcd failover | 12*8 | 1
| 1NOS | Drop Neck | 6 | 6 | 0.5 | 1 |  | vcd failover | 16*8 | 1
|  | Plenum Box | 37 | 16 | 3 | 26.5
|  | End Cap | 37 | 16 |  | 4.1111
|  | Return Air Duct | 12 | 8 | 14 | 46.6667
|  | Fresh Air Duct | 20 | 10 | 148.25 | 741.25
|  | Fresh Air Duct | 16 | 8 | 26.5 | 106
|  | Fresh Air Duct | 12 | 8 | 4 | 13.3333
|  | Fresh Air Duct | 12 | 8 | 48.5 | 161.6667
|  | Fresh Air Duct | 8 | 6 | 7 | 16.3333
|  | Plenum Box | 20 | 10 | 1 | 5
TOTAL | [5 empty] | 1315.48 | 2938.6256
| AHU | Reducer | 20 | 12 | 1.5 | 10
| SF01 |  | 36 | 12
|  | Supply Air Duct | 36 | 12 | 38.83 | 310.64
|  | Reducer | 36 | 12 | 1.5 | 10.75
|  |  | 26 | 12
|  | Supply Air Duct | 26 | 12 | 16.75 | 106.0833
|  | Reducer | 26 | 12 | 1.5 | 8.5
|  |  | 22 | 8 |  |  |  | sad | 18*18 | 3
|  | Supply Air Duct | 22 | 8 | 25.83 | 129.15 |  | rad | 12*12 | 3
|  | End Cap | 22 | 8 |  | 1.2222 |  | vcd | 22*8 | 3
|  | Supply Air Duct | 22 | 8 | 10.16 | 50.8 |  | vcd | 30*12 | 1
|  | End Cap | 22 | 8 |  | 1.2222
|  | Supply Air Duct | 22 | 8 | 9 | 45
|  | End Cap | 22 | 8 |  | 1.2222
| 3NOS | Drop Neck | 18 | 18 | 0.5 | 9
|  | Plenum Box | 40 | 15 | 3 | 27.5
|  | End Cap | 40 | 15 |  | 4.1667
|  | Return Air Duct | 30 | 12 | 19 | 133
TOTAL | [5 empty] | 848.2567
| AHU | Reducer | 20 | 12 | 1.5 | 8.25
| SF02 |  | 24 | 10
|  | Supply Air Duct | 24 | 10 | 52.33 | 296.5367
|  | Reducer | 24 | 10 | 1.5 | 7.5 |  | sad | 15*15 | 2
|  |  | 16 | 10 |  |  |  | rad | 12*12 | 2
|  | Supply Air Duct | 16 | 10 | 24 | 104 |  | vcd | 16*10 | 2
|  | End Cap | 16 | 10 |  | 1.1111
|  | Supply Air Duct | 16 | 10 | 4.83 | 20.93
|  | End Cap | 16 | 10 |  | 1.1111
| 2NOS | Drop Neck | 15 | 15 | 0.5 | 5
|  | Plenum Box | 32 | 14 | 1.66 | 12.7267
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 18 | 10 | 48.25 | 225.1667
TOTAL | [5 empty] | 685.4433
| AHU | Reducer | 20 | 12 | 1.5 | 7.5
| SF03 |  | 18 | 10
|  | Supply Air Duct | 18 | 10 | 14.25 | 66.5 |  | sad | 12*12 | 2
|  | Reducer | 18 | 10 | 1 | 4.1667 |  | rad | 12*12 | 2
|  |  | 14 | 8 |  |  |  | vcd | 14*8 | 1
|  | Supply Air Duct | 14 | 8 | 20.25 | 74.25
|  | End Cap | 14 | 8 |  | 0.77778
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4
|  | Plenum Box | 32 | 14 | 1.83 | 14.03
|  | End Cap | 32 | 14 |  | 3.1111
|  | Return Air Duct | 16 | 10 | 15 | 65
TOTAL | [5 empty] | 239.3356
| AHU | Reducer | 20 | 12 | 1.5 | 7
| SF04 |  | 14 | 10
|  | Supply Air Duct | 14 | 10 | 9.5 | 38
|  | Reducer | 14 | 10 | 1 | 3.5 |  | sad | 6*6 | 1
|  |  | 12 | 6 |  |  |  | sad | 12*12 | 2
|  | Supply Air Duct | 12 | 6 | 9.25 | 27.75 |  | rad | 9*9 | 2
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd | 12*6 | 2
|  | Supply Air Duct | 12 | 6 | 21.5 | 64.5
|  | End Cap | 12 | 6 |  | 0.5 |  | vcd failover | 20*10 | 1
|  | Supply Air Duct | 8 | 4 | 26.5 | 53 |  | vcd failover | 8*6 | 1
|  | End Cap | 8 | 4 |  | 0.22222 |  | vcd failover | 12*6 | 1
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4 |  | vcd failover | 12*8 | 1
| 1NOS | Drop Neck | 6 | 6 | 0.5 | 1 |  | vcd failover | 16*8 | 1
|  | Plenum Box | 37 | 16 | 3 | 26.5
|  | End Cap | 37 | 16 |  | 4.1111
|  | Return Air Duct | 12 | 8 | 14 | 46.6667
|  | Fresh Air Duct | 20 | 10 | 148.25 | 741.25
|  | Fresh Air Duct | 16 | 8 | 26.5 | 106
|  | Fresh Air Duct | 12 | 8 | 4 | 13.3333
|  | Fresh Air Duct | 12 | 8 | 48.5 | 161.6667
|  | Fresh Air Duct | 8 | 6 | 7 | 16.3333
|  | Plenum Box | 20 | 10 | 1 | 5
TOTAL | [5 empty] | 1320.8333 | 3093.8689
| AHU | Plenum Box | 21 | 14 | 2 | 11.6667
| TF01 | Supply Air Duct | 16 | 12 | 4.5 | 21
|  | Reducer | 16 | 12 | 1 | 4.3333
|  |  | 14 | 10
|  | Supply Air Duct | 14 | 10 | 7 | 28
|  | End Cap | 14 | 10 |  | 0.97222
|  | Supply Air Duct | 14 | 6 | 13 | 43.3333 |  | sad | 12*12 | 1
|  | End Cap | 14 | 6 |  | 0.58333 |  | sad | 9*9 | 3
|  | Supply Air Duct | 14 | 6 | 10 | 33.3333 |  | rad | 9*9 | 3
|  | End Cap | 14 | 6 |  | 0.58333 |  | vcd | 14*6 | 2
| 3NOS | Drop Neck | 9 | 9 | 0.5 | 4.5 |  | vcd | 14*10 | 1
| 3NOS | Drop Neck | 9 | 9 | 0.5 | 4.5
| 1NOS | Drop Neck | 12 | 12 | 1 | 4
|  | Plenum Box | 25 | 13 | 1.66 | 10.5133
|  | End Cap | 25 | 13 |  | 2.2569
|  | Return Air Duct | 14 | 10 | 24 | 96
|  | Reducer | 14 | 10 | 1 | 3.3333
|  |  | 12 | 4
|  | Supply Air Duct | 12 | 4 | 17 | 45.3333
|  | End Cap | 12 | 4 |  | 0.33333
|  | Supply Air Duct | 12 | 4 | 2.5 | 6.6667
|  | End Cap | 12 | 4 |  | 0.33333
|  | Supply Air Duct | 12 | 4 | 4.75 | 12.6667
|  | End Cap | 12 | 4 |  | 0.33333
TOTAL | [5 empty] | 334.5758
| AHU | Plenum Box | 21 | 14 | 1.5 | 8.75
| TF02 | Supply Air Duct | 14 | 8 | 31.58 | 115.7933
|  | End Cap | 14 | 8 |  | 0.77778
|  | Supply Air Duct | 12 | 6 | 6.75 | 20.25 |  | sad | 12*12 | 2
|  | End Cap | 12 | 6 |  | 0.5 |  | rad | 9*9 | 2
| 2NOS | Drop Neck | 12 | 12 | 0.5 | 4 |  | vcd | 14*8 | 1
| 2NOS | Drop Neck | 9 | 9 | 0.5 | 3
|  | Plenum Box | 25 | 13 | 1.66 | 10.5133
|  | End Cap | 25 | 13 |  | 2.2569
|  | Return Air Duct | 12 | 8 | 32.5 | 108.3333
|  | Reducer | 12 | 8 | 1 | 2.8333
|  |  | 8 | 6
|  | Supply Air Duct | 8 | 6 | 8 | 18.6667
|  | End Cap | 8 | 6 |  | 0.33333
|  | Supply Air Duct | 8 | 6 | 8.5 | 19.8333
|  | End Cap | 8 | 6 |  | 0.33333
TOTAL | [5 empty] | 316.1747
| AHU | Reducer | 20 | 12 | 1.5 | 8.75
| TF03 |  | 26 | 12
|  | Supply Air Duct | 26 | 12 | 39.33 | 249.09 |  | sad | 12*12 | 5
|  | Reducer | 26 | 12 | 1.5 | 8 |  | rad | 9*9 | 3
|  |  | 16 | 10 |  |  |  | vcd | 26*12 | 1
|  | Supply Air Duct | 16 | 10 | 6.5 | 28.1667 |  | vcd | 16*10 | 1
|  | Reducer | 16 | 10 | 1 | 3.8333
|  |  | 12 | 8
|  | Supply Air Duct | 12 | 8 | 6.5 | 21.6667
|  | End Cap | 12 | 8 |  | 0.66667
|  | Supply Air Duct | 16 | 10 | 21.5 | 93.1667
|  | Reducer | 16 | 10 | 1 | 3.8333
|  |  | 12 | 8
|  | Supply Air Duct | 12 | 8 | 6.75 | 22.5
|  | End Cap | 12 | 8 |  | 0.66667
| 5NOS | Drop Neck | 12 | 12 | 0.5 | 10
| 3NOS | Drop Neck | 9 | 9 | 0.5 | 4.5
|  | Plenum Box | 37 | 16 | 3 | 26.5
|  | End Cap | 37 | 16 |  | 4.1111
|  | Return Air Duct | 22 | 12 | 34.5 | 195.5
|  | Reducer | 22 | 12 | 1 | 5
|  |  | 16 | 10
|  | Supply Air Duct | 16 | 10 | 5.16 | 22.36
|  | Reducer | 16 | 10 | 1 | 3.8333
|  |  | 12 | 8
|  | Supply Air Duct | 12 | 8 | 7.75 | 25.8333
|  | End Cap | 12 | 8 |  | 0.66667
TOTAL | [5 empty] | 738.6444
| EF | Exhaust Air Duct | 12 | 8 | 13 | 43.3333
| TF01 | Exhaust Air Duct | 14 | 11 | 1 | 4.1667 |  | ead | 12*12 | 1
| 1NOS | Drop Neck | 12 | 12 | 1 | 4 |  | exlover | 14*11 | 1
TOTAL | [5 empty] | 51.5
| VF | Fresh Air Duct | 12 | 8 | 4 | 13.3333
| TF01 | Reducer | 12 | 8 | 1 | 2.8333
|  |  | 8 | 6
|  | Supply Air Duct | 8 | 6 | 7.5 | 17.5 |  | FAF lover | 12*12 | 1
|  | Supply Air Duct | 8 | 6 | 19 | 44.3333
| 1NOS | Fresh Air Duct | 12 | 12 | 1 | 4
TOTAL | [5 empty] | 82 | 1522.895
TOTAL DUCTS QUANTITIES SUMMARY (SQ.FT.) | [6 empty] | fad | 2381.3333
Duct Insulation |  |  |  | 6401
Upper Ground Floor Ducting |  |  |  |  | 1228.26
First Floor Ducting |  |  |  |  | 2938.63
Second Floor Ducting |  |  |  |  | 3093.87
Third Floor Ducting |  |  |  |  | 1522
GRAND TOTAL OF DUCT WORKS. |  |  |  | 6401 | 8782.76

## Sheet1
ground floor |  |  | first floor |  |  | second floor |  |  | third floor |  |  | diffuser
sad | 12*12 | 2 | sad | 15*15 | 3 | sad | 18*18 | 3 | sad | 12*12 | 1 | 12*12 | 25
sad | 15*15 | 3 | rad | 15*15 | 3 | rad | 12*12 | 3 | sad | 9*9 | 3 | 15*15 | 11
rad | 9*9 | 2 | fail | 20*10 | 1 | vcd | 22*8 | 3 | rad | 9*9 | 3 | 18*18 | 5
rad | 18*18 | 2 | vcd | 18*8 | 3 | vcd | 30*12 | 1 | vcd | 14*6 | 2 | 9*9 | 23
sad | 6*6 | 1 | vcd | 12*8 | 1 | fail | 20*10 | 1 | vcd | 14*10 | 1 | 6*6 | 4
rad | 6*6 | 1 | vcd | 24*10 | 1 | sad | 15*15 | 2
fail | 12*12 | 1 |  |  |  | rad | 12*12 | 2 | sad | 12*12 | 2 | failouver
vcd | 18*10 | 3 | sad | 12*12 | 2 | vcd | 16*10 | 2 | rad | 9*9 | 2 | 12*12 | 2
vcd | 16*12 | 1 | rad | 9*9 | 2 |  |  |  | vcd | 14*8 | 1 | 20*10 | 2
vcd | 16*8 | 2 | vcd | 16*10 | 2 | sad | 12*12 | 2 |  |  |  | exl14*11 | 1
vcd | 12*8 | 1 |  |  |  | rad | 12*12 | 2 | sad | 12*12 | 5 | 12*12 | 1
|  | 19 | sad | 12*12 | 2 | vcd | 14*8 | 1 | rad | 9*9 | 3 | vcd
|  |  | rad | 9*9 | 2 |  |  |  | vcd | 26*12 | 1 | 18*10 | 3
|  |  | vcd | 16*10 | 1 | sad | 6*6 | 1 | vcd | 16*10 | 1 | 16*12 | 1
[6 empty] | sad | 12*12 | 2 |  |  |  | 16*8 | 4
|  |  | sad | 6*6 | 1 | rad | 9*9 | 2 | ead | 12*12 | 1 | 12*8 | 4
|  |  | sad | 9*9 | 2 | vcd | 12*6 | 2 | exlover | 14*11 | 1 | 18*8 | 3
|  |  | rad | 9*9 | 2 |  |  |  | FAF lover | 12*12 | 1 | 24*10 | 1
|  |  | vcd | 12*6 | 2 | vcd failover | 20*10 | 1 |  |  | 28 | 16*10 | 6
[6 empty] | vcd failover | 8*6 | 1 |  |  |  | 12*6 | 6
|  |  | vcd failover | 20*10 | 1 | vcd failover | 12*6 | 1 |  |  |  | 20*10 | 2
|  |  | vcd failover | 8*6 | 1 | vcd failover | 12*8 | 1 |  |  |  | 8*6 | 2
|  |  | vcd failover | 12*6 | 1 | vcd failover | 16*8 | 1 |  |  |  | 14*6 | 2
|  |  | vcd failover | 12*8 | 1 |  |  | 34 |  |  |  | 14*10 | 1
|  |  | vcd failover | 16*8 | 1 | [6 empty] | 14*8 | 2
[5 empty] | 35 | [6 empty] | 26*12 | 1
[12 empty] | 22*8 | 3
[12 empty] | 30*12 | 1
[11 empty] | 116 |  | 116

## Sheet2
| Pioneer Engineering Services | [6 empty] | Pioneer Engineering Services
| Copper Pipe & Upvc Drain Pipe | [6 empty] | Copper Pipe & Upvc Drain Pipe
| Measurement Sheet For the bill. | [6 empty] | Measurement Sheet For Running Bill.
| BAI TUL SUKOON HOSPITAL KARACHI. | [6 empty] | BAI TUL SUKOON HOSPITAL KARACHI.
[7 empty] | 27-08-2021 | [5 empty] | 27-08-2021
DESCRIPTION |  | COPPER PIPE QTY |  |  |  | DRAIN PIPE QTY |  | DESCRIPTION |  | COPPER PIPE QTY |  | DRAIN PIPE QTY
S/NO | AHU LOCATION | 1" | 5/8" | 1/2" | 3/4" | 1" | 3/4" | S/NO | AHU LOCATION | 5/8" | 3/8" | 1" | 3/4"
1 | AHU-UG-01 | 75 RFT | 75 RFT |  |  | 15 RFT | 36 RFT | 1 | AHU-PCKG-01 |  |  | 14 RFT | 26 RFT
2 | AHU-FF-01 |  |  | 82 RFT | 82 RFT | 9 RFT |  | 2 | AHU-TF-01 | 25 RFT | 25 RFT | 10 RFT
3 | AHU-FF-02 |  |  | 34 RFT | 34 RFT | 30 RFT |  | 3 | AHU-TF-02 | 25 RFT | 25 RFT | 38 RFT
4 | AHU-FF-03 |  |  | 34 RFT | 34 RFT |  | 43 RFT | TOTAL |  | 50 RFT | 50 RFT | 62 RFT | 26 RFT
5 | AHU-FF-04 |  |  | 41 RFT | 41 RFT |  | 60 RFT
6 | AHU-SF-01 |  |  | 98 RFT | 98 RFT | 9 RFT
7 | AHU-SF-02 |  |  | 42 RFT | 42 RFT | 31 RFT
8 | AHU-SF-03 |  |  | 45 RFT | 45 RFT |  | 38 RFT
9 | AHU-SF-04 |  |  | 52 RFT | 52 RFT |  | 72 RFT
TOTAL |  | 75 RFT | 75 RFT | 428 RFT | 428 RFT | 94 RFT | 249 RFT