## Sheet1
HVAC & Fire Fighting Works (Construction Schedule)
Months | JUNE 2022 |  |  |  | July 2022
Weeks | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
HVAC
Site Visit and Marking
Prepairation of Shop Drawings
Submittal / samples approvals
Supply/ installation of Motorized Dampers
Supply of Air Devices
Installation of Air Devices
Testing & Commissioning
Fire Fighting
Site Visit and Marking
Prepairation Shop Drawings
Submittal / samples approvals
M.S Piping
Painting / stencling
Installation of NOVEC system with related accessories
Testing & Commissioning

## Sheet2
HVAC & Fire Fighting Works (Construction Schedule)
Months | JUNE 2022 |  |  |  | July 2022
Weeks | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
HVAC
Site Visit and Marking
Preparation of Shop Drawings
Submittal / samples approvals
Supply/ installation of Motorized Dampers
Supply of Air Devices
Installation of Air Devices
Testing & Commissioning
Fire Fighting
Site Visit and Marking
Preparation Shop Drawings
Submittal / samples approvals
M.S Piping
Painting / stencling
Installation of NOVEC system with related accessories
Testing & Commissioning