## Sheet1
Material required by Engr Imran at JPMC
Welding Rods 10 NO (zodian) | 1 Packet
Welding Rods 12 NO (zodian) | 8 Packet
Cutting Disc 12" (Rhodius) | 4
Cutting Disc 5" (Rhodius) | 12

## Sheet2
Status of Ethnic submittal |  |  |  | Deutsche Bank
Submittal | Comment | Brand | Status | Submittal | Comment | Status
Valves | Not Approved due to Approved list |  | What to do????? | FIREX Extinguishing System (FIREX) | Authorized Certificate required Resubmission required
Air Devices | Resubmission required | Uni-Air | What to do????? | Extinghuishers (NAFFCO)
Fittings |  |  | Received | M.S SCH 40 Seamless Pipes (PROTEK) | Origin required -- Approved
Supports and Anchor |  | WALVEREN | Talha will deliver hard copy tomorrow | Air Devices (Uni-Air) | Sample -- Approved
Drain Pipe |  | Hepworth | Received | Aerofoam Insulation (XLPE) | Approved
MCC |  | (Sunbeam) | Nadeem bahi talked to Majad Owner in this matter | Wiring (FP 200)
BMS |  | JES | Kashi told that he will provide soon | G.I duct
Fire Stoping |  | WALVEREN | Talha will deliver hard copy tomorrow | Shop Drawings
PICV |  | SCON | Received | any thing else