## Sheet1
HVAC & Fire Fighting Schedule
Description |  | Remarks | May 2023 | [20 empty] | April 2023 | [19 empty] | May 2023 | [19 empty] | June 2023
| Days |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
GROUND FLOOR
Submission of submittal | 05 Days
Shop Drawings | 05 Days
Procurement of material | 03 Days | After Approval
Installation of hangers & supports | 03 Days | After Approval
Fabrication / Duct installation | 09 Days | After Approval
Installation of MS Fire Pipe | 26 Days | After Demolishing CC floor of Ground Floor
MS Fire Pipe Hydro testing | 02 Days
Installation of ducting | 60 Days | After Approval of Submittal & shop drawings
Installation of copper pipe | 60 Days | After Approval of Submittal & shop drawings
Duct Leak Testing | 02 Days
Copper pipe pressure test | 02 Days
Copper pipe Insulation work | 08 Days
Duct Insulation work | 08 Days
Condensate Drain Piping with insulation | 45 Days
Installation of Diffusers | 04 Days | Subject to Approval
Painting / Identification | 50 Days
Fire Hose Cabinet & Fire Extinguishers | 08 Days
Testing & Commissioning | 08 Days
FIRST FLOOR
Installation of hangers & supports | 03 Days | After Approval of Submittal
Fabrication / Duct installation | 08 Days | After Approval of Submittal
Installation of MS Fire Pipe | 26 Days | After Demolishing CC floor of Ground Floor
MS Fire Pipe Hydro testing | 02 Days
Installation of ducting | 60 Days | After Approval of Submittal & shop drawings
Installation of copper pipe | 60 Days | After Approval of Submittal & shop drawings
Duct Leak Testing | 02 Days
Copper pipe pressure test | 02 Days
Copper pipe Insulation work | 08 Days
Duct Insulation work | 08 Days
Condensate Drain Piping with insulation | 45 Days
Installation of Diffusers | 04 Days | Subject to Approval
Dismantling Works | 10 Days | After Approval of dismantling
Installation of Unit & piping Layout | 08 Days
Installation of hangers & supports | 20 Days | After Approval of Submittal
Installation of MS Fire Pipe | 26 Days
MS Fire Pipe Hydro testing | 02 Days
Installation of ducting | 52 Days | After Approval of Submittal & shop drawings
Installation of copper pipe | 52 Days | After Approval of Submittal & shop drawings
Duct Leak Testing | 02 Days
Copper pipe pressure test | 02 Days
Copper pipe Insulation work | 08 Days
Duct Insulation work | 08 Days
Condensate Drain Piping with insulation | 45 Days
Installation of air devices | 50 Days
Painting / Identification | 50 Days
Fire Hose Cabinet & Fire Extinguishers | 08 Days
Testing & Commissioning | 08 Days
SECOND FLOOR
Installation of hangers & supports | 03 Days | After Approval of Submittal
Fabrication / Duct installation | 08 Days | After Approval of Submittal
Installation of MS Fire Pipe | 26 Days | After Demolishing CC floor of Ground Floor
MS Fire Pipe Hydro testing | 02 Days
Installation of ducting | 60 Days | After Approval of Submittal & shop drawings
Installation of copper pipe | 60 Days | After Approval of Submittal & shop drawings
Duct Leak Testing | 02 Days
Copper pipe pressure test | 02 Days
Copper pipe Insulation work | 08 Days
Duct Insulation work | 08 Days
Condensate Drain Piping with insulation | 45 Days
Installation of Diffusers | 04 Days | Subject to Approval
Installation of Unit & piping Layout | 08 Days
Installation of hangers & supports | 20 Days | After Approval of Submittal
Installation of MS Fire Pipe | 26 Days
MS Fire Pipe Hydro testing | 02 Days
Installation of ducting | 52 Days | After Approval of Submittal & shop drawings
Installation of copper pipe | 52 Days | After Approval of Submittal & shop drawings
Duct Leak Testing | 02 Days
Copper pipe pressure test | 02 Days
Copper pipe Insulation work | 08 Days
Duct Insulation work | 08 Days
Condensate Drain Piping with insulation | 45 Days
Installation of air devices | 50 Days
Painting / Identification | 50 Days
Fire Hose Cabinet & Fire Extinguishers | 08 Days
Testing & Commissioning | 08 Days