## Sheet1
HVAC & Fire Fighting Works (Construction Schedule)
Months | JUNE 2022 |  |  |  | JULY 2022 |  |  |  | August 2022
Days | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
HVAC
Site Visit and Marking
Shop Drawings
Submittal / samples approvals
G.I Ducting
Ducting insulation
CHW Piping
CHW Pipe insulation
Valves and Fittings
Drain Piping
Drain Insulation
Controls / Electrical works
Painting
Installation of Air Devices
Meters & Guages
Testing & Commissioning
Fire Fighting
Site Visit and Marking
Prepairation Shop Drawings
Submittal / samples approvals
M.S Piping
Flushing
Painting / stencling
Installation of Valves
Installation of sprinklers
Installation of Fire Hose Cabinet
Extinghuisers
Testing & Commissioning