## HVAC
PS/BD/317/08/23 | [6 empty] | 2023-10-30
Bill
HVAC work for Badri Office at 7th Floor Fakhri Trade Center Karachi.
S. # | Description | Unit | Billed Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
1 | Removal & dismantle of existing duct & air devices complete in all respect. | Job | 1 | 0 | 20000 | 0 | 20000
2 | Supply & Installation of G.I. sheet metal duct machine made with flange, nut bolts, gasket, duct sealent etc complete in all respect. | Sqft | 1318 | 350 | 60 | 461300 | 79080
3 | Supply & Installation of Glass wool insulation of 25mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 1840 | 180 | 40 | 331200 | 73600
4 | Removal / reinstallation of existing duct including repairing of insulation (approx) | Sqft | 780 | 40 | 80 | 31200 | 62400
5 | Supply & Installation of Linear Grill 2 Slot x 36" | Nos | 22 | 5000 | 700 | 110000 | 15400
6 | Removal & reinstallation of existing grills. | Nos | 24 | 1000 | 1000 | 24000 | 24000
7 | Supply and installation of volume control damper | Sqin | 0 | 26 | 60 | 0 | 0
8 | Supply and installation of hangers / supports for G.I sheet metal ducts. | Job | 1 | 40000 | 15000 | 40000 | 15000
9 | Supply of 2 Roll glass wool | Roll | 2 | 8000 | 0 | 16000 | 0
10 | Making of Shop drawings & As built. | Set | 1 | 5000 | 5000 | 5000 | 5000
11 | Painting & Identification. | Job | 1 | 5000 | 5000 | 5000 | 5000
12 | Testing & commissioning / air balancing | Job | 1 | 0 | 25000 | 0 | 25000
Sub - Total Amount Rs | [5 empty] | 1023700 | 324480
SST Tax 13% | [5 empty] | 0 | 42182.4
Total Amount Rs | [5 empty] | 1023700 | 366662.4
Grand Total Amount Rs | [6 empty] | 1348180
For PIONEER ENGINEERING SERVICES.
PIONEER SERVICES

## PES estimate
PS/BD/317/08/23 | [6 empty] | 2023-10-30
OUR estimate
HVAC work for Badri Office at 7th Floor Fakhri Trade Center Karachi.
S. # | Description | Unit | Billed Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
1 | Removal & dismantle of existing duct & air devices complete in all respect. | Job | 1 | 0 | 20000 | 0 | 20000
2 | Supply & Installation of G.I. sheet metal duct machine made with flange, nut bolts, gasket, duct sealent etc complete in all respect. | Sqft | 824 | 350 | 60 | 288400 | 49440
3 | Supply & Installation of Glass wool insulation of 25mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 924 | 180 | 40 | 166320 | 36960
4 | Removal / reinstallation of existing duct including repairing of insulation (approx) | Sqft | 706 | 40 | 80 | 28240 | 56480
5 | Supply & Installation of Linear Grill 2 Slot x 36" | Nos | 22 | 5000 | 700 | 110000 | 15400
6 | Removal & reinstallation of existing grills. | Nos | 24 | 1000 | 1000 | 24000 | 24000
7 | Supply and installation of volume control damper | Sqin | 0 | 26 | 60 | 0 | 0
8 | Supply and installation of hangers / supports for G.I sheet metal ducts. | Job | 1 | 40000 | 15000 | 40000 | 15000
9 | Making of Shop drawings & As built. | Set | 1 | 5000 | 5000 | 5000 | 5000
10 | Painting & Identification. | Job | 1 | 5000 | 5000 | 5000 | 5000
11 | Testing & commissioning / air balancing | Job | 1 | 0 | 25000 | 0 | 25000
Sub - Total Amount Rs | [5 empty] | 666960 | 252280
SST Tax 13% | [5 empty] | 0 | 32796.4
Total Amount Rs | [5 empty] | 666960 | 285076.4
Grand Total Amount Rs | [6 empty] | 919240
For PIONEER SERVICES.
PIONEER SERVICES