## HVAC
M/S Dawat-e-Hadiyah Burhani Mahal |  |  |  |  | Date |  | 2023-06-22
Mciver Road, Karachi |  |  |  |  | Invoice # |  | 319
[5 empty] | NTN # |  | 4312149-7
Invoice
HVAC work Food Court - The North Walk Shopping Mall
S. # | Description | Unit | Qty | Material Rate | Labor Rate | Material Amount | Labor Amount
1 | Regging, lifting & shifting of packaged unit at over head tank roof including installation of vibration isolator by rigger. | Nos | 2 |  | 25000 | 0 | 50000
2 | Supply & Installation of G.I. sheet metal duct machine made (22 / 24 SWG) with flange, nut bolts, gasket, duct sealant etc. complete in all respect. | Sqft | 4560 | 325 | 60 | 1482000 | 273600
3 | Supply & Installation of aluminum faced XLPE insulation 20mm thick for supply & return air ducts. (internal duct area) | Sqft | 1041 | 550 | 60 | 572550 | 62460
4 | Supply & Installation of Glass wool insulation of 25mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 262 | 130 | 30 | 34060 | 7860
5 | Supply & Installation of PU insulation 50mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 2880 | 645 | 75 | 1857600 | 216000
6 | Supply & Installation of G.I Cladding on exposed area duct (26 SWG) for protection of insulation. | Sqft | 3626 | 300 | 60 | 1087800 | 217560
7 | Providing and installation of folding for installation of ducts and cladding. (after completion of job remove the folding from Site) | Job | 1 | 0 | 150000 | 0 | 150000
8 | Supply and installation of double deflection return air grill including rectagular M.S pipe frame.
| i) 18 x 24 | Nos | 4 | 16500 | 2000 | 66000 | 8000
| ii) 10 x 30 | Nos | 5 | 11800 | 2000 | 59000 | 10000
8 | Installation of owner supplied 06" dia jet diffuser | Nos | 20 | 0 | 1000 | 0 | 20000
9 | Supply & Installation of fresh air in take louver 12 x 20 | Nos | 2 | 6700 | 1000 | 13400 | 2000
10 | Supply & Installation of aluminium filter 1" thick 12 x 20 | Nos | 2 | 3600 | 700 | 7200 | 1400
11 | Supply & installation of Flexible duct connector for return / supply air duct connection. | Rft | 36 | 650 | 100 | 23400 | 3600
12 | Supply and installation of volume control damper 12 x 20 | Nos | 2 | 6000 | 1000 | 12000 | 2000
13 | Supply and installation of volume control damper 32 x 20 | Nos | 2 | 17600 | 1500 | 35200 | 3000
14 | Supply & installation of Fire damper 32 x 20 | Nos | 2 | 17600 | 1500 | 35200 | 3000
15 | Supply and installation of hangers / supports for G.I sheet metal ducts. | Job | 1 | 120000 | 15000 | 120000 | 15000
16 | Making of Shop drawings & As built on Auto CAD 2018. | Set | 1 | 20000 | 10000 | 20000 | 10000
17 | Supply and installation of control wiring including installation of thermostat complete in all respect. | Job | 0 | 15000 | 5000 | 0 | 0
18 | Painting & Identification. | Job | 1 | 30000 | 20000 | 30000 | 20000
19 | Testing & commissioning cordination with supplier | Job | 2 | 0 | 5000 | 0 | 10000
Sub- Total Amount Rs | [5 empty] | 5455410 | 1085480
SST Tax 13% | [5 empty] | 0 | 141112.4
Total Amount Rs | [5 empty] | 5455410 | 1226592.4
Grand Total Amount Rs | [5 empty] | 6682192.4
For PIONEER SERVICES.
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
PIONEER SERVICES

## working
|  |  | Discount | 4.811%
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
Discount | 88065.0403 | 18198.9538
Sub Total Amount | 1742534.9597 | 360101.0462
SRB 13% on Labour | 0 | 46813.136
Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
SRB 13% on Labour | 0 | 49179
Total Amount | 1830600 | 427479
Discount | 88065.0403 | 20564.8177
Grand Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419