## Sheet1
Ref # PS/305/11/21 |  |  |  |  | 22 Nov 2021
M/S Dawat-e-Hadiyah Burhani Mahal
Attn: Mr. Muhammad
Bill for (04) Nos Staff Toilet & locker area - Hydery Mall Karachi
S. # | Description | Unit | Qty | Rate | Amount
1 | Supply & Installation of G.I. sheet metal ducting (22 SWG) for air ducting, plenums and other sheet fabrications complete in all respect as per drawings. | Sqft | 480 | 300 | 144000
2 | Supply & Installation of Glass wool insulation 25mm thick for supply air ducts complete in all respect as per drawings. | Sqft | 480 | 160 | 76800
3 | Supply, Installation, testing & Commissioning of pre-insulated phenolic foam ducting complete in all respect as per drawings. | Sqft | 1396 | 365 | 509540
4 | Supply and installation of Sound liner complete with all respect in supply & return air ducts. (Aeroflex 12mm NBR) | Sqft | 140 | 225 | 31500
5 | Supply & installation of Flexible duct connector for packaged units supply and return air connection. | Rft | 14 | 750 | 10500
6 | Supply, Installation, testing & Commissioning of dampers complete in all respect as per drawings.
| 1) Volume control dampers. | Sqin | 1240 | 22 | 27280
| 2) Fire Damper | Sqin | 960 | 22 | 21120
7 | Supply, Installation, testing & Commissioning of Diffusers, Louvers and Grilles complete in all respect
8 | 1) Diffusers (15 x 15) | Nos | 16 | 5950 | 95200
9 | 2) Fresh air intake louwer with filter (10 x 16) | No | 1 | 8500 | 8500
10 | 3) Return air linear bar grill. | Rft | 42 | 900 | 37800
11 | Supply and installation of hangers and supports complete in all respect. | Job | 1 | 60000 | 60000
12 | Shop / as built drawings. | Job | 1 | 8000 | 8000
13 | Air balancing of entire system | Job | 1 | 15000 | 15000
14 | Testing & commissioning of system | Job | 1 | 8000 | 8000
Total Amount Rs |  |  |  |  | 1053240
SST 13% |  |  |  |  | 136921.2
Grand Total Amount Rs |  |  |  |  | 1190161.2
S. # | Description | Unit | Qty | Rate | Amount
1 | Installation of OFM fresh / exhaust air fan. | No. | 8 | 3000 | 24000
2 | Supply, Installation of G.I. sheet metal ducting (22 SWG) for air ducting, plenums and other sheet fabrications complete in all respect as per drawings. | Sqft | 640 | 280 | 179200
3 | Supply & installation of Flexible duct connector for supply and return air. | Job | 4 | 5000 | 20000
4 | Supply and installation of Disc valve for exhaust system for each toilet.
| 1) 06" Dia | Nos | 22 | 1750 | 38500
| 2) 08" Dia | Nos | 2 | 3000 | 6000
5 | Supply, Installation, testing & Commissioning of Fresh air intake louver (8 x 8) | Nos | 2 | 1500 | 3000
6 | Supply and installation of hangers and supports | Job | 4 | 6000 | 24000
7 | Testing, commissioning, air balancing, shop drawings & as built drawings. | Job | 4 | 5000 | 20000
Total Amount Rs |  |  |  |  | 314700
SST 13% |  |  |  |  | 40911
Grand Total Amount Rs |  |  |  |  | 355611
For PIONEER SERVICES.
PIONEER SERVICES