## Sheet1
PS/TNW/306/11/21 | [5 empty] | 2021-11-22
M/S Dawat-e-Hadiyah Burhani Mahal
Mciver Road, Karachi
Attn: Mr. Muhammad
Bill for The North Walk Shopping Mall
S. # | Description | Unit | Qty | BOQ Rate | Billed Qty | Billed Amount
1 | Supply, Installation, testing & Commissioning of medium/low pressure G.I. sheet metal ducting (22 SWG) for air ducting, plenums and other sheet fabrications complete in all respect as per drawings. | Sqft | 1320 | 280 | 1060 | 296800
2 | Supply, Installation & Commissioning of Glass wool insulation of 25mm thickness for supply and return air ducts complete in all respect as per drawings. | Sqft | 1320 | 150 | 1020 | 153000
3 | Supply & installation of Flexible duct connector for supply and return air. | Rft | 40 | 750 | 64 | 48000
4 | Supply, Installation, testing & Commissioning of Diffusers, Louvers and Grilles complete in all respect
| a) Fresh air intake louver | Sqft | 4 | 4000 | 0 | 0
| b) Return air grills | Sqft | 24 | 4000 | 6.42 | 25680
5 | Installation of Jet Diffuser 4" Dia with damper | Nos | 8 | 1000 | 9 | 9000
6 | Installation of Jet Diffuser 6" Dia with damper | Nos | 20 | 1500 | 15 | 22500
7 | Supply, Installation, testing & Commissioning of dampers complete in all respect as per drawings.
| a) VCD | Sqft | 15 | 4000 | 10.92 | 43680 | Advance payment Working
| b) Fire Damper | Sqft | 15 | 5000 | 10.25 | 51250 | Advance | 40% | 424839.32
8 | Supply and installation of Sound liner complete with all respect in supply & return air ducts. (Aeroflex 12mm NBR) | Sqft | 200 | 200 | 250 | 50000 | Less Tax | 7.5% | 31862.949
9 | Supply and installation of hangers & supports complete in all respect. | Job | 1 | 45000 | 1 | 45000 | Cheque amount |  | 392976.371
10 | Air balancing of entire system | Job | 3 | 25000 | 3 | 75000
11 | Testing & comissioning of system. | Job | 3 | 15000 | 3 | 45000
12 | Regging, lifting & installation of vibration isolator according to unit supplier. | Job | 3 | 25000 | 3 | 75000
Total Amount Rs | [5 empty] | 939910
SST Tax 13% | [5 empty] | 122188.3 | Gross amout |  | 1062098.3
Grand Total Amount Rs | [5 empty] | 1062098.3 | received amount |  | 424839.32
[7 empty] | Net |  | 637258.98
Thanking you, | [6 empty] | Less Tax 7.5% |  | 47794.4235
[7 empty] | Net |  | 589464.5565
For PIONEER SERVICES. | [6 empty] | Less 20% SRB W/H |  | 24437.66
565026.8965
958003.2675
[7 empty] | Gross amout |  | 1062098.3
[7 empty] | Less Tax 7.5% |  | 79657.3725
[7 empty] | Net |  | 982440.9275
[7 empty] | Less 20% SRB W/H |  | 24437.66
958003.2675
PIONEER SERVICES