## Main Summary
15 Sept 2021
IMTIAZ SUPER MARKET
IMTIAZ SUPER MARKET, THE PLACE, DHA, KARACHI
GRAND SUMMARY
S.No | DESCRIPTION | Materials | Installation
1 | Cost of HVAC Systems | #REF! | #REF!
2 | Cost of Fire Fighting Systems | #REF! | #REF!
* | Total Project Cost Before Discount | #REF! | #REF!
* | Less: Discount Factor @ 7.403666 % | #REF! | #REF!
* | Total Project Cost After Discount | #REF! | #REF!
* | SST 13% | 0 | #REF!
* | Total after SST | #REF! | #REF!
* | Grand Total Amount | #REF!

## HVAC-BOQ
Item # | Description | Qty. | Unit | BILL OF QUANITITIES |  |  |  |  | YH Verified |  |  |  |  | IMTIAZ Working
|  |  |  | Rates |  | Amount |  | Total Amount | Material |  | Installation |  | Total Billed Amount
|  |  |  | Material | Installation | Material | Installation |  | Billed Qty | Billed Amount | Billed Qty | Billed Amount |  | Billed Qty | Billed Amount
230010 | General Requirements for HVAC System
a. | Making of Shop Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 25000 | 7000 | 25000 | 7000 | 32000 | 1 | 25000 | 1 | 7000 | 32000 | 1 | 32000
b. | Making of As Built Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 15000 | 5000 | 15000 | 5000 | 20000 |  | 0 |  | 0 | 0 |  | 0
d. | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained. | [8 empty] | 0 |  | 0 |  |  | 0
[10 empty] | 0 |  | 0 |  |  | 0
| SUB TOTAL |  |  |  |  | 40000 | 12000 | 52000 |  | 25000 |  | 7000 | 32000 |  | 32000
230100 | Operation and maintenance of HVAC System | [8 empty] | 0 |  | 0 |  |  | 0
230113 | Operation and maintenance of HVAC System | [8 empty] | 0 |  | 0 |  |  | 0
a. | One month test run | 1 | Job | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
b. | Operation and mainteance of HVAC System for one year (One Supervisor, one Mechanics, one Electrician, one helpers) | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
c. | Special tools and instruments for operation and maineance | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
230500 | Common Work Results for HVAC | [8 empty] | 0 |  | 0 |  |  | 0
230513.16 | Wires, Cables, Conduites and Cable Tray | [8 empty] | 0 |  | 0 |  |  | 0
a. | Supply and installation of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system complete in all respect as per drawings and specifications. | 1 | Job | 400000 | 120000 | 400000 | 120000 | 520000 | 0 | 0 |  | 0 | 0 | 0 | 0
230519 | Meters and gages for HVAC Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, installation, testing and commissioning of meters and gagues and accessories for HVAC piping complete in all respect as per drawings and specifications | [8 empty] | 0 |  | 0 | 0 |  | 0
| For Fresh Air Handling Unit (s) | [8 empty] | 0 |  | 0 | 0 |  | 0
i. | Insertion type pipe mounted thermometers | 6 | Nos | 5000 | 500 | 30000 | 3000 | 33000 | 0 | 0 |  | 0 | 0 | 0 | 0
ii. | Pressure gauge | 6 | Nos | 4800 | 500 | 28800 | 3000 | 31800 |  | 0 |  | 0 | 0 |  | 0
iii. | gague cock | 6 | Nos | 800 | 300 | 4800 | 1800 | 6600 |  | 0 |  | 0 | 0 |  | 0
iv. | thermometer well | 6 | Nos | 800 | 300 | 4800 | 1800 | 6600 |  | 0 |  | 0 | 0 |  | 0
230523 | General-Duty Valves for HVAC Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply, installation, testing and commissioning of valves complete with flanges and all other accessories for HVAC piping complete in all respect as per drawings and specifications | [8 empty] | 0 |  | 0 | 0 |  | 0
| Fresh Air Handling Units | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Gate Valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 6 | Nos | 8500 | 1500 | 51000 | 9000 | 60000 |  | 0 |  | 0 | 0 |  | 0
b. | CFRV | [8 empty] | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 3 | Nos | 16500 | 1500 | 49500 | 4500 | 54000 |  | 0 |  | 0 | 0 |  | 0
c. | Motorized Valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 3 | Nos | 85000 | 1500 | 255000 | 4500 | 259500 |  | 0 |  | 0 | 0 |  | 0
| Stand alone controller for FAHU | 3 | Nos | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| Fan Coil Units | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Gate Valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 36 | Nos | 2550 | 800 | 91800 | 28800 | 120600 | 20 | 51000 | 20 | 16000 | 67000 | 20 | 67000
| 32 mm (1-1/4 inch) Diameter | 88 | Nos | 3800 | 800 | 334400 | 70400 | 404800 | 50 | 190000 | 50 | 40000 | 230000 | 48 | 220800
b. | CFRV | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 18 | No | 6850 | 800 | 123300 | 14400 | 137700 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 44 | Nos | 7500 | 800 | 330000 | 35200 | 365200 |  | 0 |  | 0 | 0 |  | 0
c. | Motorized Valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 20 mm (3/4 inch) Diameter | 4 | Nos | 9500 | 1000 | 38000 | 4000 | 42000 |  | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 18 | Nos | 10500 | 1000 | 189000 | 18000 | 207000 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 44 | Nos | 16000 | 1000 | 704000 | 44000 | 748000 |  | 0 |  | 0 | 0 |  | 0
| BTU METERS | [8 empty] | 0 |  | 0 | 0 |  | 0
| 100mm (4 inch) Diameter (200 Gpm) | 1 | No | 0 | 8000 | 0 | 8000 | 8000 |  | 0 |  | 0 | 0 |  | 0
| 150 mm (6 inch) Diameter (295 Gpm) | 1 | No | 0 | 10000 | 0 | 10000 | 10000 |  | 0 |  | 0 | 0 |  | 0
| Miscellanous Valves | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Gate Valves | [8 empty] | 0 |  | 0 | 0 |  | 0
| 150 mm (6 inch) Diameter | 5 | Nos | 47500 | 2500 | 237500 | 12500 | 250000 |  | 0 |  | 0 | 0 |  | 0
| 100 mm (4 inch) Diameter | 3 | Nos | 29900 | 2200 | 89700 | 6600 | 96300 |  | 0 |  | 0 | 0 |  | 0
b. | Globe Valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 100 mm (4 inch) Diameter | 1 | No | 27000 | 2200 | 27000 | 2200 | 29200 |  | 0 |  | 0 | 0 |  | 0
| 150 mm (6 inch) Diameter | 1 | No | 57000 | 2500 | 57000 | 2500 | 59500 |  | 0 |  | 0 | 0 |  | 0
230526 | Hangers and Supports for HVAC Ducting | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of hangers and supports for HVAC ducting complete in all respect as per drawings and specifications. | 1 | Job | 510000 | 25000 | 510000 | 25000 | 535000 | 0.9 | 459000 | 0.9 | 22500 | 481500 | 0.75 | 401250
230529.13 | Hangers and Supports for HVAC Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of hangers and supports for HVAC piping complete in all respect as per drawings and specifications. | 1 | Job | 475000 | 70000 | 475000 | 70000 | 545000 | 0.8 | 380000 | 0.8 | 56000 | 436000 | 0.75 | 408750
230529.16 | Hangers and Supports for HVAC Equipment | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of hangers and supports for HVAC equipment complete in all respect as per drawings and specifications. | 1 | Job | 120000 | 20000 | 120000 | 20000 | 140000 | 0.8 | 96000 | 0.8 | 16000 | 112000 | 0.75 | 105000
230553 | Identification for HVAC Ducting, Piping and Equipment | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of identification for HVAC ducting, piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 35000 | 15000 | 35000 | 15000 | 50000 |  | 0 |  | 0 | 0 |  | 0
230579 | Fire Stopping | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of firestopping complete in all respect as per drawings and specifications. | 1 | Job | 20000 | 5000 | 20000 | 5000 | 25000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 4205600 | 539200 | 4744800 |  | 1176000 |  | 150500 | 1326500 |  | 1202800
230700 | HVAC Insulation | [8 empty] | 0 |  | 0 | 0 |  | 0
230716 | HVAC Equipment Insulation | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, installation of thermal insulation for HVAC Equipment complete in all respect as per drawings and specifications. | 1 | Lot |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
230719.13 | Chilled Water Piping Insulation | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply and installation of premoulded Fiber Glass Insulation of density 64 kg/m3 with Aluminum Facing for chilled water pipes, Including missing insulation on existing pipes bends, tees, unions, sockets, valves and on speicals, wrapped with 8 oz. canvas cloth than painted with anti fungus paint, protected 26 SWG painted G.I. sheet metal cladding complete in all respect as per scheudle, specifications and drawings. | [8 empty] | 0 |  | 0 | 0 |  | 0
i | 38 mm (1-1/2 inch) thickness | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 260 | Rft | 450 | 130 | 117000 | 33800 | 150800 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 1150 | Rft | 500 | 150 | 575000 | 172500 | 747500 |  | 0 |  | 0 | 0 |  | 0
| 38 mm (1-1/2 inch) Diameter | 430 | Rft | 590 | 160 | 253700 | 68800 | 322500 |  | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 580 | Rft | 680 | 170 | 394400 | 98600 | 493000 |  | 0 |  | 0 | 0 |  | 0
ii | 50 mm (2 inch) thickness | [8 empty] | 0 |  | 0 | 0 |  | 0
| 65 mm (2-1/2 inch) Diameter | 620 | Rft | 750 | 200 | 465000 | 124000 | 589000 |  | 0 |  | 0 | 0 |  | 0
| 75 mm (3 inch) Diameter | 250 | Rft | 835 | 210 | 208750 | 52500 | 261250 |  | 0 |  | 0 | 0 |  | 0
| 100 mm (4 inch) Diameter | 370 | Rft | 925 | 250 | 342250 | 92500 | 434750 |  | 0 |  | 0 | 0 |  | 0
| 150 mm (6 inch) Diameter | 230 | Rft | 1150 | 390 | 264500 | 89700 | 354200 |  | 0 |  | 0 | 0 |  | 0
b. | Supply, installation & commissioning of Chilled Water Valves insulation complete in all respect as per drawings and specifications | 1 | Lot | 90000 | 55000 | 90000 | 55000 | 145000 |  | 0 |  | 0 | 0 |  | 0
230719.23 | Refrigerant pipe insulation | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply and installation of 12 mm thick Pre-moulded Foam Pipe and valve Insulation complete in all respect as per schedule, specifications and drawings. | 1 | Lot | 70000 | 30000 | 70000 | 30000 | 100000 |  | 0 |  | 0 | 0 |  | 0
230719.26 | Condensate Drain Insulation | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply and installation of 6 mm thick Pre-moulded Armaflex Pipe Insulation including missing insulation on existing pipe complete in all respect as per schedule, specifications and drawings. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 740 | Rft | 90 | 20 | 66600 | 14800 | 81400 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 320 | Rft | 100 | 25 | 32000 | 8000 | 40000 |  | 0 |  | 0 | 0 |  | 0
| 38 mm (1-1/2 inch) Diameter | 380 | Rft | 107 | 30 | 40660 | 11400 | 52060 |  | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 310 | Rft | 127 | 35 | 39370 | 10850 | 50220 |  | 0 |  | 0 | 0 |  | 0
| 65 mm (2-1/2 inch) Diameter | 200 | Rft | 135 | 40 | 27000 | 8000 | 35000 |  | 0 |  | 0 | 0 |  | 0
| 75 mm (3 inch) Diameter | 150 | Rft | 190 | 45 | 28500 | 6750 | 35250 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 3014730 | 877200 | 3891930 |  | 0 |  | 0 | 0 |  | 0
230800 | Commissioning of HVAC | [8 empty] | 0 |  | 0 | 0 |  | 0
230813 | Testing, Adjusting and balancing for HVAC systems | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Air and Water Testing, balancing and commissioning of HVAC system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 175000 | 25000 | 175000 | 25000 | 200000 |  | 0 |  | 0 | 0 |  | 0
b. | Chilled water Quality test report from PCSIR laboratery to be submitted. | 1 | Job | 25000 | 2000 | 25000 | 2000 | 27000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 200000 | 27000 | 227000 |  | 0 |  | 0 | 0 |  | 0
230900 | Instrumentation and Control for HVAC | [8 empty] | 0 |  | 0 | 0 |  | 0
230923 | Direct-Digital Control System | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of direct-digital control system, Control & Power Wiring and Thermostats with Remote Control (Stand Alone Control) complete in all respect as per drawings and specifications. | 65 | No | 11923.0769 | 1907.6923 | 775000 | 124000 | 899000 |  | 0 |  | 0 | 0 |  | 0
230926 | Building Management System | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation & Commissioning of Building Management system complete in all respect as per drawings and specifications. | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 775000 | 124000 | 899000 |  | 0 |  | 0 | 0 |  | 0
232100 | HVAC Piping and Pumps | [8 empty] | 0 |  | 0 | 0 |  | 0
232113.23 | Hydronic Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of M.S Schedule 40 (as per ASME & API standard, heavy quality with standard Schedule 40 thickness) pipes & fittings for chilled water circulation system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 260 | Rft | 300 | 120 | 78000 | 31200 | 109200 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 1150 | Rft | 395 | 130 | 454250 | 149500 | 603750 | 211 | 83345 | 211 | 27430 | 110775 | 188.4 | 98910
| 38 mm (1-1/2 inch) Diameter | 430 | Rft | 475 | 140 | 204250 | 60200 | 264450 |  | 0 | 0 | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 580 | Rft | 635 | 160 | 368300 | 92800 | 461100 | 355 | 225425 | 355 | 56800 | 282225 | 310 | 246450
| 65 mm (2-1/2 inch) Diameter | 620 | Rft | 890 | 180 | 551800 | 111600 | 663400 | 519 | 461910 | 519 | 93420 | 555330 | 487.3 | 521411
| 75 mm (3 inch) Diameter | 250 | Rft | 1220 | 280 | 305000 | 70000 | 375000 | 242 | 295240 | 242 | 67760 | 363000 | 204.9 | 307350
| 100 mm (4 inch) Diameter | 370 | Rft | 1690 | 350 | 625300 | 129500 | 754800 | 340 | 574600 | 340 | 119000 | 693600 | 306.6 | 625464
| 150 mm (6 inch) Diameter | 230 | Rft | 2825 | 590 | 649750 | 135700 | 785450 |  | 0 |  | 0 | 0 |  | 0
232113.26 | Condensate Drain Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of UPVC Class C pipes & fittings for condensate drain trap system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 740 | Rft | 100 | 20 | 74000 | 14800 | 88800 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 320 | Rft | 107 | 20 | 34240 | 6400 | 40640 |  | 0 |  | 0 | 0 |  | 0
| 38 mm (1-1/2 inch) Diameter | 380 | Rft | 134 | 20 | 50920 | 7600 | 58520 |  | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 310 | Rft | 200 | 20 | 62000 | 6200 | 68200 |  | 0 |  | 0 | 0 |  | 0
| 65 mm (2-1/2 inch) Diameter | 200 | Rft | 330 | 30 | 66000 | 6000 | 72000 |  | 0 |  | 0 | 0 |  | 0
| 75 mm (3 inch) Diameter | 150 | Rft | 460 | 40 | 69000 | 6000 | 75000 |  | 0 |  | 0 | 0 |  | 0
232116 | Hydronic piping specialties | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of hydronic piping specialties alongwith flanges, coupling, unions complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
i | For Fresh Air Handling Unit(s) | [8 empty] | 0 |  | 0 | 0 |  | 0
| Strainers with blow off 20 mm dia ball valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 50 mm (2 inch) Diameter | 3 | Nos | 7500 | 1800 | 22500 | 5400 | 27900 |  | 0 |  | 0 | 0 |  | 0
ii | For Chilled Water Riser | [8 empty] | 0 |  | 0 | 0 |  | 0
| Automatic Air Vent | 2 | Nos | 4200 | 1700 | 8400 | 3400 | 11800 |  | 0 |  | 0 | 0 |  | 0
| For Fan Coil Unit(s) | [8 empty] | 0 |  | 0 | 0 |  | 0
| Strainers with blow off 20 mm dia ball valve | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 18 | No | 2200 | 700 | 39600 | 12600 | 52200 |  | 0 |  | 0 | 0 |  | 0
| 32 mm (1-1/4 inch) Diameter | 44 | Nos | 3500 | 900 | 154000 | 39600 | 193600 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 3817310 | 888500 | 4705810 |  | 1640520 |  | 364410 | 2004930 | 1497.2 | 1799585
232300 | Refrigerant Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
232313 | Refrigerant piping | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of refrigerant piping with valves, fittings and specialities complete in all respect as per drawings and specifications. | 1 | Lot | 90000 | 24000 | 90000 | 24000 | 114000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 90000 | 24000 | 114000 |  | 0 |  | 0 | 0 |  | 0
233100 | HVAC Ducts and Casings | [8 empty] | 0 |  | 0 | 0 |  | 0
233116.23 | Pre-insulated aluminum phenolic foam Ducting | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply, Installation, testing & Commissioning of pre-insulated phenolic foam ducting complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Internal ducting | 14200 | Sq.ft | 230 | 50 | 3266000 | 710000 | 3976000 | 7605 | 1749150 | 7605 | 380250 | 2129400 | 2028 | 567840
233119 | Access door for Fan coil unit | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of access door for fan coil units complete in all respect as per drawings and specifications, for the area where false ceiling has been shown in the drawing. | 1 | Lot | 175000 | 25000 | 175000 | 25000 | 200000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 3441000 | 735000 | 4176000 |  | 1749150 |  | 380250 | 2129400 |  | 567840
233300 | Air Duct Accessories | [8 empty] | 0 |  | 0 | 0 |  | 0
233313 | Dampers | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of dampers complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| Volume Control Damper | 1 | Lot | 30000 | 7000 | 30000 | 7000 | 37000 |  | 0 |  | 0 | 0 |  | 0
| Fire Damper | 1 | Lot | 25000 | 7000 | 25000 | 7000 | 32000 |  | 0 |  | 0 | 0 |  | 0
233343 | Flexible Connectors | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of flexible connectors (AHUS ,FCU & FANS) between blower section and air duct complete in all respect as per drawings and specifications. | 1 | Job | 130000 | 38000 | 130000 | 38000 | 168000 | 0.8 | 104000 | 0.8 | 30400 | 134400 | 0.75 | 126000
233346 | Flexible Duct | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of flexible duct complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 150 mm (6 inch) Diameter | 450 | Rft | 240 | 70 | 108000 | 31500 | 139500 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 293000 | 83500 | 376500 |  | 104000 |  | 30400 | 134400 |  | 126000
233400 | HVAC Fans | [8 empty] | 0 |  | 0 | 0 |  | 0
233419.13 | Blowers and fans | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply, Installation, testing & Commissioning of blowers and fans complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| E.A.FAN 600 CFM Static 0.4" | 2 | Nos | 42000 | 10000 | 84000 | 20000 | 104000 |  | 0 |  | 0 | 0 |  | 0
| E.A.FAN 800 CFM Static 0.3" | 1 | No | 44000 | 10000 | 44000 | 10000 | 54000 |  | 0 |  | 0 | 0 |  | 0
233433 | Air Curtains | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply, Installation, testing & Commissioning of air curtains complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 6 Feet Long 2000 CFM | 2 | Nos | 46000 | 3500 | 92000 | 7000 | 99000 |  | 0 |  | 0 | 0 |  | 0
| 4 Feet Long 1300 CFM | 1 | No | 39500 | 3500 | 39500 | 3500 | 43000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 259500 | 40500 | 300000 |  | 0 |  | 0 | 0 |  | 0
233700 | Air Outlets and inlets | [8 empty] | 0 |  | 0 | 0 |  | 0
233713 | Diffusers, Registers, and Grilles | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply, Installation, testing & Commissioning of Diffusers, Registers and Grilles complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply Air Diffusers (SAD) | [8 empty] | 0 |  | 0 | 0 |  | 0
| 375x375 (15"x15") | 192 | Nos | 4750 | 750 | 912000 | 144000 | 1056000 |  | 0 |  | 0 | 0 |  | 0
b. | Supply Air Round Diffusers (SAD) | [8 empty] | 0 |  | 0 | 0 |  | 0
| 375 mm (15" dia) | 38 | Nos | 5500 | 750 | 209000 | 28500 | 237500 |  | 0 |  | 0 | 0 |  | 0
d | Fresh Air Register (FAR) | [8 empty] | 0 |  | 0 | 0 |  | 0
| 850x300 (34"x12") | 1 | No | 8250 | 500 | 8250 | 500 | 8750 |  | 0 |  | 0 | 0 |  | 0
| 800x300 (32"x12") | 2 | Nos | 8000 | 500 | 16000 | 1000 | 17000 |  | 0 |  | 0 | 0 |  | 0
f. | Exhaust Air Register (EAR) | [8 empty] | 0 |  | 0 | 0 |  | 0
| 225x225 (9"x9") | 9 | Nos | 2300 | 500 | 20700 | 4500 | 25200 |  | 0 |  | 0 | 0 |  | 0
g | Imperialine linear air diffuser 3/4" slot with volume control dampers with link to adjust the damper blade from the face of linear air diffuser complete in all respect as per drawings and specifications | [8 empty] | 0 |  | 0 | 0 |  | 0
| S.A.L.D 3 slot 4 Feet Long | 15 | Nos | 4750 | 450 | 71250 | 6750 | 78000 |  | 0 |  | 0 | 0 |  | 0
h | Fresh air intake louver | 1 | Lot | 35000 | 4000 | 35000 | 4000 | 39000 |  | 0 |  | 0 | 0 |  | 0
i | Exhaust air intake louver | 1 | Lot | 25000 | 7000 | 25000 | 7000 | 32000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 1297200 | 196250 | 1493450 |  | 0 |  | 0 | 0 |  | 0
234100 | Particulate Air Filters | [8 empty] | 0 |  | 0 | 0 |  | 0
234119 | Air Filters | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Panel Air Filters | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply, Installation, testing & Commissioning of Viscous oil type 2 inch (50 mm) thick cleanable type Air Filters complete in all respect as per drawings and specifications. | 1 | Lot | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
237400 | Fresh Air Handling Units | [8 empty] | 0 |  | 0 | 0 |  | 0
237413 | Fresh air handling units | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Installation, lifting, testing & Commissioning of fresh air handling units complete in all respect as per drawings and specifications. | 3 | Nos | 0 | 5000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 0 | 15000 | 15000 |  | 0 |  | 0 | 0 |  | 0
238100 | Decentralized Unitary HVAC Equipment | [8 empty] | 0 |  | 0 | 0 |  | 0
238126.13 | Mini Split Air-Conditioners | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | Supply Installation, testing & Commissioning of Mini Split Air-Conditioners complete in all respect as per drawings and specifications. The copper coils of condensers shall be of heavy duty and with copper fins. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 1 TR HAIER / GREE | 1 | No | 77500 | 3500 | 77500 | 3500 | 81000 |  | 0 |  | 0 | 0 |  | 0
| 2 TR HAIER / GREE | 2 | Nos | 90000 | 3500 | 180000 | 7000 | 187000 |  | 0 |  | 0 | 0 |  | 0
238219 | Fan Coil Units | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | installation, testing & Commissioning of Fan Coil Units complete in all respect as per drawings and specifications. | 62 | Nos | 0 | 2000 | 0 | 124000 | 124000 |  | 0 | 45 | 90000 | 90000 | 45 | 90000
| DISMENTLING WORKS | [8 empty] | 0 |  | 0 | 0 |  | 0
| Dismentling of existing HVAC piping ducting & hanger support system, complete in all respect as per actual site conditions | 1 | Job | 25000 | 5000 | 25000 | 5000 | 30000 | 0.9 | 22500 | 0.9 | 4500 | 27000 | 0.9 | 27000
| SUB TOTAL |  |  |  |  | 282500 | 139500 | 422000 |  | 22500 |  | 94500 | 117000 |  | 117000
TOTAL COST OF HVAC WORKS | [5 empty] | 17715840 | 3701650 | 21417490 | 0 |  |  |  | 5744230 |  | 3845225

## FSS-BOQ
Item # | Description | Qty. | Unit | BILL OF QUANITITIES |  |  |  |  | YH Verified |  |  |  |  | IMTIAZ Working
|  |  |  | Rates |  | Amount |  | Total Amount | Material |  | Installation |  | Total Billed Amount
|  |  |  | Material | Installation | Material | Installation |  | Billed Qty | Billed Amount | Billed Qty | Billed Amount |  | Billed Qty | Billed Amount
210010 | General Requirements for Fire Suppression System
a. | Making of Shop Drawings with sectional details complete in all respect for complete Fire suppression Systems as per Specifications | 1 | Job | 0 | 25000 | 0 | 25000 | 25000 | 1 | 0 | 1 | 25000 | 25000 | 1 | 25000
b. | Making of As Built Drawings with sectional details complete in all respect for complete Fire suppression Systems as per Specifications | 1 | Job | 0 | 10000 | 0 | 10000 | 10000 |  | 0 |  | 0 | 0 |  | 0
e. | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained. | [8 empty] | 0 |  | 0 | 0 |  | 0
[10 empty] | 0 |  | 0 |  |  | 0
| SUB TOTAL |  |  |  |  | 0 | 35000 | 35000 |  | 0 |  | 25000 | 25000 | 1 | 25000
210100 | Operation and maintenance of Fire Suppression System | [8 empty] | 0 |  | 0 |  |  | 0
a. | One month test run | 1 | Job | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
210113 | Operation and maintenance of fire suppression system for one year. | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
210500 | Common Work Results for Fire Suppression | [13 empty] | 25000
210513.16 | Wire, cables, conduites and cable tray | [8 empty] | 0 |  | 0 |  |  | 0
| Supply and installation of of wire, cables, conduites and cable tray for power supply, earthing and controls of fire suppression system complete in all respect as per drawings and specifications. | 1 | Job | 175000 | 25000 | 175000 | 25000 | 200000 | 0 | 0 |  | 0 |  |  | 0
210519 | Pressure gauges | [8 empty] | 0 |  | 0 | 0 | 0 | 0
| Supply and installation of pressure gauges for fire suppression system complete in all respect as per specifications and drawings. | 4 | Nos | 5000 | 2000 | 20000 | 8000 | 28000 |  | 0 |  | 0 | 0 |  | 0
210523 | Valves | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of valves for water based fire suppression system complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| MISCELLANEOUS | [8 empty] | 0 |  | 0 | 0 | 0 | 0
a. | Gate Valves | [8 empty] | 0 |  | 0 | 0 |  | 0
| 1 inch (25 mm) dia | 2 | Nos | 8900 | 1000 | 17800 | 2000 | 19800 |  | 0 |  | 0 | 0 |  | 0
| 2-1/2 inch (65 mm) dia | 6 | Nos | 48500 | 4000 | 291000 | 24000 | 315000 |  | 0 |  | 0 | 0 |  | 0
e. | Pressure regulating valves | [8 empty] | 0 |  | 0 | 0 |  | 0
| 1-1/4 inch (32 mm ) dia, Class 150, Inlet Pressure 250 PSI | 1 | Nos | 6800 | 1000 | 6800 | 1000 | 7800 |  | 0 |  | 0 | 0 |  | 0
| 4 inch (110 mm ) dia, Class 150, Inlet Pressure 250 PSI | 2 | Nos | 248000 | 10000 | 496000 | 20000 | 516000 |  | 0 |  | 0 | 0 |  | 0
210529 | Hangers and supports | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of hangers and supports for fire suppression piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 377000 | 50000 | 377000 | 50000 | 427000 | 0.7 | 263900 | 0.7 | 35000 | 298900 | 0.7 | 298900
210553 | Painting and identification works | [8 empty] | 0 |  | 0 | 0 |  | 0
| Painting and identification works of all components, supports, hangers & brackets etc. complete in all respect as per drawings and specifications. | 1 | Job | 95000 | 15000 | 95000 | 15000 | 110000 | 0.6 | 57000 | 0.6 | 9000 | 66000 | 0.6 | 66000
210563 | Fire stopping | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of fire stopping system complete in all respect as per drawings and specifications. | 1 | Job | 15000 | 5000 | 15000 | 5000 | 20000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 1493600 | 150000 | 1643600 |  | 320900 |  | 44000 | 364900 |  | 0
210800 | Testing, balancing and commissioning of fire suppression system | [8 empty] | 0 |  | 0 | 0 |  | 0
210813 | Testing, balancing and commissioning | [8 empty] | 0 |  | 0 | 0 |  | 0
| Testing, balancing and commissioning of fire suppression system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 25000 | 15000 | 25000 | 15000 | 40000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 25000 | 15000 | 40000 |  | 0 |  | 0 | 0 | 48 | 0
210900 | Instruments and Controls for fire suppression system | [8 empty] | 0 |  | 0 | 0 |  | 0
210913.13 | Zone control valves assembly complete with butterfly valve, water flow switch with supervisory switch (temper switch), pressure gauge, 40 mm sectional drain valve with union and corrosion resistant orifice, butterfuly control valve with supervisory switch as per specifications and drawings. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 4 inch (100 mm) dia | 2 | Nos | 95500 | 15000 | 191000 | 30000 | 221000 |  | 0 |  | 0 | 0 |  | 0
| SUB TOTAL |  |  |  |  | 191000 | 30000 | 221000 |  | 0 |  | 0 | 0 |  | 0
211100 | Fire Suppression Water-Service Piping | [8 empty] | 0 |  | 0 | 0 |  | 0
211113.13 | MS piping | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of ASTM A53 and A120 Schedule 40 MS piping with fittings and specials for fire protection system, including all cutting, fixing, laying through walls and roofs and making good complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
| 25 mm (1 inch) Diameter | 1480 | Rft | 300 | 100 | 444000 | 148000 | 592000 | 849 | 254700 | 849 | 84900 | 339600 | 748.4 | 299360
| 32 mm (1-1/4 inch) Diameter | 220 | Rft | 395 | 125 | 86900 | 27500 | 114400 | 101 | 39895 | 101 | 12625 | 52520 | 100.5 | 52260
| 38 mm (1-1/2 inch) Diameter | 260 | Rft | 475 | 150 | 123500 | 39000 | 162500 | 153 | 72675 | 153 | 22950 | 95625 | 152.4 | 95250
| 50 mm (2 inch) Diameter | 265 | Rft | 635 | 200 | 168275 | 53000 | 221275 | 95 | 60325 | 95 | 19000 | 79325 | 91.2 | 76152
| 62 mm (2-1/2 inch) Diameter | 220 | Rft | 890 | 250 | 195800 | 55000 | 250800 | 442 | 393380 | 442 | 110500 | 503880 | 394.5 | 449730
| 75 mm (3 inch) Diameter | 130 | Rft | 1220 | 300 | 158600 | 39000 | 197600 | 121 | 147620 | 121 | 36300 | 183920 | 119 | 180880
| 100 mm (4 inch) Diameter | 560 | Rft | 1690 | 400 | 946400 | 224000 | 1170400 | 277 | 468130 | 277 | 110800 | 578930 | 171 | 357390
| SUB TOTAL |  |  |  |  | 2123475 | 585500 | 2708975 |  | 1436725 |  | 397075 | 1833800 | 1777
211200 | Fire Suppression Stand pipes | [10 empty] | 0 | 0 |  | 0
211213.13 | Fire hose cabinet (Singel door, surface mounted type, complete mild steel) | [8 empty] | 0 |  | 0 | 0 |  | 0
| Relocating of existing single door fire hose cabinet , with fire hose reel (1"x30 meter, cabinet mounted, swing, manual type) complete in all respect as per drawings. (Supply of 5 Nos of Fire Hose Cabinet) | 5 | Nos | 0 | 5000 | 0 | 25000 | 25000 |  | 0 | 1 | 5000 | 5000 | 1 | 5000
| Supply and installation of Fire Hose Cabinet double compartment with: 1. Fire Hose Reel Size 2-1/2" Dia x 30 Mtr long 2. Jet Spray Nozzle Size 2-1/2" Dia 3. Lock Shield Valve Size 1"Dia 4. Pressure Reducing Valve Size 1" Dia 5. E-Type Landing Valve Size 2-1/2" Dia 6. DCP Fire Extinguisehr 06 KG 7. CO2 Fire Extinguisher 05 KG | 5 | Nos | 225000 | 8000 | 1125000 | 40000 | 1165000 | 3.5 | 787500 | 3.5 | 28000 | 815500 | 3 | 699000
| SUB TOTAL |  |  |  |  | 1125000 | 65000 | 1190000 |  | 787500 |  | 33000 | 820500 |  | 0
211300 | Fire Suppression Sprinkler System | [8 empty] | 0 |  | 0 | 0 |  | 0
211313 | Wet-pipe sprinkler system | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of wet-pipe sprinkler system complete in all respect as per drawings and specifications | [8 empty] | 0 |  | 0 | 0 |  | 0
| Concealed Sprinkler Head 1/2" 68 Deg, Standard Response, Brass Finish, complete with Escuteon plate 1/2" Crome Finish (k=5.6, orifice 1/2") | 250 | Nos | 2000 | 300 | 500000 | 75000 | 575000 |  | 0 |  | 0 | 0 |  | 0
| Horizontal Pendent type Sprinkler Head 1/2" 68 Deg, Standard Response, Brass Finish | 60 | Nos | 1350 | 300 | 81000 | 18000 | 99000 |  | 0 |  | 0 | 0 |  | 0
| Dismantling and shifting of existing Sprinklers to new location as per drawing and specifications | 44 | Nos | 500 | 200 | 22000 | 8800 | 30800 | 44 | 22000 | 44 | 8800 | 30800 | 44 | 30800
| SUB TOTAL |  |  |  |  | 603000 | 101800 | 704800 |  | 22000 |  | 8800 | 30800 |  | 0
212000 | Fire Extinguishing System | [13 empty] | 2610722
212116 | Carbondi Oxide Fire Extinguishers | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of Carbondi Oxide Fire Extinguishers complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
b. | 5 kg | 6 | Nos | 4500 | 500 | 27000 | 3000 | 30000 |  | 0 |  | 0 | 0 |  | 0
212416 | Dry Powder Fire Exitinguishers | [8 empty] | 0 |  | 0 | 0 |  | 0
| Supply and installation of Dry Powder Fire Exitinguishers complete in all respect as per drawings and specifications. | [8 empty] | 0 |  | 0 | 0 |  | 0
a. | 4.5 kg | 6 | Nos | 12500 | 500 | 75000 | 3000 | 78000 | 0 | 0 | 0 | 0 | 0 |  | 0
| DISMENTLING WORKS | [8 empty] | 0 |  | 0 | 0 |  | 0
| Dismentling of piping ducting & Fire Fighting,piping , hanger support ,F.H.C system, complete in all respect as per actual site conditions | 1 | Job | 25000 | 5000 | 25000 | 5000 | 30000 | 0.8 | 20000 | 0.8 | 4000 | 24000 | 0.8 | 24000
| SUB TOTAL |  |  |  |  | 127000 | 11000 | 138000 |  | 20000 |  | 4000 | 24000
0
TOTAL COST OF FIRE FIGHTING WORKS | [5 empty] | 5688075 | 993300 | 6681375 |  |  |  |  | 3099000 |  | 2659722
0
0
0
0
0
0
0
0
0
0
0
0
0
0
2683722
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[14 empty] | 188 | 0
0
[14 empty] | 310 | 0
[14 empty] | 487.3 | 0
[14 empty] | 204.9 | 0
[14 empty] | 306.6 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[14 empty] | 1496.8 | 0
0
0
0
0
0
0
0
[14 empty] | 2028 | 0
0
0
0
0
0
0
0
0
0
[14 empty] | 0.75 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[14 empty] | 0 | 0
0
0
0
0
0
0
0
0
0
[14 empty] | 0.9 | 0
0
[14 empty] | 1496.8 | 5319444