## 3rd bill
24 Mar 2022
IMTIAZ SUPER MARKET
IMTIAZ SUPER MARKET, THE PLACE, DHA, KARACHI
GRAND SUMMARY
Summary of 3rd Running Bill
S.No | DESCRIPTION | Materials | Installation
1 | Cost of HVAC Systems | 1139035.3846 | 227228.4615 | 1366263.8462
2 | Cost of Fire Fighting Systems | 902270 | 127800 | 1030070
3 | Additional Work (Part of BOQ Items) | 25400 | 63700 | 89100
* | Total Amount of Bill Before Discount | 2066705.3846 | 418728.4615
* | Less: Discount Factor @ 7.403666 % | 153011.9639 | 31001.2567
* | Total Amount After Discount | 1913693.4207 | 387727.2048
* | Additional Work (Non BOQ Items) | 91400 | 148500 | 239900
* | Sub-Total Amount | 2005093.4207 | 536227.2048
* | SST 13% | 0 | 69709.5366
* | Total after SST | 2005093.4207 | 605936.7414
* | Grand Total Amount Rs |  | 2611030.1622
* | Less 1st Bill Payment
* | Gross Payable Amount |  | 2611030.1622
* | Less Mobilization Advance 25% Rs |  | 600000
* | Retention 10% Rs |  | 261103.0162
* | Net Payable Amount Rs. |  | 1749927.1459
* | Adhoc Payment received
* | Net |  | 1749927.1459
|  | income tax 7% | 122494.9002
|  | Net | 1627432.2457

## actual summary
Financial Summary for the project Imtiaz Store DHA Phase VIII Karachi
[7 empty] | Contract Value |  |  | 26562748
Receiving details
Payment | Verified Amount | SST 13% on Installation | Gross Verified Amount after SST | Less Mob Adv 25% | Less Retention 10% | Payable Amount | Payment received | Tax Rate | Tax amount | Chq amount | Receive date
Mobilzation Advance 25% | xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx | [5 empty] | 6500000 | 7.5% | 487500 | 6012500 | 2021-07-01
IPC-01 | 6019639.5232 | 136814.3984 | 6156453.9217 | 1504909.8808 | 601963.9523 | 4049580.0885 | 3000000 | 6.5% | 195000 | 2805000 | 2021-10-23 |  | Total Payable Amount |  |  | 3887032
[7 empty] | 1049580 | 7% | 73470.6 | 976109.4 | 2021-11-17 |  | Tax 7% |  |  | 272092.24
IPC-02 | 17395742 | 375687 | 17771429 | 4348935.5 | 1739574.2 | 11682919.3 | 6000000 | 7% | 420000 | 5580000 | 2021-12-01 |  | Net Amount |  |  | 3614939.76
[7 empty] | 5627713 | 6.5% | 365801.345 | 5261911.655 | 2022-01-20
IPC-03 | 2178426 | 42224 | 2220650 | 624204 | 217842.6 | 1378603.4 | 1378603 | 7% | 365801.345 | 1012801.655
Total Amount till to date | 25593807.5232 | 554725.3984 | 26148532.9217 | 6478049.3808 | 2551094 |  | 23555896 |  | 1907573.29 | 21648322.71
[7 empty] | Total Work Done amount till final |  |  | 26148532.9217
[7 empty] | Less Mob 25% |  |  | 6500000
[7 empty] | Less Retention 10% |  |  | 2551094
[7 empty] | Less advance paid in IPC -01 |  |  | 3000000
[7 empty] | final amount paid in IPC -01 |  |  | 1049580
[7 empty] | Less advance paid in IPC -02 |  |  | 6000000
[7 empty] | final amount paid in IPC -02 |  |  | 5627713
[7 empty] | Add Retention 10% |  |  | 2551094
[7 empty] | Net |  |  | 3971239.9217
[14 empty] | HVAC | Fire
[7 empty] | Tax 7% |  |  | 277986.7945 |  | SRB amount |  | 394459 | 276497 | 670956
[12 empty] | 13% |  |  |  | 87224.28
[7 empty] | Net |  |  | 3693253.1272 | [5 empty] | 758180.28
[7 empty] | SRB 20% |  |  | #REF!
[7 empty] | Net |  |  | #REF!
[7 empty] | Extra tax deduct |  |  | 166605
[7 empty] | Net |  |  | #REF!
[7 empty] | IMIAZ AMOUNT |  |  | 3334403
[7 empty] | Difference |  |  | #REF!

## HVAC-BOQ
Item # | Description | Qty. | Unit | BILL OF QUANITITIES |  |  |  |  | Previous Work done |  |  |  | Running Bill No 3 |  |  |  | Total Work Done
|  |  |  | Rates |  | Amount |  | Total Amount
|  |  |  | Material | Installation | Material | Installation |  | Prv Qty | Material Amount | Labour Amount | Total Amount | Curr Qty | Material Amount | Labour Amount | Total Amount | Total Qty | Material Amount | Labour Amount | Total Amount Amount
230010 | General Requirements for HVAC System
a. | Making of Shop Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 25000 | 7000 | 25000 | 7000 | 32000 | 1 | 25000 | 7000 | 32000 |  | 0 | 0 | 0 | 1 | 25000 | 7000 | 32000
b. | Making of As Built Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 15000 | 5000 | 15000 | 5000 | 20000 |  | 0 | 0 | 0 | 1 | 15000 | 5000 | 20000 | 1 | 15000 | 5000 | 20000
d. | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained.
| SUB TOTAL |  |  |  |  | 40000 | 12000 | 52000 |  |  |  | 32000 |  |  |  | 20000 |  |  |  | 52000
230100 | Operation and maintenance of HVAC System
230113 | Operation and maintenance of HVAC System
a. | One month test run | 1 | Job | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. | Operation and mainteance of HVAC System for one year (One Supervisor, one Mechanics, one Electrician, one helpers) | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. | Special tools and instruments for operation and maineance | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
230500 | Common Work Results for HVAC
230513.16 | Wires, Cables, Conduites and Cable Tray
a. | Supply and installation of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system complete in all respect as per drawings and specifications. | 1 | Job | 400000 | 120000 | 400000 | 120000 | 520000 | 0.95 | 380000 | 114000 | 494000 | 0.05 | 20000 | 6000 | 26000 | 1 | 400000 | 120000 | 520000
230519 | Meters and gages for HVAC Piping
a. | Supply, installation, testing and commissioning of meters and gagues and accessories for HVAC piping complete in all respect as per drawings and specifications
For Fresh Air Handling Unit (s)
i. | Insertion type pipe mounted thermometers | 6 | Nos | 5000 | 500 | 30000 | 3000 | 33000 | 10 | 50000 | 5000 | 55000 |  | 0 | 0 | 0 | 10 | 50000 | 5000 | 55000
ii. | Pressure gauge | 6 | Nos | 4800 | 500 | 28800 | 3000 | 31800 | 10 | 48000 | 5000 | 53000 |  | 0 | 0 | 0 | 10 | 48000 | 5000 | 53000
iii. | gague cock | 6 | Nos | 800 | 300 | 4800 | 1800 | 6600 | 10 | 8000 | 3000 | 11000 |  | 0 | 0 | 0 | 10 | 8000 | 3000 | 11000
iv. | thermometer well | 6 | Nos | 800 | 300 | 4800 | 1800 | 6600 | 10 | 8000 | 3000 | 11000 |  | 0 | 0 | 0 | 10 | 8000 | 3000 | 11000
230523 | General-Duty Valves for HVAC Piping
Supply, installation, testing and commissioning of valves complete with flanges and all other accessories for HVAC piping complete in all respect as per drawings and specifications
Fresh Air Handling Units
a. | Gate Valve
| 50 mm (2 inch) Diameter | 6 | Nos | 8500 | 1500 | 51000 | 9000 | 60000 | 8 | 68000 | 12000 | 80000 |  | 0 | 0 | 0 | 8 | 68000 | 12000 | 80000
b. | CFRV
| 50 mm (2 inch) Diameter | 3 | Nos | 16500 | 1500 | 49500 | 4500 | 54000 | 3 | 49500 | 4500 | 54000 |  | 0 | 0 | 0 | 3 | 49500 | 4500 | 54000
c. | Motorized Valve | [16 empty] | 0 | 0
| 50 mm (2 inch) Diameter | 3 | Nos | 85000 | 1500 | 255000 | 4500 | 259500 | 3 | 255000 | 4500 | 259500 |  | 0 | 0 | 0 | 3 | 255000 | 4500 | 259500
| Stand alone controller for FAHU | 3 | Nos | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
Fan Coil Units
a. | Gate Valve
| 25 mm (1 inch) Diameter | 36 | Nos | 2550 | 800 | 91800 | 28800 | 120600 | 36 | 91800 | 28800 | 120600 |  | 0 | 0 | 0 | 36 | 91800 | 28800 | 120600
| 32 mm (1-1/4 inch) Diameter | 88 | Nos | 3800 | 800 | 334400 | 70400 | 404800 | 88 | 334400 | 70400 | 404800 |  | 0 | 0 | 0 | 88 | 334400 | 70400 | 404800
b. | CFRV
| 25 mm (1 inch) Diameter | 18 | No | 6850 | 800 | 123300 | 14400 | 137700 | 18 | 123300 | 14400 | 137700 |  | 0 | 0 | 0 | 18 | 123300 | 14400 | 137700
| 32 mm (1-1/4 inch) Diameter | 44 | Nos | 7500 | 800 | 330000 | 35200 | 365200 | 44 | 330000 | 35200 | 365200 |  | 0 | 0 | 0 | 44 | 330000 | 35200 | 365200
c. | Motorized Valve
| 20 mm (3/4 inch) Diameter | 4 | Nos | 9500 | 1000 | 38000 | 4000 | 42000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 25 mm (1 inch) Diameter | 18 | Nos | 10500 | 1000 | 189000 | 18000 | 207000 | 18 | 189000 | 18000 | 207000 |  | 0 | 0 | 0 | 18 | 189000 | 18000 | 207000
| 32 mm (1-1/4 inch) Diameter | 44 | Nos | 16000 | 1000 | 704000 | 44000 | 748000 | 44 | 704000 | 44000 | 748000 |  | 0 | 0 | 0 | 44 | 704000 | 44000 | 748000
BTU METERS
| 100mm (4 inch) Diameter (200 Gpm) | 1 | No | 0 | 8000 | 0 | 8000 | 8000 |  | 0 | 0 | 0 | 1 | 0 | 8000 | 8000 | 1 | 0 | 8000 | 8000
| 150 mm (6 inch) Diameter (295 Gpm) | 1 | No | 0 | 10000 | 0 | 10000 | 10000 |  | 0 | 0 | 0 | 1 | 0 | 10000 | 10000 | 1 | 0 | 10000 | 10000
Miscellanous Valves
a. | Gate Valves
| 150 mm (6 inch) Diameter | 5 | Nos | 47500 | 2500 | 237500 | 12500 | 250000 | 2 | 95000 | 5000 | 100000 | 4 | 190000 | 10000 | 200000 | 6 | 285000 | 15000 | 300000
| 100 mm (4 inch) Diameter | 3 | Nos | 29900 | 2200 | 89700 | 6600 | 96300 | 2 | 59800 | 4400 | 64200 |  | 0 | 0 | 0 | 2 | 59800 | 4400 | 64200
b. | Globe Valve
| 100 mm (4 inch) Diameter | 1 | No | 27000 | 2200 | 27000 | 2200 | 29200 | 1 | 27000 | 2200 | 29200 |  | 0 | 0 | 0 | 1 | 27000 | 2200 | 29200
| 150 mm (6 inch) Diameter | 1 | No | 57000 | 2500 | 57000 | 2500 | 59500 | 1 | 57000 | 2500 | 59500 |  | 0 | 0 | 0 | 1 | 57000 | 2500 | 59500
230526 | Hangers and Supports for HVAC Ducting
a. | Supply, Installation & Commissioning of hangers and supports for HVAC ducting complete in all respect as per drawings and specifications. | 1 | Job | 510000 | 25000 | 510000 | 25000 | 535000 | 0.95 | 484500 | 23750 | 508250 | 0.05 | 25500 | 1250 | 26750 | 1 | 510000 | 25000 | 535000
230529.13 | Hangers and Supports for HVAC Piping
a. | Supply, Installation & Commissioning of hangers and supports for HVAC piping complete in all respect as per drawings and specifications. | 1 | Job | 475000 | 70000 | 475000 | 70000 | 545000 | 0.95 | 451250 | 66500 | 517750 | 0.05 | 23750 | 3500 | 27250 | 1 | 475000 | 70000 | 545000
230529.16 | Hangers and Supports for HVAC Equipment
a. | Supply, Installation & Commissioning of hangers and supports for HVAC equipment complete in all respect as per drawings and specifications. | 1 | Job | 120000 | 20000 | 120000 | 20000 | 140000 | 0.95 | 114000 | 19000 | 133000 | 0.05 | 6000 | 1000 | 7000 | 1 | 120000 | 20000 | 140000
230553 | Identification for HVAC Ducting, Piping and Equipment
a. | Supply, Installation & Commissioning of identification for HVAC ducting, piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 35000 | 15000 | 35000 | 15000 | 50000 |  | 0 | 0 | 0 | 1 | 35000 | 15000 | 50000 | 1 | 35000 | 15000 | 50000
230579 | Fire Stopping
a. | Supply, Installation & Commissioning of firestopping complete in all respect as per drawings and specifications. | 1 | Job | 20000 | 5000 | 20000 | 5000 | 25000 | 1 | 20000 | 5000 | 25000 |  | 0 | 0 | 0 | 1 | 20000 | 5000 | 25000
| SUB TOTAL |  |  |  |  | 4205600 | 539200 | 4744800 |  |  | 0 | 4437700 |  |  | 0 | 355000 |  |  |  | 4792700
230700 | HVAC Insulation
230716 | HVAC Equipment Insulation
a. | Supply, installation of thermal insulation for HVAC Equipment complete in all respect as per drawings and specifications. | 1 | Lot |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
230719.13 | Chilled Water Piping Insulation
a. | Supply and installation of premoulded Fiber Glass Insulation of density 64 kg/m3 with Aluminum Facing for chilled water pipes, Including missing insulation on existing pipes bends, tees, unions, sockets, valves and on speicals, wrapped with 8 oz. canvas cloth than painted with anti fungus paint, protected 26 SWG painted G.I. sheet metal cladding complete in all respect as per scheudle, specifications and drawings.
i | 38 mm (1-1/2 inch) thickness
| 25 mm (1 inch) Diameter | 260 | Rft | 450 | 130 | 117000 | 33800 | 150800 | 450 | 202500 | 58500 | 261000 |  | 0 | 0 | 0 | 450 | 202500 | 58500 | 261000
| 32 mm (1-1/4 inch) Diameter | 1150 | Rft | 500 | 150 | 575000 | 172500 | 747500 | 929 | 464500 | 139350 | 603850 | 17 | 8500 | 2550 | 11050 | 946 | 473000 | 141900 | 614900
| 38 mm (1-1/2 inch) Diameter | 430 | Rft | 590 | 160 | 253700 | 68800 | 322500 | 173 | 102070 | 27680 | 129750 |  | 0 | 0 | 0 | 173 | 102070 | 27680 | 129750
| 50 mm (2 inch) Diameter | 580 | Rft | 680 | 170 | 394400 | 98600 | 493000 | 590 | 401200 | 100300 | 501500 | 61 | 41480 | 10370 | 51850 | 651 | 442680 | 110670 | 553350
ii | 50 mm (2 inch) thickness
| 65 mm (2-1/2 inch) Diameter | 620 | Rft | 750 | 200 | 465000 | 124000 | 589000 | 518 | 388500 | 103600 | 492100 |  | 0 | 0 | 0 | 518 | 388500 | 103600 | 492100
| 75 mm (3 inch) Diameter | 250 | Rft | 835 | 210 | 208750 | 52500 | 261250 | 199 | 166165 | 41790 | 207955 |  | 0 | 0 | 0 | 199 | 166165 | 41790 | 207955
| 100 mm (4 inch) Diameter | 370 | Rft | 925 | 250 | 342250 | 92500 | 434750 | 319 | 295075 | 79750 | 374825 |  | 0 | 0 | 0 | 319 | 295075 | 79750 | 374825
| 150 mm (6 inch) Diameter | 230 | Rft | 1150 | 390 | 264500 | 89700 | 354200 | 242 | 278300 | 94380 | 372680 | 18 | 20700 | 7020 | 27720 | 260 | 299000 | 101400 | 400400
b. | Supply, installation & commissioning of Chilled Water Valves insulation complete in all respect as per drawings and specifications | 1 | Lot | 90000 | 55000 | 90000 | 55000 | 145000 | 0.95 | 85500 | 52250 | 137750 | 0.05 | 4500 | 2750 | 7250 | 1 | 90000 | 55000 | 145000
230719.23 | Refrigerant pipe insulation
a. | Supply and installation of 12 mm thick Pre-moulded Foam Pipe and valve Insulation complete in all respect as per schedule, specifications and drawings. | 1 | Lot | 70000 | 30000 | 70000 | 30000 | 100000 | 0.95 | 66500 | 28500 | 95000 | 0.05 | 3500 | 1500 | 5000 | 1 | 70000 | 30000 | 100000
230719.26 | Condensate Drain Insulation
a. | Supply and installation of 6 mm thick Pre-moulded Armaflex Pipe Insulation including missing insulation on existing pipe complete in all respect as per schedule, specifications and drawings.
| 25 mm (1 inch) Diameter | 740 | Rft | 90 | 20 | 66600 | 14800 | 81400 | 718 | 64620 | 14360 | 78980 | 100 | 9000 | 2000 | 11000 | 818 | 73620 | 16360 | 89980
| 32 mm (1-1/4 inch) Diameter | 320 | Rft | 100 | 25 | 32000 | 8000 | 40000 | 212 | 21200 | 5300 | 26500 |  | 0 | 0 | 0 | 212 | 21200 | 5300 | 26500
| 38 mm (1-1/2 inch) Diameter | 380 | Rft | 107 | 30 | 40660 | 11400 | 52060 | 315 | 33705 | 9450 | 43155 |  | 0 | 0 | 0 | 315 | 33705 | 9450 | 43155
| 50 mm (2 inch) Diameter | 310 | Rft | 127 | 35 | 39370 | 10850 | 50220 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 65 mm (2-1/2 inch) Diameter | 200 | Rft | 135 | 40 | 27000 | 8000 | 35000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 75 mm (3 inch) Diameter | 150 | Rft | 190 | 45 | 28500 | 6750 | 35250 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 3014730 | 877200 | 3891930 |  |  | 0 | 3325045 |  |  | 0 | 113870 |  |  |  | 3438915
230800 | Commissioning of HVAC
230813 | Testing, Adjusting and balancing for HVAC systems
a. | Air and Water Testing, balancing and commissioning of HVAC system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 175000 | 25000 | 175000 | 25000 | 200000 | 0.95 | 166250 | 23750 | 190000 | 0.05 | 8750 | 1250 | 10000 | 1 | 175000 | 25000 | 200000
b. | Chilled water Quality test report from PCSIR laboratery to be submitted. | 1 | Job | 25000 | 2000 | 25000 | 2000 | 27000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 200000 | 27000 | 227000 |  |  | 0 | 190000 |  |  | 0 | 10000 |  |  |  | 200000
230900 | Instrumentation and Control for HVAC
230923 | Direct-Digital Control System
a. | Supply, Installation & Commissioning of direct-digital control system, Control & Power Wiring and Thermostats with Remote Control (Stand Alone Control) complete in all respect as per drawings and specifications. | 65 | No | 11923.0769 | 1907.6923 | 775000 | 124000 | 899000 | 60 | 715384.6154 | 114461.5385 | 829846.1538 | 5 | 59615.3846 | 9538.4615 | 69153.8462 | 65 | 775000 | 124000 | 899000
230926 | Building Management System
a. | Supply, Installation & Commissioning of Building Management system complete in all respect as per drawings and specifications. | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 775000 | 124000 | 899000 |  |  | 0 | 829846.1538 |  |  | 0 | 69153.8462 |  |  |  | 899000
232100 | HVAC Piping and Pumps
232113.23 | Hydronic Piping
a. | Supply, Installation, testing & Commissioning of M.S Schedule 40 (as per ASME & API standard, heavy quality with standard Schedule 40 thickness) pipes & fittings for chilled water circulation system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 260 | Rft | 300 | 120 | 78000 | 31200 | 109200 | 450 | 135000 | 54000 | 189000 |  | 0 | 0 | 0 | 450 | 135000 | 54000 | 189000
| 32 mm (1-1/4 inch) Diameter | 1150 | Rft | 395 | 130 | 454250 | 149500 | 603750 | 929 | 366955 | 120770 | 487725 | 17 | 6715 | 2210 | 8925 | 946 | 373670 | 122980 | 496650
| 38 mm (1-1/2 inch) Diameter | 430 | Rft | 475 | 140 | 204250 | 60200 | 264450 | 173 | 82175 | 24220 | 106395 |  | 0 | 0 | 0 | 173 | 82175 | 24220 | 106395
| 50 mm (2 inch) Diameter | 580 | Rft | 635 | 160 | 368300 | 92800 | 461100 | 590 | 374650 | 94400 | 469050 | 61 | 38735 | 9760 | 48495 | 651 | 413385 | 104160 | 517545
| 65 mm (2-1/2 inch) Diameter | 620 | Rft | 890 | 180 | 551800 | 111600 | 663400 | 518 | 461020 | 93240 | 554260 |  | 0 | 0 | 0 | 518 | 461020 | 93240 | 554260
| 75 mm (3 inch) Diameter | 250 | Rft | 1220 | 280 | 305000 | 70000 | 375000 | 199 | 242780 | 55720 | 298500 |  | 0 | 0 | 0 | 199 | 242780 | 55720 | 298500
| 100 mm (4 inch) Diameter | 370 | Rft | 1690 | 350 | 625300 | 129500 | 754800 | 319 | 539110 | 111650 | 650760 |  | 0 | 0 | 0 | 319 | 539110 | 111650 | 650760
| 150 mm (6 inch) Diameter | 230 | Rft | 2825 | 590 | 649750 | 135700 | 785450 | 242 | 683650 | 142780 | 826430 | 18 | 50850 | 10620 | 61470 | 260 | 734500 | 153400 | 887900
232113.26 | Condensate Drain Piping
a. | Supply, Installation, testing & Commissioning of UPVC Class C pipes & fittings for condensate drain trap system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 740 | Rft | 100 | 20 | 74000 | 14800 | 88800 | 719 | 71900 | 14380 | 86280 | 100 | 10000 | 2000 | 12000 | 819 | 81900 | 16380 | 98280
| 32 mm (1-1/4 inch) Diameter | 320 | Rft | 107 | 20 | 34240 | 6400 | 40640 | 212 | 22684 | 4240 | 26924 |  | 0 | 0 | 0 | 212 | 22684 | 4240 | 26924
| 38 mm (1-1/2 inch) Diameter | 380 | Rft | 134 | 20 | 50920 | 7600 | 58520 | 315 | 42210 | 6300 | 48510 |  | 0 | 0 | 0 | 315 | 42210 | 6300 | 48510
| 50 mm (2 inch) Diameter | 310 | Rft | 200 | 20 | 62000 | 6200 | 68200 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 65 mm (2-1/2 inch) Diameter | 200 | Rft | 330 | 30 | 66000 | 6000 | 72000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 75 mm (3 inch) Diameter | 150 | Rft | 460 | 40 | 69000 | 6000 | 75000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
232116 | Hydronic piping specialties | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
a. | Supply, Installation, testing & Commissioning of hydronic piping specialties alongwith flanges, coupling, unions complete in all respect as per drawings and specifications.
i | For Fresh Air Handling Unit(s)
Strainers with blow off 20 mm dia ball valve
| 50 mm (2 inch) Diameter | 3 | Nos | 7500 | 1800 | 22500 | 5400 | 27900 | 3 | 22500 | 5400 | 27900 |  | 0 | 0 | 0 | 3 | 22500 | 5400 | 27900
ii | For Chilled Water Riser
| Automatic Air Vent | 2 | Nos | 4200 | 1700 | 8400 | 3400 | 11800 | 2 | 8400 | 3400 | 11800 |  | 0 | 0 | 0 | 2 | 8400 | 3400 | 11800
For Fan Coil Unit(s)
Strainers with blow off 20 mm dia ball valve
| 25 mm (1 inch) Diameter | 18 | No | 2200 | 700 | 39600 | 12600 | 52200 | 18 | 39600 | 12600 | 52200 |  | 0 | 0 | 0 | 18 | 39600 | 12600 | 52200
| 32 mm (1-1/4 inch) Diameter | 44 | Nos | 3500 | 900 | 154000 | 39600 | 193600 | 44 | 154000 | 39600 | 193600 |  | 0 | 0 | 0 | 44 | 154000 | 39600 | 193600
| SUB TOTAL |  |  |  |  | 3817310 | 888500 | 4705810 |  |  | 0 | 4029334 |  |  | 0 | 130890 |  |  |  | 4160224
232300 | Refrigerant Piping
232313 | Refrigerant piping
a. | Supply, Installation, testing & Commissioning of refrigerant piping with valves, fittings and specialities complete in all respect as per drawings and specifications. | 1 | Lot | 90000 | 24000 | 90000 | 24000 | 114000 | 0.95 | 85500 | 22800 | 108300 | 0.05 | 4500 | 1200 | 5700 | 1 | 90000 | 24000 | 114000
| SUB TOTAL |  |  |  |  | 90000 | 24000 | 114000 |  |  | 0 | 108300 |  |  | 0 | 5700 |  |  |  | 114000
233100 | HVAC Ducts and Casings
233116.23 | Pre-insulated aluminum phenolic foam Ducting
Supply, Installation, testing & Commissioning of pre-insulated phenolic foam ducting complete in all respect as per drawings and specifications.
a. | Internal ducting | 14200 | Sq.ft | 230 | 50 | 3266000 | 710000 | 3976000 | 11914 | 2740220 | 595700 | 3335920 | 1064 | 244720 | 53200 | 297920 | 12978 | 2984940 | 648900 | 3633840
233119 | Access door for Fan coil unit
a. | Supply, Installation, testing & Commissioning of access door for fan coil units complete in all respect as per drawings and specifications, for the area where false ceiling has been shown in the drawing. | 1 | Lot | 175000 | 25000 | 175000 | 25000 | 200000 |  | 0 | 0 | 0 | 1 | 175000 | 25000 | 200000 | 1 | 175000 | 25000 | 200000
| SUB TOTAL |  |  |  |  | 3441000 | 735000 | 4176000 |  |  | 0 | 3335920 |  |  | 0 | 497920 |  |  |  | 3833840
233300 | Air Duct Accessories
233313 | Dampers
a. | Supply, Installation, testing & Commissioning of dampers complete in all respect as per drawings and specifications.
| Volume Control Damper | 1 | Lot | 30000 | 7000 | 30000 | 7000 | 37000 | 1 | 30000 | 7000 | 37000 |  | 0 | 0 | 0 | 1 | 30000 | 7000 | 37000
| Fire Damper | 1 | Lot | 25000 | 7000 | 25000 | 7000 | 32000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
233343 | Flexible Connectors
a. | Supply, Installation, testing & Commissioning of flexible connectors (AHUS ,FCU & FANS) between blower section and air duct complete in all respect as per drawings and specifications. | 1 | Job | 130000 | 38000 | 130000 | 38000 | 168000 | 0.95 | 123500 | 36100 | 159600 | 0.05 | 6500 | 1900 | 8400 | 1 | 130000 | 38000 | 168000
233346 | Flexible Duct
a. | Supply, Installation, testing & Commissioning of flexible duct complete in all respect as per drawings and specifications.
| 150 mm (6 inch) Diameter | 450 | Rft | 240 | 70 | 108000 | 31500 | 139500 | 12 | 2880 | 840 | 3720 | 8 | 1920 | 560 | 2480 | 20 | 4800 | 1400 | 6200
| SUB TOTAL |  |  |  |  | 293000 | 83500 | 376500 |  |  | 0 | 200320 |  |  | 0 | 10880 |  |  |  | 211200
233400 | HVAC Fans
233419.13 | Blowers and fans
Supply, Installation, testing & Commissioning of blowers and fans complete in all respect as per drawings and specifications.
| E.A.FAN 600 CFM Static 0.4" | 2 | Nos | 42000 | 10000 | 84000 | 20000 | 104000 | 2 | 84000 | 20000 | 104000 |  | 0 | 0 | 0 | 2 | 84000 | 20000 | 104000
| E.A.FAN 800 CFM Static 0.3" | 1 | No | 44000 | 10000 | 44000 | 10000 | 54000 | 1 | 44000 | 10000 | 54000 |  | 0 | 0 | 0 | 1 | 44000 | 10000 | 54000
233433 | Air Curtains
a. | Supply, Installation, testing & Commissioning of air curtains complete in all respect as per drawings and specifications.
| 6 Feet Long 2000 CFM | 2 | Nos | 46000 | 3500 | 92000 | 7000 | 99000 | 1 | 46000 | 3500 | 49500 | 1 | 46000 | 3500 | 49500 | 2 | 92000 | 7000 | 99000
| 4 Feet Long 1300 CFM | 1 | No | 39500 | 3500 | 39500 | 3500 | 43000 | 1 | 39500 | 3500 | 43000 |  | 0 | 0 | 0 | 1 | 39500 | 3500 | 43000
| SUB TOTAL |  |  |  |  | 259500 | 40500 | 300000 |  |  | 0 | 250500 |  |  | 0 | 49500 |  |  |  | 300000
233700 | Air Outlets and inlets
233713 | Diffusers, Registers, and Grilles
Supply, Installation, testing & Commissioning of Diffusers, Registers and Grilles complete in all respect as per drawings and specifications.
a. | Supply Air Diffusers (SAD)
| 375x375 (15"x15") | 192 | Nos | 4750 | 750 | 912000 | 144000 | 1056000 | 180 | 855000 | 135000 | 990000 |  | 0 | 0 | 0 | 180 | 855000 | 135000 | 990000
b. | Supply Air Round Diffusers (SAD)
| 375 mm (15" dia) | 38 | Nos | 5500 | 750 | 209000 | 28500 | 237500 | 26 | 143000 | 19500 | 162500 |  | 0 | 0 | 0 | 26 | 143000 | 19500 | 162500
d | Fresh Air Register (FAR) | [9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 850x300 (34"x12") | 1 | No | 8250 | 500 | 8250 | 500 | 8750 | 1 | 8250 | 500 | 8750 |  | 0 | 0 | 0 | 1 | 8250 | 500 | 8750
| 800x300 (32"x12") | 2 | Nos | 8000 | 500 | 16000 | 1000 | 17000 | 2 | 16000 | 1000 | 17000 |  | 0 | 0 | 0 | 2 | 16000 | 1000 | 17000
f. | Exhaust Air Register (EAR)
| 225x225 (9"x9") | 9 | Nos | 2300 | 500 | 20700 | 4500 | 25200 | 11 | 25300 | 5500 | 30800 | 1 | 2300 | 500 | 2800 | 12 | 27600 | 6000 | 33600
g | Imperialine linear air diffuser 3/4" slot with volume control dampers with link to adjust the damper blade from the face of linear air diffuser complete in all respect as per drawings and specifications
| S.A.L.D 3 slot 4 Feet Long | 15 | Nos | 4750 | 450 | 71250 | 6750 | 78000 | 6 | 28500 | 2700 | 31200 |  | 0 | 0 | 0 | 6 | 28500 | 2700 | 31200
h | Fresh air intake louver | 1 | Lot | 35000 | 4000 | 35000 | 4000 | 39000 | 0.95 | 33250 | 3800 | 37050 | 0.05 | 1750 | 200 | 1950 | 1 | 35000 | 4000 | 39000
i | Exhaust air intake louver | 1 | Lot | 25000 | 7000 | 25000 | 7000 | 32000 | 0.95 | 23750 | 6650 | 30400 | 0.05 | 1250 | 350 | 1600 | 1 | 25000 | 7000 | 32000
| SUB TOTAL |  |  |  |  | 1297200 | 196250 | 1493450 |  |  | 0 | 1307700 |  |  | 0 | 6350 |  |  |  | 1314050
234100 | Particulate Air Filters
234119 | Air Filters
a. | Panel Air Filters
| Supply, Installation, testing & Commissioning of Viscous oil type 2 inch (50 mm) thick cleanable type Air Filters complete in all respect as per drawings and specifications. | 1 | Lot | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
237400 | Fresh Air Handling Units
237413 | Fresh air handling units
a. | Installation, lifting, testing & Commissioning of fresh air handling units complete in all respect as per drawings and specifications. | 3 | Nos | 0 | 5000 | 0 | 15000 | 15000 | 2 | 0 | 10000 | 10000 | 2 | 0 | 10000 | 10000 | 4 | 0 | 20000 | 20000
| SUB TOTAL |  |  |  |  | 0 | 15000 | 15000 |  |  | 0 | 10000 |  |  | 0 | 10000 |  |  |  | 20000
238100 | Decentralized Unitary HVAC Equipment
238126.13 | Mini Split Air-Conditioners
a. | Supply Installation, testing & Commissioning of Mini Split Air-Conditioners complete in all respect as per drawings and specifications. The copper coils of condensers shall be of heavy duty and with copper fins.
| 1 TR HAIER / GREE | 1 | No | 77500 | 3500 | 77500 | 3500 | 81000 | 1 | 77500 | 3500 | 81000 | 1 | 77500 | 3500 | 81000 | 2 | 155000 | 7000 | 162000
| 2 TR HAIER / GREE | 2 | Nos | 90000 | 3500 | 180000 | 7000 | 187000 | 2 | 180000 | 7000 | 187000 |  | 0 | 0 | 0 | 2 | 180000 | 7000 | 187000
238219 | Fan Coil Units
a. | installation, testing & Commissioning of Fan Coil Units complete in all respect as per drawings and specifications. | 62 | Nos | 0 | 2000 | 0 | 124000 | 124000 | 62 | 0 | 124000 | 124000 | 3 | 0 | 6000 | 6000 | 65 | 0 | 130000 | 130000
DISMENTLING WORKS
| Dismentling of existing HVAC piping ducting & hanger support system, complete in all respect as per actual site conditions | 1 | Job | 25000 | 5000 | 25000 | 5000 | 30000 | 1 | 25000 | 5000 | 30000 |  | 0 | 0 | 0 | 1 | 25000 | 5000 | 30000
| SUB TOTAL |  |  |  |  | 282500 | 139500 | 422000 |  |  |  | 422000 |  |  |  | 87000 |  |  |  | 509000
TOTAL COST OF HVAC WORKS | [5 empty] | 17715840 | 3701650 | 21417490 | 0 | 15281803.6154 | 3196861.5385 | 18478665.1538 |  | 1139035.3846 | 227228.4615 | 1366263.8462 |  | 16420839 | 3424090 | 19844929
[12 empty] | 3755225 |  | 25288100.1538
101103.5246
1265160.3215
29539.7
1294700.0215
90629.0015
[16 empty] | 1204071.02 |  |  |  | 27684434
[16 empty] | 421424.857 |  |  |  | 2048648.116
[16 empty] | 782646.163 |  |  |  | 25635785.884
1369288.5197

## FSS-BOQ
Item # | Description | Qty. | Unit | BILL OF QUANITITIES |  |  |  |  | Previous Work done |  |  |  | Running Bill No 3 |  |  |  | Total Work Done
|  |  |  | Rates |  | Amount |  | Total Amount
|  |  |  | Material | Labour | Material | Installation |  | Prv Qty | Material Amount | Labour Amount | Total Amount | Curr Qty | Material Amount | Labour Amount | Total Amount | Total Qty | Material Amount | Labour Amount | Total Amount
210010 | General Requirements for Fire Suppression System
a. | Making of Shop Drawings with sectional details complete in all respect for complete Fire suppression Systems as per Specifications | 1 | Job | 0 | 25000 | 0 | 25000 | 25000 | 1 | 0 | 25000 | 25000 |  | 0 | 0 | 0 | 1 | 0 | 25000 | 25000
b. | Making of As Built Drawings with sectional details complete in all respect for complete Fire suppression Systems as per Specifications | 1 | Job | 0 | 10000 | 0 | 10000 | 10000 |  | 0 | 0 | 0 | 1 | 0 | 10000 | 10000 | 1 | 0 | 10000 | 10000
e. | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained. | [8 empty] | 0 | 0
| SUB TOTAL |  |  |  |  | 0 | 35000 | 35000 |  | 0 | 25000 | 25000 |  |  | 0 | 10000 |  |  |  | 35000
210100 | Operation and maintenance of Fire Suppression System | [8 empty] | 0 | 0
a. | One month test run | 1 | Job | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
210113 | Operation and maintenance of fire suppression system for one year. | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0
210500 | Common Work Results for Fire Suppression
210513.16 | Wire, cables, conduites and cable tray
| Supply and installation of of wire, cables, conduites and cable tray for power supply, earthing and controls of fire suppression system complete in all respect as per drawings and specifications. | 1 | Job | 175000 | 25000 | 175000 | 25000 | 200000 | 0 | 0 | 0 | 0 | 1 | 175000 | 25000 | 200000 | 1 | 175000 | 25000 | 200000
210519 | Pressure gauges
| Supply and installation of pressure gauges for fire suppression system complete in all respect as per specifications and drawings. | 4 | Nos | 5000 | 2000 | 20000 | 8000 | 28000 | 4 | 20000 | 8000 | 28000 |  | 0 | 0 | 0 | 4 | 20000 | 8000 | 28000
210523 | Valves
Supply and installation of valves for water based fire suppression system complete in all respect as per drawings and specifications.
MISCELLANEOUS
a. | Gate Valves
| 1 inch (25 mm) dia | 2 | Nos | 8900 | 1000 | 17800 | 2000 | 19800 | 7 | 62300 | 7000 | 69300 |  | 0 | 0 | 0 | 7 | 62300 | 7000 | 69300
| 2-1/2 inch (65 mm) dia | 6 | Nos | 48500 | 4000 | 291000 | 24000 | 315000 | 5 | 242500 | 20000 | 262500 |  | 0 | 0 | 0 | 5 | 242500 | 20000 | 262500
e. | Pressure regulating valves | [8 empty] | 0 | 0
| 1-1/4 inch (32 mm ) dia, Class 150, Inlet Pressure 250 PSI | 1 | Nos | 6800 | 1000 | 6800 | 1000 | 7800 | 5 | 34000 | 5000 | 39000 |  | 0 | 0 | 0 | 5 | 34000 | 5000 | 39000
| 4 inch (110 mm ) dia, Class 150, Inlet Pressure 250 PSI | 2 | Nos | 248000 | 10000 | 496000 | 20000 | 516000 | 2 | 496000 | 20000 | 516000 |  | 0 | 0 | 0 | 2 | 496000 | 20000 | 516000
210529 | Hangers and supports
| Supply and installation of hangers and supports for fire suppression piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 377000 | 50000 | 377000 | 50000 | 427000 | 0.95 | 358150 | 47500 | 405650 | 0.05 | 18850 | 2500 | 21350 | 1 | 377000 | 50000 | 427000
210553 | Painting and identification works
| Painting and identification works of all components, supports, hangers & brackets etc. complete in all respect as per drawings and specifications. | 1 | Job | 95000 | 15000 | 95000 | 15000 | 110000 | 0.95 | 90250 | 14250 | 104500 | 0.05 | 4750 | 750 | 5500 | 1 | 95000 | 15000 | 110000
210563 | Fire stopping
| Supply and installation of fire stopping system complete in all respect as per drawings and specifications. | 1 | Job | 15000 | 5000 | 15000 | 5000 | 20000 | 1 | 15000 | 5000 | 20000 |  | 0 | 0 | 0 | 1 | 15000 | 5000 | 20000
| SUB TOTAL |  |  |  |  | 1493600 | 150000 | 1643600 |  | 1318200 | 126750 | 1444950 |  |  | 0 | 226850 |  |  |  | 1671800
210800 | Testing, balancing and commissioning of fire suppression system
210813 | Testing, balancing &commissioning
| Testing, balancing and commissioning of fire suppression system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 25000 | 15000 | 25000 | 15000 | 40000 | 1 | 25000 | 15000 | 40000 | 1 | 25000 | 15000 | 40000 | 2 | 50000 | 30000 | 80000
| SUB TOTAL |  |  |  |  | 25000 | 15000 | 40000 |  | 25000 | 15000 | 40000 |  |  |  | 40000 |  |  |  | 80000
210900 | Instruments and Controls for fire suppression system
210913.13 | Zone control valves assembly complete with butterfly valve, water flow switch with supervisory switch (temper switch), pressure gauge, 40 mm sectional drain valve with union and corrosion resistant orifice, butterfuly control valve with supervisory switch as per specifications and drawings.
| 4 inch (100 mm) dia | 2 | Nos | 95500 | 15000 | 191000 | 30000 | 221000 | 2 | 191000 | 30000 | 221000 |  | 0 | 0 | 0 | 2 | 191000 | 30000 | 221000
| SUB TOTAL |  |  |  |  | 191000 | 30000 | 221000 |  | 191000 | 30000 | 221000 |  |  |  | 0 |  |  |  | 221000
211100 | Fire Suppression Water-Service Piping
211113.13 | MS piping
Supply and installation of ASTM A53 and A120 Schedule 40 MS piping with fittings and specials for fire protection system, including all cutting, fixing, laying through walls and roofs and making good complete in all respect as per drawings and specifications.
| 25 mm (1 inch) Diameter | 1480 | Rft | 300 | 100 | 444000 | 148000 | 592000 | 2076 | 622800 | 207600 | 830400 |  | 0 | 0 | 0 | 2076 | 622800 | 207600 | 830400
| 32 mm (1-1/4 inch) Diameter | 220 | Rft | 395 | 125 | 86900 | 27500 | 114400 | 170 | 67150 | 21250 | 88400 |  | 0 | 0 | 0 | 170 | 67150 | 21250 | 88400
| 38 mm (1-1/2 inch) Diameter | 260 | Rft | 475 | 150 | 123500 | 39000 | 162500 | 248 | 117800 | 37200 | 155000 |  | 0 | 0 | 0 | 248 | 117800 | 37200 | 155000
| 50 mm (2 inch) Diameter | 265 | Rft | 635 | 200 | 168275 | 53000 | 221275 | 345 | 219075 | 69000 | 288075 |  | 0 | 0 | 0 | 345 | 219075 | 69000 | 288075
| 62 mm (2-1/2 inch) Diameter | 220 | Rft | 890 | 250 | 195800 | 55000 | 250800 | 700 | 623000 | 175000 | 798000 | 60 | 53400 | 15000 | 68400 | 760 | 676400 | 190000 | 866400
| 75 mm (3 inch) Diameter | 130 | Rft | 1220 | 300 | 158600 | 39000 | 197600 | 168 | 204960 | 50400 | 255360 |  | 0 | 0 | 0 | 168 | 204960 | 50400 | 255360
| 100 mm (4 inch) Diameter | 560 | Rft | 1690 | 400 | 946400 | 224000 | 1170400 | 455 | 768950 | 182000 | 950950 | 58 | 98020 | 23200 | 121220 | 513 | 866970 | 205200 | 1072170
| SUB TOTAL |  |  |  |  | 2123475 | 585500 | 2708975 |  | 2623735 | 742450 | 3366185 |  |  |  | 189620 |  |  |  | 3555805
211200 | Fire Suppression Stand pipes
211213.13 | Fire hose cabinet (Singel door, surface mounted type, complete mild steel)
| Relocating of existing single door fire hose cabinet , with fire hose reel (1"x30 meter, cabinet mounted, swing, manual type) complete in all respect as per drawings. (Supply of 5 Nos of Fire Hose Cabinet) | 5 | Nos | 0 | 5000 | 0 | 25000 | 25000 | 1 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 1 | 0 | 5000 | 5000
| Supply and installation of Fire Hose Cabinet double compartment with: 1. Fire Hose Reel Size 2-1/2" Dia x 30 Mtr long 2. Jet Spray Nozzle Size 2-1/2" Dia 3. Lock Shield Valve Size 1"Dia 4. Pressure Reducing Valve Size 1" Dia 5. E-Type Landing Valve Size 2-1/2" Dia 6. DCP Fire Extinguisehr 06 KG 7. CO2 Fire Extinguisher 05 KG | 5 | Nos | 225000 | 8000 | 1125000 | 40000 | 1165000 | 5 | 1125000 | 40000 | 1165000 | 1 | 225000 | 8000 | 233000 | 6 | 1350000 | 48000 | 1398000
| SUB TOTAL |  |  |  |  | 1125000 | 65000 | 1190000 |  | 1125000 | 45000 | 1170000 |  |  |  | 233000 |  |  |  | 1403000
211300 | Fire Suppression Sprinkler System
211313 | Wet-pipe sprinkler system
Supply and installation of wet-pipe sprinkler system complete in all respect as per drawings and specifications
| Concealed Sprinkler Head 1/2" 68 Deg, Standard Response, Brass Finish, complete with Escuteon plate 1/2" Crome Finish (k=5.6, orifice 1/2") | 250 | Nos | 2000 | 300 | 500000 | 75000 | 575000 | 210 | 420000 | 63000 | 483000 | 57 | 114000 | 17100 | 131100 | 267 | 534000 | 80100 | 614100
| Horizontal Pendent type Sprinkler Head 1/2" 68 Deg, Standard Response, Brass Finish | 60 | Nos | 1350 | 300 | 81000 | 18000 | 99000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dismantling and shifting of existing Sprinklers to new location as per drawing and specifications | 44 | Nos | 500 | 200 | 22000 | 8800 | 30800 | 44 | 22000 | 8800 | 30800 |  | 0 | 0 | 0 | 44 | 22000 | 8800 | 30800
| SUB TOTAL |  |  |  |  | 603000 | 101800 | 704800 |  | 442000 | 71800 | 513800 |  |  |  | 131100 |  |  |  | 644900
212000 | Fire Extinguishing System
212116 | Carbondi Oxide Fire Extinguishers
Supply and installation of Carbondi Oxide Fire Extinguishers complete in all respect as per drawings and specifications.
b. | 5 kg | 6 | Nos | 4500 | 500 | 27000 | 3000 | 30000 |  | 0 | 0 | 0 | 11 | 49500 | 5500 | 55000 | 11 | 49500 | 5500 | 55000
212416 | Dry Powder Fire Exitinguishers
Supply and installation of Dry Powder Fire Exitinguishers complete in all respect as per drawings and specifications.
a. | 4.5 kg | 6 | Nos | 12500 | 500 | 75000 | 3000 | 78000 | 0 | 0 | 0 | 0 | 11 | 137500 | 5500 | 143000 | 11 | 137500 | 5500 | 143000
DISMENTLING WORKS
| Dismentling of piping ducting & Fire Fighting,piping , hanger support ,F.H.C system, complete in all respect as per actual site conditions | 1 | Job | 25000 | 5000 | 25000 | 5000 | 30000 | 0.95 | 23750 | 4750 | 28500 | 0.05 | 1250 | 250 | 1500 | 1 | 25000 | 5000 | 30000
| SUB TOTAL |  |  |  |  | 127000 | 11000 | 138000 |  | 23750 | 4750 | 28500 |  |  |  | 199500 |  |  |  | 228000
TOTAL COST OF FIRE FIGHTING WORKS | [5 empty] | 5688075 | 993300 | 6681375 |  | 5748685 | 1060750 | 6809435 |  | 902270 | 127800 | 1030070 |  | 6650955 | 1188550 | 7839505
76225.18
953844.82
16614
970458.82
67932.1174
902526.7026
315884.3459
586642.3567