## Summery 1st IPC (hidden)
1st Running Bill
Total Construction
CONSTRUCTION OF NEW SURGICAL ONCOLOGY COMPLEX AT JPMC , KARACHI
Civil Works |  | SUMMARY
S # | BOQ # | Description | Previous Bill Amount | Current Bill Amount | Total Amount ( Rs)
Demolition Works
A | 01-1C | Demolition Works | 0 | #REF! | #REF!
B |  | Earth Work
| 01-2C | Excavation | 0 | #REF! | #REF!
| 01-4C | Back Filling ( out side source ) | 0 | #REF! | #REF!
| 01-5C | Stone Soling | 0 | #REF! | #REF!
C |  | Termite Control Treatment
| 01-6C | Termite | 0 | #REF! | #REF!
D |  | Reinforcement
| 01-7C | Steel Grade 70 | 0 | #REF! | #REF!
E |  | SUB-STRUCTURE
| 01-8C | Class 'E' concrete ( Lean for Foundation ) | 0 | #REF! | #REF!
| 01-10C | Class 'B' concrete (Footing / Foundation) | 0 | #REF! | #REF!
| 01-11C | Class 'A' concrete (Column up to plinth) | 0 | #REF! | #REF!
F |  | Water Proofing & Built up Roofing.
| 01-40C | Bitumen coating grade 10/20 | 0 | #REF! | #REF!
| Total ( A+B+C+D+E+F ) = G |  | 0 | #REF! | #REF! | #REF!
| I | Deduction Against Rebate @ 2.64 % | 0 | #REF! | #REF!
| H= G-I | Work done Amount after Rebate | 0 | #REF! | #REF! | #REF!
Extra Works detail
|  | Relocation of Electrical cables | 0 | 222300 | 222300
|  | Work done Amount including Extra Woks | 0 | #REF! | #REF!
DEDUCTIONS
| I | Recovery of OFM
| ia | Deduction Against Steel 91.23 tons @ 85500 per tons | 0 | -7800250.5 | -7800250.5
| ib | Deduction Against Cement @ 550/= Per Bag ( OPC ) [ 4184 bags ] | 0 | -2301200 | -2301200
| I | Total Amount after OFM Deduction | 0 | #REF! | #REF!
| ja | 10 % Of Retention Mooney | 0 | #REF! | #REF!
| jb | Mobilization Advance | 0 | -2000000 | -2000000
| J | Total Amount After deduction of Retention & Mobilization | 0 | #REF! | #REF!
|  | Deduction Income tax @7.5 % | 0 | #REF! | #REF!
| K | Total Payable Amount after all deductions | 0 | #REF! | #REF!

## Plumbing Works (UGT)
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES 0F PLUMBING AND FIRE FIGHTING WORKS
Item No. | Description | Unit | Qty | Pioneer Quoted | [7 empty] | Net Rates | Basic rates by NESPAK / Market | Total
|  |  |  | Rate | Total Amount (Rupees) | Rebate 12% |  | Tax |  | TC Margin
P. PIPING / PLUMBING WORKS
A. | Water Supply Ref: Spec. No5100 & 5180
1P | PPR cold and hot water pipes SDR - 6 (PN 20) conforming to DIN 8077 & DIN 8078 & fittings, SDR 6 (PN 25) conforming to DIN 16962 of following inner diameters (for unexposed piping)
| a) 1/2 inch Inner Dia. | R-Ft | 25 | 175 | 4375 | 525 | 3850 | 312 | 3538 | 177 | 3361 | 134.44 | 57 | 1425 | 6.722 | 141.162 | 3529.05
| b) 3/4 inch Inner Dia. | R-Ft | 1625 | 230 | 373750 | 44850 | 328900 | 26674 | 302226 | 15111 | 287115 | 176.6862 | 144 | 234000 | 8.8343 | 185.5205 | 301470.75
| c) 1 inch Inner Dia. | R-Ft | 625 | 357 | 223125 | 26775 | 196350 | 15924 | 180426 | 9021 | 171405 | 274.248 | 220 | 137500 | 13.7124 | 287.9604 | 179975.25
| d) 1-1/4 inch Inner Dia. | R-Ft | 250 | 467 | 116750 | 14010 | 102740 | 8332 | 94408 | 4720 | 89688 | 358.752 | 349 | 87250 | 17.9376 | 376.6896 | 94172.4
| e) 1-1/2 inch Inner Dia. | R-Ft | 313 | 661 | 206893 | 24827 | 182066 | 14766 | 167300 | 8365 | 158935 | 507.7796 | 548 | 171524 | 25.389 | 533.1685 | 166881.75
| f) 2 inch Inner Dia. | R-Ft | 125 | 790 | 98750 | 11850 | 86900 | 7048 | 79852 | 3993 | 75859 | 606.872 | 775 | 96875 | 30.3436 | 637.2156 | 79651.95
| g) 2-1/2 inch Inner Dia. | R-Ft | 13 | 1320 | 17160 | 2059 | 15101 | 1225 | 13876 | 694 | 13182 | 1014 | 1115 | 14495 | 50.7 | 1064.7 | 13841.1
| h) 3 inch Inner Dia. | R-Ft | 13 | 3370 | 43810 | 5257 | 38553 | 3127 | 35426 | 1771 | 33655 | 2588.8462 | 1660 | 21580 | 129.4423 | 2718.2885 | 35337.75
2P | Electric Water Cooler | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| h) 90 Ltr / hr | Nos. | 3 | 85000 | 255000 | 30600 | 224400 | 18199 | 206201 | 10310 | 195891 | 65297 | 80000 | 240000 | 3264.85 | 68561.85 | 205685.55
3P | Bronze gate valve of the following diameters. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3/4 inch | Nos. | 1 | 2600 | 2600 | 312 | 2288 | 186 | 2102 | 105 | 1997 | 1997 | 3500 | 3500 | 99.85 | 2096.85 | 2096.85
| b) 1 inch Inner | Nos. | 6 | 3800 | 22800 | 2736 | 20064 | 1627 | 18437 | 922 | 17515 | 2919.1667 | 4900 | 29400 | 145.9583 | 3065.125 | 18390.75
| c) 1-1/4 inch | Nos. | 1 | 4670 | 4670 | 560 | 4110 | 333 | 3777 | 189 | 3588 | 3588 | 7000 | 7000 | 179.4 | 3767.4 | 3767.4
| d) 1-1/2 inch | Nos. | 13 | 5950 | 77350 | 9282 | 68068 | 5520 | 62548 | 3127 | 59421 | 4570.8462 | 9000 | 117000 | 228.5423 | 4799.3885 | 62392.05
| e) 2 inch | Nos. | 9 | 8340 | 75060 | 9007 | 66053 | 5357 | 60696 | 3035 | 57661 | 6406.7778 | 14000 | 126000 | 320.3389 | 6727.1167 | 60544.05
| f) 2-1/2 inch | Nos. | 11 | 33220 | 365420 | 43850 | 321570 | 26079 | 295491 | 14775 | 280716 | 25519.6364 | 17500 | 192500 | 1275.9818 | 26795.6182 | 294751.8
| g) 3 inch | Nos. | 5 | 38800 | 194000 | 23280 | 170720 | 13845 | 156875 | 7844 | 149031 | 29806.2 | 28000 | 140000 | 1490.31 | 31296.51 | 156482.55
| h) 4 inch | Nos. | 3 | 48900 | 146700 | 17604 | 129096 | 10470 | 118626 | 5931 | 112695 | 37565 | 32000 | 96000 | 1878.25 | 39443.25 | 118329.75
4P | C.P. brass double bib tap with muslim shower of following diameter | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3/4 inch | Nos. | 118 | 4350 | 513300 | 61596 | 451704 | 36633 | 415071 | 20754 | 394317 | 3341.6695 | 3000 | 354000 | 167.0835 | 3508.753 | 414032.85
5P | Electric Water Heater Including gate valve and all other accesspries of the following capacity. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 12 US Gallons | No | 5 | 36000 | 180000 | 21600 | 158400 | 12846 | 145554 | 7278 | 138276 | 27655.2 | 25000 | 125000 | 1382.76 | 29037.96 | 145189.8
| b) 25 US Gallons | No | 4 | 44000 | 176000 | 21120 | 154880 | 12561 | 142319 | 7116 | 135203 | 33800.75 | 32000 | 128000 | 1690.0375 | 35490.7875 | 141963.15
| c) 35 Gallons | No | 4 | 53500 | 214000 | 25680 | 188320 | 15273 | 173047 | 8652 | 164395 | 41098.75 | 45000 | 180000 | 2054.9375 | 43153.6875 | 172614.75
B. | PLUMBING FIXTURES Ref: Spec. No 5100 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
6P | Europen water closet (Coupled) including all other necessary accessories as specified & required for installation. | Nos. | 115 | 24000 | 2760000 | 331200 | 2428800 | 196976 | 2231824 | 111591 | 2120233 | 18436.8087 | 20000 | 2300000 | 921.8404 | 19358.6491 | 2226244.65
7P | Europen water closet (Coupled) for disable including all other necessary accessories as specified & required for installation. | Nos. | 3 | 31500 | 94500 | 11340 | 83160 | 6744 | 76416 | 3821 | 72595 | 24198.3333 | 29000 | 87000 | 1209.9167 | 25408.25 | 76224.75
8P | Pedestal type wash basin with all other accessories as specified & required for installation. | Nos. | 43 | 18045 | 775935 | 93112 | 682823 | 55377 | 627446 | 31372 | 596074 | 13862.186 | 13000 | 559000 | 693.1093 | 14555.2953 | 625877.7
9P | Counter type wash basin for all other accessories as specified & required for installation. | Nos. | 64 | 18505 | 1184320 | 142118 | 1042202 | 84523 | 957679 | 47884 | 909795 | 14215.5469 | 5000 | 320000 | 710.7773 | 14926.3242 | 955284.75
10P | Pedestal type wash basin for disable with all other accessories as specified & required for installation. | Nos. | 3 | 15000 | 45000 | 5400 | 39600 | 3212 | 36388 | 1819 | 34569 | 11523 | 7000 | 21000 | 576.15 | 12099.15 | 36297.45
11P | Imported galss mirror of Belgium origin as specified. | SM | 975 | 5600 | 5460000 | 655200 | 4804800 | 389669 | 4415131 | 220757 | 4194374 | 4301.9221 | 8500 | 8287500 | 215.0961 | 4517.0182 | 4404092.7
12P | C.P towel rail as specified. | Nos. | 45 | 2200 | 99000 | 11880 | 87120 | 7065 | 80055 | 4003 | 76052 | 1690.0444 | 1700 | 76500 | 84.5022 | 1774.5467 | 79854.6
13P | C.P toilet paper holder as specified. | Nos. | 118 | 1400 | 165200 | 19824 | 145376 | 11790 | 133586 | 6679 | 126907 | 1075.4831 | 1200 | 141600 | 53.7742 | 1129.2572 | 133252.35
14P | C.P Soap dispensor as Specified. | Nos. | 78 | 1350 | 105300 | 12636 | 92664 | 7515 | 85149 | 4257 | 80892 | 1037.0769 | 900 | 70200 | 51.8538 | 1088.9308 | 84936.6
15P | Shower rose including all accessories as specified. | Nos. | 20 | 11075 | 221500 | 26580 | 194920 | 15808 | 179112 | 8956 | 170156 | 8507.8 | 21645 | 432900 | 425.39 | 8933.19 | 178663.8
16P | Stainless stell single bowl kitchen sink with all accessories as specified & required for installation. | Nos. | 5 | 18400 | 92000 | 11040 | 80960 | 6566 | 74394 | 3720 | 70674 | 14134.8 | 10500 | 52500 | 706.74 | 14841.54 | 74207.7
16P(a) | Stainless steel Sluice including all other accessories complete as specified and as per manufacture's recommendations. | Nos. | 8 | 82000 | 656000 | 78720 | 577280 | 46817 | 530463 | 26523 | 503940 | 62992.5 | 17000 | 136000 | 3149.625 | 66142.125 | 529137
C. | SANITARY DRAINAGE Ref: Spec. No 5100 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
17P | uPVC soil,waste and vent pipes conforming to ASTM D-1785 of Schedule 40 & fittings D-2465 of Schedule 40 including fittings Compatible with pipe of following diameter: | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 1-1/2 inch | R-Ft | 513 | 270 | 138510 | 16621 | 121889 | 9885 | 112004 | 5600 | 106404 | 207.4152 | 136 | 69768 | 10.3708 | 217.786 | 111724.2
| b) 2 inch | R-Ft | 1075 | 351 | 377325 | 45279 | 332046 | 26929 | 305117 | 15256 | 289861 | 269.6381 | 225 | 241875 | 13.4819 | 283.12 | 304354.05
| c) 3 inch | R-Ft | 3250 | 584 | 1898000 | 227760 | 1670240 | 135456 | 1534784 | 76739 | 1458045 | 448.6292 | 335 | 1088750 | 22.4315 | 471.0607 | 1530947.25
| d) 4 inch | R-Ft | 2250 | 630 | 1417500 | 170100 | 1247400 | 101164 | 1146236 | 57312 | 1088924 | 483.9662 | 476 | 1071000 | 24.1983 | 508.1645 | 1143370.2
18P | Floor drains with stainless steel gratings and UPVC P- trap of the folllowing diameter as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3 inch | Nos. | 125 | 4200 | 525000 | 63000 | 462000 | 37468 | 424532 | 21227 | 403305 | 3226.44 | 2700 | 337500 | 161.322 | 3387.762 | 423470.25
19P | Floor trap with stainless steel gratings and UPVC P - trap of the following diameter as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3 inch | Nos. | 138 | 2800 | 386400 | 46368 | 340032 | 27577 | 312455 | 15623 | 296832 | 2150.9565 | 2700 | 372600 | 107.5478 | 2258.5043 | 311673.6
20P | Floor cleanout with brass cover of the following diameter as specified | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3 inch | Nos. | 15 | 5000 | 75000 | 9000 | 66000 | 5353 | 60647 | 3032 | 57615 | 3841 | 2500 | 37500 | 192.05 | 4033.05 | 60495.75
| b) 4 inch | Nos. | 15 | 6000 | 90000 | 10800 | 79200 | 6423 | 72777 | 3639 | 69138 | 4609.2 | 2500 | 37500 | 230.46 | 4839.66 | 72594.9
21P | Plug cleanout of the following diameter as specified | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3 inch | Nos. | 58 | 1800 | 104400 | 12528 | 91872 | 7451 | 84421 | 4221 | 80200 | 1382.7586 | 1000 | 58000 | 69.1379 | 1451.8966 | 84210
| b) 4 inch | Nos. | 50 | 2100 | 105000 | 12600 | 92400 | 7494 | 84906 | 4245 | 80661 | 1613.22 | 1000 | 50000 | 80.661 | 1693.881 | 84694.05
22P | C.I vent cowel for soil / waste pipe of the following diameter as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3 inch | Nos. | 13 | 1800 | 23400 | 2808 | 20592 | 1670 | 18922 | 946 | 17976 | 1382.7692 | 4000 | 52000 | 69.1385 | 1451.9077 | 18874.8
D. | RAIN WATER PIPING. Ref: Spec. No 5100 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
23P | uPVC rain water pipes conforming to ASTM D-1785 of Schedule 40 & fittings D-2465 of Schedule 40 including jointing with solvent cement confirming to ASTM D-2564 compatible with pipe of following diameter: | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 4 inch | R-Ft | 375 | 630 | 236250 | 28350 | 207900 | 16861 | 191039 | 9552 | 181487 | 483.9653 | 475 | 178125 | 24.1983 | 508.1636 | 190561.35
| b) 6 inch | R-Ft | 63 | 950 | 59850 | 7182 | 52668 | 4271 | 48397 | 2420 | 45977 | 729.7937 | 900 | 56700 | 36.4897 | 766.2833 | 48275.85
24P | Cast Iron pipe conforming to BS 416 of following diameter as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| 3 inch | R-Ft | 31 | 1450 | 44950 | 5394 | 39556 | 3208 | 36348 | 1817 | 34531 | 1113.9032 | 1200 | 37200 | 55.6952 | 1169.5984 | 36257.55
| 4 inch | R-Ft | 600 | 1750 | 1050000 | 126000 | 924000 | 74936 | 849064 | 42453 | 806611 | 1344.3517 | 1350 | 810000 | 67.2176 | 1411.5693 | 846941.55
25P | Cast Iron roof drains side inlet type of the following diameter as specified and as shown in the drawing. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| 3 inch | Nos. | 1 | 15000 | 15000 | 1800 | 13200 | 1071 | 12129 | 606 | 11523 | 11523 | 10000 | 10000 | 576.15 | 12099.15 | 12099.15
| 4 inch | Nos. | 1 | 18000 | 18000 | 2160 | 15840 | 1285 | 14555 | 728 | 13827 | 13827 | 12000 | 12000 | 691.35 | 14518.35 | 14518.35
26P | Cast Iron roof drains dome type of the following diameter as specified and as shown in the drawing. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| 3 inch | Nos. | 8 | 20000 | 160000 | 19200 | 140800 | 11419 | 129381 | 6469 | 122912 | 15364 | 10000 | 80000 | 768.2 | 16132.2 | 129057.6
| 4 inch | Nos. | 1 | 25000 | 25000 | 3000 | 22000 | 1784 | 20216 | 1011 | 19205 | 19205 | 12000 | 12000 | 960.25 | 20165.25 | 20165.25
27P | uPVC rain water shoes of following diameters | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 6 inch | Nos. | 1 | 12000 | 12000 | 1440 | 10560 | 856 | 9704 | 485 | 9219 | 9219 | 18000 | 18000 | 460.95 | 9679.95 | 9679.95
| b) 4 inch | Nos. | 8 | 8700 | 69600 | 8352 | 61248 | 4967 | 56281 | 2814 | 53467 | 6683.375 | 20000 | 160000 | 334.1688 | 7017.5437 | 56140.35
E. | EXTERNAL WATER SUPPLY SYSTEM Ref: Spec. No. 5100,5225,5213 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
28P | Supply and installation of HDPE Pipes PE-100, (PN-16 & SDR-11) conforming to ISO-4427 : 1996 with fittings conforming to ISO-3458 including puddle flangesof following diametersas shown in drawings and as specified for filling OHWT. (O.D - Outer Diameter) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia 3.54 inch (90 mm OD) | R-Ft | 500 | 1050 | 525000 | 63000 | 462000 | 37468 | 424532 | 21227 | 403305 | 806.61 | 580 | 290000 | 40.3305 | 846.9405 | 423470.25
29P | GI Pipes and fittings (Medium duty) of following diameters as specified (exposed piping on roof) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia. 4 inch | R-Ft | 25 | 1720 | 43000 | 5160 | 37840 | 3069 | 34771 | 1739 | 33032 | 1321.28 | 635 | 15875 | 66.064 | 1387.344 | 34683.6
| b) Dia. 3 inch | R-Ft | 250 | 1440 | 360000 | 43200 | 316800 | 25692 | 291108 | 14555 | 276553 | 1106.212 | 475 | 118750 | 55.3106 | 1161.5226 | 290380.65
| c) Dia. 2-1/2 inch | R-Ft | 750 | 900 | 675000 | 81000 | 594000 | 48173 | 545827 | 27291 | 518536 | 691.3813 | 370 | 277500 | 34.5691 | 725.9504 | 544462.8
| d) Dia. 2 inch | R-Ft | 563 | 687 | 386781 | 46414 | 340367 | 27604 | 312763 | 15638 | 297125 | 527.7531 | 290 | 163270 | 26.3877 | 554.1408 | 311981.25
| e) Dia. 1-1/2 inch | R-Ft | 250 | 490 | 122500 | 14700 | 107800 | 8743 | 99057 | 4953 | 94104 | 376.416 | 210 | 52500 | 18.8208 | 395.2368 | 98809.2
| f) Dia. 3/4 inch | R-Ft | 100 | 330 | 33000 | 3960 | 29040 | 2355 | 26685 | 1334 | 25351 | 253.51 | 95 | 9500 | 12.6755 | 266.1855 | 26618.55
30P | Gate Valve in chamber of following diameter as shown on the drawing and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia. 3 inch | Nos. | 1 | 43000 | 43000 | 5160 | 37840 | 3069 | 34771 | 1739 | 33032 | 33032 | 28000 | 28000 | 1651.6 | 34683.6 | 34683.6
31P | Dia 2" G.I overflow pipe for over head tank | R-Ft | 13 | 687 | 8931 | 1072 | 7859 | 637 | 7222 | 361 | 6861 | 527.7692 | 2200 | 28600 | 26.3885 | 554.1577 | 7204.05
32P | Cast iron cover with frame of following size (Light Duty) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 2'-0" x 2'x0" | Nos. | 5 | 22000 | 110000 | 13200 | 96800 | 7850 | 88950 | 4448 | 84502 | 16900.4 | 18000 | 90000 | 845.02 | 17745.42 | 88727.1
33P | G.I U-turn vent pipe of following diameter: | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia. 2 inch | Nos. | 5 | 6600 | 33000 | 3960 | 29040 | 2355 | 26685 | 1334 | 25351 | 5070.2 | 1800 | 9000 | 253.51 | 5323.71 | 26618.55
34P | Galavanised M.S ladder rungs for roof tank as specified. | Nos. | 20 | 8000 | 160000 | 19200 | 140800 | 11419 | 129381 | 6469 | 122912 | 6145.6 | 6000 | 120000 | 307.28 | 6452.88 | 129057.6
F. | EXTERNAL SEWERAGE SYSTEM | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| uPVC PIPE AND FITTINGS (SEWERAGE) Ref: Spec No. 5218 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
35P | uPVC drainage pipe & fittings conforming to BS 3505 & BS 4346 of Calss 'B' as specified (below ground) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia 6 inch | R-Ft | 13 | 1450 | 18850 | 2262 | 16588 | 1345 | 15243 | 762 | 14481 | 1113.9231 | 360 | 4680 | 55.6962 | 1169.6192 | 15205.05
| b) Dia 8 inch | R-Ft | 938 | 2188 | 2052344 | 246281 | 1806063 | 146472 | 1659591 | 82980 | 1576611 | 1680.822 | 552 | 517776 | 84.0411 | 1764.8631 | 1655441.55
| c) Dia 10 inch | R-Ft | 94 | 4017 | 377598 | 45312 | 332286 | 26948 | 305338 | 15267 | 290071 | 3085.8617 | 995 | 93530 | 154.2931 | 3240.1548 | 304574.55
| d) Dia 12 inch | R-Ft | 125 | 5577 | 697125 | 83655 | 613470 | 49752 | 563718 | 28186 | 535532 | 4284.256 | 1205 | 150625 | 214.2128 | 4498.4688 | 562308.6
| Gully Trap Ref. Spec. No 5100 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
36P | Chamber with Gully Trap of following size as shown on the drawing. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 1'-6" x 1'-6" | Nos. | 14 | 30000 | 420000 | 50400 | 369600 | 29975 | 339625 | 16981 | 322644 | 23046 | 27000 | 378000 | 1152.3 | 24198.3 | 338776.2
| b) 2' x 2' | Nos. | 1 | 55000 | 55000 | 6600 | 48400 | 3925 | 44475 | 2224 | 42251 | 42251 | 32000 | 32000 | 2112.55 | 44363.55 | 44363.55
| MANHOLES Ref. Spec. No. 5225 & 5233 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
37P | Manholes of following sizes comprising earthworks, plain cement concrete reinforced cement concrete, ladder rungs and C.I (Medium Duty) Cover with frame etc. Complete in all respect as shown on drawings. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 3' x 3' | No | 23 | 80000 | 1840000 | 220800 | 1619200 | 131317 | 1487883 | 74394 | 1413489 | 61456.0435 | 60000 | 1380000 | 3072.8022 | 64528.8457 | 1484163.45
| b) 2' x 2' | No | 1 | 65000 | 65000 | 7800 | 57200 | 4639 | 52561 | 2628 | 49933 | 49933 | 50000 | 50000 | 2496.65 | 52429.65 | 52429.65
| SERVICE CONNECTION Ref: Spec. No 5270 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
38P | Service Connection with existing manhole complete in all respects and as approved by the Engineer. | No | 1 | 120000 | 120000 | 14400 | 105600 | 8564 | 97036 | 4852 | 92184 | 92184 | 50000 | 50000 | 4609.2 | 96793.2 | 96793.2
G. | FIRE FIGHTING Ref: Spec. No. 5150 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
39P | Foam 9 litre | Nos | 5 | 11900 | 59500 | 7140 | 52360 | 4246 | 48114 | 2406 | 45708 | 9141.6 | 5265 | 26325 | 457.08 | 9598.68 | 47993.4
40P | Dry Chemical powder 6 Kg | Nos | 33 | 6900 | 227700 | 27324 | 200376 | 16250 | 184126 | 9206 | 174920 | 5300.6061 | 7600 | 250800 | 265.0303 | 5565.6364 | 183666
41P | Carbon dioxide 5 kg | Nos | 3 | 14400 | 43200 | 5184 | 38016 | 3083 | 34933 | 1747 | 33186 | 11062 | 10000 | 30000 | 553.1 | 11615.1 | 34845.3
42P | Seamless black steel pipe conforming to ASTM A-53 Schedule 40 and fittings conforming to BS - 534 of Following diameters as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia 4 inch | R-Ft | 140 | 2100 | 294000 | 35280 | 258720 | 20982 | 237738 | 11887 | 225851 | 1613.2214 | 976 | 136640 | 80.6611 | 1693.8825 | 237143.55
| b) Dia 3 inch | R-Ft | 388 | 1660 | 644080 | 77290 | 566790 | 45967 | 520823 | 26041 | 494782 | 1275.2113 | 685 | 265780 | 63.7606 | 1338.9719 | 519521.1
| c) Dia 2-1/2 inch | R-Ft | 875 | 1310 | 1146250 | 137550 | 1008700 | 81806 | 926894 | 46345 | 880549 | 1006.3417 | 548 | 479500 | 50.3171 | 1056.6588 | 924576.45
43P | Fire Hose Cabinet including all accessories as shown on drawings and as specified. | Nos | 20 | 42500 | 850000 | 102000 | 748000 | 60663 | 687337 | 34367 | 652970 | 32648.5 | 60000 | 1200000 | 1632.425 | 34280.925 | 685618.5
H. | EXTERNAL FIRE FIGHTING SYSTEM Ref: Spec. No. 5150 & 5180 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
44P | Seamless black steel pipe conforming to ASTM A-53 Schedule 40 and fittings conforming to BS - 534 of Following diameters as specified.(burried pipe wrapped with approved with anti corrosive tape) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia 6 inch | R-Ft | 1000 | 3500 | 3500000 | 420000 | 3080000 | 249788 | 2830212 | 141511 | 2688701 | 2688.701 | 3550 | 3550000 | 134.4351 | 2823.1361 | 2823136.05
45P | Cast Iron Gate Valve (PN-16) in chamber of following diameter as shown on the drawing and as specified | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) Dia 6 inch | Nos. | 4 | 92202 | 368808 | 44257 | 324551 | 26321 | 298230 | 14912 | 283318 | 70829.5 | 68000 | 272000 | 3541.475 | 74370.975 | 297483.9
46P | Siamese Connection as shown on the drawing and as specified | Nos. | 1 | 70000 | 70000 | 8400 | 61600 | 4996 | 56604 | 2830 | 53774 | 53774 | 72000 | 72000 | 2688.7 | 56462.7 | 56462.7
[10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| Total Cost Of Plumbing Works Carried Over to Summary | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| P.PLUMBING WORKS | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| UNDERGROUND WATER TANK & PUMP ROOM | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| MS PIPES & PIPE FITTINGS Ref. Spec. No. 5214 & 5280 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
02b-1P | Supply and Installation of Seamless Black Steel pipe of Schedule 40 Grade B Conforming to ASTM - A53 with fittings conforming to ASTM A-234 including pipe supports as shown in the drawings and as specified (I.D - Internal Diameter) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 6 in (I.D) | R.ft | 31 | 3370 | 104470 | 12536 | 91934 | 7456 | 84478 | 4224 | 80254 | 2588.8387 | 3300 | 102300 | 129.4419 | 2718.2806 | 84266.7
| b) 4 in (I.D) | R.ft | 119 | 2100 | 249900 | 29988 | 219912 | 17835 | 202077 | 10104 | 191973 | 1613.2185 | 1850 | 220150 | 80.6609 | 1693.8794 | 201571.65
| c) 2.5 in (I.D) | R.ft | 6 | 1310 | 7860 | 943 | 6917 | 561 | 6356 | 318 | 6038 | 1006.3333 | 1020 | 6120 | 50.3167 | 1056.65 | 6339.9
| POLY ETHYLENE PIPES & PIPE FITTINGS Ref. Spec 5213 & 5280. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
02b-2P | Supply and installation of HDPE Pipes PE-100 (PN-10 & SDR-17) Conforming to ISO - 4427:1996 with fittings conforming to ISO -3458 including puddle flanges of following diameters as shown in drawings and as specified. (O.D - Ouer Diameter) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 6.29 in or 160mm (O.D) | R.ft | 125 | 1870 | 233750 | 28050 | 205700 | 16682 | 189018 | 9451 | 179567 | 1436.536 | 1250 | 156250 | 71.8268 | 1508.3628 | 188545.35
| VALVES AND APPURTENANCES Ref. Spec. No 5220 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
02b-3P | Supply and installation of flanges ands Cast Iron Gate Valve of the following diameter as per BS 5154 or equivalent (PN-16) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 6 in (I.D) | No. | 3 | 93202 | 279606 | 33553 | 246053 | 19955 | 226098 | 11305 | 214793 | 71597.6667 | 48000 | 144000 | 3579.8833 | 75177.55 | 225532.65
| b) 4 in (I.D) | No. | 9 | 52900 | 476100 | 57132 | 418968 | 33978 | 384990 | 19250 | 365740 | 40637.7778 | 32000 | 288000 | 2031.8889 | 42669.6667 | 384027
| c) 2.5 in (I.D) | No. | 1 | 31460 | 31460 | 3775 | 27685 | 2245 | 25440 | 1272 | 24168 | 24168 | 17500 | 17500 | 1208.4 | 25376.4 | 25376.4
02b-4P | Supply and installation of flanges ends Cast Iron Check Valve of the following diameter conforming to BS 5153 or equivalent (PN-16) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 4 in (I.D) | No. | 6 | 58880 | 353280 | 42394 | 310886 | 25213 | 285673 | 14284 | 271389 | 45231.5 | 35000 | 210000 | 2261.575 | 47493.075 | 284958.45
| b) 2.5 in (I.D) | No. | 1 | 30240 | 30240 | 3629 | 26611 | 2158 | 24453 | 1223 | 23230 | 23230 | 13000 | 13000 | 1161.5 | 24391.5 | 24391.5
02b-5P | Supply and installation of surage relief valve of following diameter including all accessoris as shown in the drawings and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 2 in (I.D) | No. | 1 | 22567 | 22567 | 2708 | 19859 | 1611 | 18248 | 912 | 17336 | 17336 | 9000 | 9000 | 866.8 | 18202.8 | 18202.8
02b-6P | Supply and installation of brass foot valve with strainer of following size as shown in the drawqings and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 4 in (I.D) | No. | 4 | 4500 | 18000 | 2160 | 15840 | 1285 | 14555 | 728 | 13827 | 3456.75 | 17000 | 68000 | 172.8375 | 3629.5875 | 14518.35
02b-7P | Supply and installation of float valve of copper alloy piston type conforming to BS 1212 including float shall be of copper conforming to BS 1968 including all accessories as shown in the drawingsand as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 6 in (I.D) | No. | 1 | 1800 | 1800 | 216 | 1584 | 128 | 1456 | 73 | 1383 | 1383 | 25000 | 25000 | 69.15 | 1452.15 | 1452.15
02b-8P | Supply and installation of galvanized mild steel U-turned vent pipes with puddle flanges as shown in the drawings and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 4 in (I.D) | No. | 10 | 8200 | 82000 | 9840 | 72160 | 5852 | 66308 | 3315 | 62993 | 6299.3 | 7500 | 75000 | 314.965 | 6614.265 | 66142.65
| PUMPING MACHINERY AND ACCESSORIES Ref. Spec. No. 5240 | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
02b-9P | Supply & Insatalltion of Horizontal Centrifugal Pump and Motor of the following capacity and head including pressure gauges level switches and all accessories required to complete the job as shown in the drawings and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| Q = 125 US Gpm, H = 130 ft | No | 3 | 375000 | 1125000 | 135000 | 990000 | 80289 | 909711 | 45486 | 864225 | 288075 | 300000 | 900000 | 14403.75 | 302478.75 | 907436.25
02b-10P | Supply & Installation Deep Well Turbine Pump and Motor of the Following capacity and head including pressure gauges, pressure switches and all accessories required to complete the job as shown in the drawings and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| Q = 200 US Gpm, H = 260 ft | No | 2 | 1150000 | 2300000 | 276000 | 2024000 | 164146 | 1859854 | 92993 | 1766861 | 883430.5 | 820000 | 1640000 | 44171.525 | 927602.025 | 1855204.05
| Q = 50 US Gpm, H = 290 ft | No | 1 | 3520000 | 3520000 | 422400 | 3097600 | 251215 | 2846385 | 142319 | 2704066 | 2704066 | 1640000 | 1640000 | 135203.3 | 2839269.3 | 2839269.3
02b-11P | Supply & Installation of Overhead Ganty with chain pulley of 2 Tonne capacity including all necessary fittings required to complete the job, as shown in the drawings and as specified. | No | 1 | 25000 | 25000 | 3000 | 22000 | 1784 | 20216 | 1011 | 19205 | 19205 | 0 | 0 | 960.25 | 20165.25 | 20165.25
02b-12P | Supply and installaion of Flexible coupling of following sizes as shown on the drawings and as specified. | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 4 in (I.D) | No. | 4 | 32000 | 128000 | 15360 | 112640 | 9135 | 103505 | 5175 | 98330 | 24582.5 | 17500 | 70000 | 1229.125 | 25811.625 | 103246.5
02b-13P | Supply and installation of Water level indicator as shown in the Drawings and as specified. | No. | 1 | 72000 | 72000 | 8640 | 63360 | 5138 | 58222 | 2911 | 55311 | 55311 | 150000 | 150000 | 2765.55 | 58076.55 | 58076.55
02b-14P | Supply and installation of cast iron cover with frame of following sizes (Heavy Duty) | [8 empty] | 0 |  |  |  | 0 | 0 | 0 | 0
| a) 2ft x 2ft | No. | 5 | 19000 | 95000 | 11400 | 83600 | 6780 | 76820 | 3841 | 72979 | 14595.8 | 24000 | 120000 | 729.79 | 15325.59 | 76627.95
Total | [13 empty] | 35774738 |  |  | 37351832.7
Hangers & Supports / Consumable material etc | [13 empty] | 950000
Site Supervision Technician / Labour approximate cost 270,000 x 12 | [13 empty] | 3240000
Net Estimated cost | [13 empty] | 39964738

## Summary
JINNAH POST GRADUATE MEDICAL CENTRE
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
SUMMARY OF COST
| S. NO. | DESCRIPTION | REVISED CONTRACT VALUE
| 1 | CIVIL WORKS | Rs. | #REF!
| 2 | PLUMBING WORKS | Rs. | #REF!
| 3 | ELECTRICAL WORKS | Rs. | #REF!
| 4 | COMMUNICATION WORKS | Rs. | #REF!
| 5 | MECHANICAL WORKS
| 5.1 | INTERNAL GAS PIPING WORKS | Rs. | #REF!
| A | TOTAL BID PRICE | Rs. | #REF!
| B | LESS OVERALL REBATE 11.758% | Rs. | #REF!
| C | FINAL CONTRACT VALUE (INCLUDING RAFT FOUNDATION AND ADDED 4H FLOOR) | Rs. | #REF!