## Lift Lobby
Plumbing works for Cafeteria, Bath & Lift Lobby JS Bank Shaheen Complex Karachi
S. # | Description | BOQ |  |  | Bill
|  | Unit | Qty | Rate | Billed Qty | Billed Amount
PLUMBING WORK
WATER SUPPLY SYSTEM-
1 | providing and fixing, testing and commissioning of complete pipe work for cold and hot water system including all accessories required to complete systems ready to operate as per specification, drawings and instruction of Consultant.
a | Polypropylene Random pipes and fittings with fusion jointing along with all types of unions, tees, bends, sockets, clamps, hangers, supports, sleeves, masking plates, chiseling, making holes making good, excavation, bedding backfilling as required complete in all respect.
i- | Dia 3/4'' (OD 25mm) | Rft. | 240 | 190 | 150 | 28500
ii- | Dia 1'' (OD 32mm) | Rft. | 115 | 310 | 50 | 15500
iii- | Dia 1-1/4'' (OD 40mm) | Rft. | 145 | 400 | 0 | 0
iv- | Dia 1-1/2'' (OD 50mm) | Rft. | 40 | 599 | 357 | 213843
b | Gate vales/ ball vales with unions
i- | Size 3/4'' | Nos | 3 | 4200 | 0 | 0
ii- | Size 1'' | Nos | 4 | 6000 | 3 | 18000
iii- | Size 1-1/2'' | Nos | 1 | 7990 | 0 | 0
SOIL, WASTE VENT AND RAIN WATER DRAINAGE
2 | providing and fixing, testing and commissioning of equipment, pipe work required to complete the soil, waste, vent and rain water system in all respects with accessories ready to operate as per specification, drawings and instruction of Consultant.
a | uPVC pipes class 'D' for approved make alongwith specials, fittings'bends, wye, tees, sockets, sleeves, masking plates, traps,vent cowel,chiseling, making hole, excavation, backfilling making good where as required jointing with rubber ring seal.
i. | Dia. 1-1/2"" | Rft. | 45 | 270 | 48 | 12960
ii. | Dia. 2" | Rft. | 210 | 318 | 20 | 6360
iii. | Dia. 3" | Rft. | 90 | 418 | 40 | 16720
iv. | Dia. 4" | Rft. | 200 | 610 | 127 | 77470
v. | Dia. 6" | Rft. | 55 | 895 | 60 | 53700
c | uPVC cowl for vent pipe of the following dia. including all accessories complete.
i. | Size 2'' | Nos. | 4 | 1200 | 0 | 0
d | Cleanout for soil, waste pipes of approved make
i. | 4" dia. FCO With SS floor cover plate | Nos. | 8 | 3800 | 6 | 22800
3 | Providing & fixing SS Sink Bowl with Sink Mixture (Grohe), stop cocks for hot and cold water, bottle trap, C.P. strainer, pipe connections, C.P. brass waste chain plug making requisite number of holes in walls, floor for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. (CAFETERIA) | Nos. | 1 | 75000 | 1 | 75000
4 | Providing & fixing Vanity Counter with Mixture (Grohe), stop cocks for hot and cold water, bottle trap, C.P. strainer, pipe connections, C.P. brass waste chain plug making requisite number of holes in walls, floor for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. Basic Price of Vanity Rs. 18,000/- Basic Price of Mixer Rs. 20,000/-
i | Executive Toilets | Nos. | 3 | 62000 | 0 | 0
ii | Staff Toilets | Nos. | 7 | 59000 | 4 | 236000
5 | Providing and install English W.C. wall hung type with Flush Tank make by (Roca), of approved sample with required fittings of (Grohe) make including all accessories. (Executive Toilets) Basic Price Rs. 45,000/- | Nos. | 3 | 62000 | 0 | 0
6 | Providing and install English W.C. wall hung type with Flush Tank make by (Roca), of approved sample with required fittings of (Grohe) make including all accessories. (Staff Toilets) Basic Price Rs. 45,000/- | Nos. | 14 | 58000 | 9 | 522000
7 | Providing and install Bibcock with Muslim Shower as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 5,500/- | Nos. | 17 | 7900 | 9 | 71100
8 | Providing and install Paper Holder as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 2,500/- | Nos. | 17 | 4200 | 9 | 37800
9 | Providing and install Towel Ring as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 1,650/- | Nos. | 4 | 2800 | 9 | 25200
10 | Providing and install Single Bibcock for Ablution as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 20,000/- | Nos. | 11 | 23500 | 4 | 94000
11 | Providing and install Soap Dispencer as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 4,500/- | Nos. | 6 | 6000 | 2 | 12000
12 | Providing and install Shower Head as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 15,000/- | Nos. | 1 | 24500 | 0 | 0
13 | Providing and install Coat Hook as approved by Architect (S.Abdullah or J.B Saeed) Basic Price Rs. 1,500/- | Nos. | 17 | 2800 | 9 | 25200
14 | Providing and install in position SS Floor drain with SS grating as approved by the Architect. (S.Abdullah or J.B Saeed) Basic Price Rs. 1,350/- | Nos. | 27 | 3500 | 14 | 49000
MECHANICAL VENTILATION SYSTEM
Centrifugal Exhaust air fan with siemens/ABB motor, inlet plenum, vibration isolators and accessories, complete in all respects.
1 | Centrifugal Exhaust air fans with siemens/ABB motor, inlet plenum, vibration isolators and accessories, complete in all respects.
i. | Exhaust air fan rated 800 cfm, ESP 1.5" of WC | Nos. | 4 | 25000 | 3 | 75000
2 | Providing, Fabrication and installation of 24 SWG MS duct for Grill duffuser sections of Toilet exhaust air complete in all respects including plenums, splitter dampers, plenums chambers, supports & hangers compete in all respects as per drawings and as per instructions of Consultant. | Sqft | 860 | 290 | 145 | 42050
3 | Providing & fixing of powder coated air registers / grills (fresh and eshaust air) with Volume Control Dampers complete in all respects ready to operate as per drawings. |  |  |  |  | 0
i. | Exhaust Air Diffuser (E.A.G) |  |  |  |  | 0
| 6" x 6" | Nos. | 32 | 2800 | 12 | 33600
TOTAL COST | [5 empty] | 1763803

## Summary of bills
Summary of Bill
Plumbing Works at JS Bank Shaheen Complex Cafeteria, Karachi.
Sr # | DESCRIPTION | AMOUNT (PKR)
1 | Plumbing Fixtures | 1763803
2 | Variation order for Cassette type units | 373293.75 | Will be submitted in next bill
| Total Cost of Bill | 2137096.75