## HVAC
HVAC Work for JS Bank Shaheen Complex Karachi
S. # | Description | BOQ |  |  | Bill
|  | Unit | Qty | Rate | Billed Qty | Billed Amount
1 | Lifting, shifting, Installation, testing & commissioning of owner provided ODU (as per tender drawing) with foundation Complete in all respect and ready to operate. | Nos. | 4 | 13498 | 4 | 53992
2 | Lifting , shifting, Installation, testing & commissioning of owner provided IDU FCU's Ducted Type Units (as per tender drawing) with support, rubber isolators, flexible c onnec tor complete in all respect and ready to operate. | Nos. | 12 | 4049 | 12 | 48588
3 | Lifting, shifting, Installation, testing & commissioning of owner provided IDU FCU's Wall-Mount Units (as per tend er drawing) with support complete in all respect and ready to operate. | Nos. | 6 | 2250 | 6 | 13500
4 | Lifting, shifting, Installation, testing & commissioning of owner provided split Units (as per tender drawing) with support complete in all respect and ready to operate. | Nos. | 6 | 2250 | 6 | 13500
5 | Supply and installation of copper piping with fittings, (OFM y-joints), welding, copper rods, nitrogen gas, hangers and supports, core cutting, slee ves in walls with all necessary accessories.
5a | 1-1/8" | RFT | 310 | 1799 | 400 | 719600
Sb | 7/8" | RFT | 16 | 981 | 41 | 40221
5c | 3/4" | RFT | 74 | 1106 | 84 | 92904
5d | 5/8 " | RFT | 447 | 684 | 535 | 365940
Se | 3/8" | RFT | 332 | 396 | 352 | 139392
Sf | 1/2" | RFT | 190 | 530 | 232 | 122960
Sg | 1/4" | RFT | 84 | 287 | 135 | 38745
6 | Suppl y and installation of copper piping foam insulation 13 mm dia with black taping {4") in all piping & necessary accessories.
6a | 1-1/8" | RFT | 310 | 192 | 400 | 76800
6b | 7/8" | RFT | 16 | 177 | 41 | 7257
6c | 3/ 4" | RFT | 74 | 163 | 84 | 13692
6d | 5/8" | RFT | 447 | 148 | 535 | 79180
6e | 3/8" | RFT | 332 | 129 | 352 | 45408
6f | 1/2" | RFT | 190 | 137 | 232 | 31784
6g | 1/4" | RFT | 84 | 117 | 135 | 15795
7 | Supply and installation of copper piping for split units with electrical conduit and electrical & control wiring from indoor to outdoor and to MCC with c ommissi oning, hangers and support with all necessary accessories.
| 5/8",3/8" | RFT | 362 | 675 | 430 | 290250
8 | Supply and installation of copper piping form insulation for split units 10 mm thickness with taping & oil necessary accessories.
8a | 5/8" | RFT | 362 | 148 | 430 | 63640
8b | 3/8" | RFT | 362 | 129 | 430 | 55470
9 | Supply and installation, testing, commisioning, balancing of GI Ducting with hangers and supports complete in all respect
9a | 22 Guage | SQFT | 3000 | 189 | 4000 | 756000
9b | 24 Guage | SQFT | 1000 | 189 | 855 | 161595
10 | Supply and Installation of GI Ducting fibre gloss insulation 1" thick 64 kg/cubic meter density with canvas cloth 8 oz, fire retordent paint st enc iling, aluminium tape complete in all respect
10a | 22 Guage | SQFT | 3000 | 76 | 4000 | 304000
10b | 24 Guage | SQFT | 1000 | 76 | 762 | 57912
11 | Supply and installation of supply & return air diffusers with dampers (as per approved colour by architect)
| 15" X 15" | Nos. | 46 | 4949 | 46 | 227654
12 | Supply and installation of supply & return double defflection grills with dampers (as per approved colour by architect)
12a | 30"X8" | Nos. | 6 | 6119 | 4 | 24476
12b | 24"X8" | Nos. | 10 | 5309 | 10 | 53090
12c | 36" X8" | Nos. | 2 | 7109 | 4 | 28436
12d | 36" X6" | Nos. | 2 | 7109 | 2 | 14218
13 | Supply & Installation of UPVC condensate drain piping class D including chiseling, cutting of walls, floor with hanger and supports complete in all respect.
13a | 3/4" dia | RFT | 180 | 108 | 190 | 20520
13b | 1" dia | RFT | 268 | 135 | 58 | 7830
13c | 1-1/2" dia | RFT | 220 | 148 | 326 | 48248
14 | Supply & Installation of UPVC condensate drain piping i nsulation 10 mm thick with complete taping in all pipes including chiseling, cutting of walls, floor with hanger and supports complete in all respect.
14a | 3/4" dia | RFT | 180 | 108 | 190 | 20520
14b | 1" dia | RFT | 268 | 135 | 58 | 7830
14c | 1-1/2" dia | RFT | 220 | 148 | 326 | 48248
15 | Shielded Control wiring 2 core, 1.5 sq mm with cunduit and supports for VRF units from outdoor to indoor units each circuit. | job | 1 | 147716 | 1 | 147716
16 | Electrical Wiring from outdoor unit to main circuit (4+l)core, 16 sq mm run in cable tray with support and commisioning and accessories. | job | 1 | 237701 | 1 | 237701
17 | Electrical Wiring from indoor unit circuit to MCC 3 core, 2.5 sq mm run in conduit with support and commisioning and accessories. | job | 1 | 147716 | 1 | 147716
18 | Testing and commisioning of HVAC Works. | job | 1 | 57732 | 1 | 57732
19 | Submission of shop and as built drawing with section and detail. | set | 3 | 22565 | 3 | 67695
20 | Supply & installation of MCC for VRF Units with Ampere, Volt meter, CT, Relay , spare breakers & all necessary with below detail. | Nos. | 1 | 179211 | 1 | 179211
(ODU 1) 45 Amp & 17 Amp for IOU circuit
(ODU 2) 45 Amp & 12 Amp for IDU circuit
(OOU 3) 45 Amp & 16 Amp for IOU circuit
(OOU 4) 32 Amp & 10 Amp for IOU circuit
2.S Tr 06 Split Units
TOTAL COST FOR HVAC WORKS | [5 empty] | 4946966

## Plumbing
Plumbing Work for JS Bank Shaheen Complex Karachi
S. # | Description | BOQ |  |  | Bill
|  | Unit | Qty | Rate | Billed Qty | Billed Amount
1 | PLUMBING WOR
2 | Providing and install of Hot & Cold water supply PPR & UPVC drainage piping (Dadex or approved equivalent), as per plumbing drawing with all accessories such as P trap, Y trap, bend, socket, reducer, etc., including fitting & fixture, making requisite holes in wall & floor etc. as per requirement complete in all respect as per drawing & details and as directed by the Architect.
3 | Toilet | Job | 3 | 119686 | 3 | 359058
4 | Kitchen | Job | 1 | 51865 | 1 | 51865
5 | Core cutting for plumbing line. | Nos | Rate Only | 7979 | 0 | 0
5a | Supply, installation, testing & commissioning of Wall Hung Water closet with "P" or "S" trap, including imported concealed flush tank C.P. stop cock, C.P., Muslim shower with all accessories & fittings, complete all connection and relative material making requisite hole in walls, floors for pipe connections and making good with approved materials complete in all respects in as shown on drawings & specifications. (Water Closet & Flush Tank Roca and other accessories Grohe) (Basic Price Rs. 65000/-) | Nos | 3 | 68820 | 3 | 206460
Sb | Supply & installation of vanity counter top including imported one hole C.P. faucet, stop cocks for hot and cold water, bottle trap, C.P. strainer, pipe connections, C.P. brass waste chain plug complete with concealed safety brackets, waste water jointing assembly, making requisite number of holes in walls, floor for pipe connections and making good with approved material complete in all respects as shown on drawings & speci.fications. (Vanity Counter Roca, Other Accessories Grobe) Basic Price Rs. 45,000/- | Nos | 3 | 53221 | 3 | 159663
5c | Providing & fixing SS Sink Bowl with Sink Mixture (Grohe), stop cocks for hot and cold water, bottle trap, C.P. strainer, pipe connections, C.P. brass waste chain plug making requisite number of holes in walls, floor for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. | Nos | 1 | 44006 | 1 | 44006
5d | Providing & fixing of Towel Rail (Orrome finish) of approved sample by Architect. S. Abdullah or JB Saeed. | Nos | 3 | 10556 | 3 | 31668
Se | Providing & fixing of Paper Holder (Chrome finish) of approved sample by Architect. S. Abdullah or JB Saeed. | Nos | 3 | 6886 | 3 | 20658
Sf | Providing & fixing of Liquid Dispenser of approved sample by Architect. S. Abdullah or JB Saeed. | Nos | 3 | 6886 | 3 | 20658
Sg | Providing & fixing of Double Coat Hook of approved sample by Architect. | Nos | 3 | 3216 | 3 | 9648
6 | Providing & fixing of SS Floor Drain. Basic Price Rs. 2000/- | Nos | 4 | 1835 | 4 | 7340
6a | Providing & fixing of Siemens Hand Dryer of approved sample by Architect. Basic Price Rs.15000/- | Nos | 2 | 13764 | 2 | 27528
TOTAL COST | [5 empty] | 938552

## Summary of bills
Summary of Bill
HVAC & Plumbing Works at JS Bank Shaheen Complex 1st Floor, Karachi.
Sr # | DESCRIPTION | AMOUNT (PKR)
1 | HVAC Works | 4946966
2 | Plumbing Fixtures | 938552
3 | Variation order for VRF Condensing units. | 141093.75
4 | Variation order for Automatic Sensor Tap | 99773.4375
| Total Cost of Bill | 6126385.1875