## Table 2
BILL OF QUANTITIES OF HVAC WORKS | [5 empty] | Running Bill
S. No. | Description | Qty. | Unit | Material (Rs.) | Labour (Rs.) | Billed | Material (Rs.) | Labour | Total (Rs.)
|  |  |  | Rate | Rate | Qty | Amount | Amount | Amount
SECTION 01: SUPPLY, INSTALLATION & TESTING OF PIPING WORKS
1 | Supply, Installation, Testing & Balalncing of MS Sch. 40 Seamless Pipes (for Chilled Water Supply/Return) with threaded & welded fittings including sockets, tees, elbows, bends, reducers, unions, clamps, hangers & supports etc. making core cuts/holes (if required), painting and protection treatments on pipe. complete in all respect ready to operate as per specifications, drawings and as per instruction of Consultant.
a | Ø 1-1/2" | 5 | Rft. | 1090 | 280 |  | 0 | 0 | 0
b | Ø 1-1/4" | 40 | Rft. | 960 | 260 |  | 0 | 0 | 0
c | Ø 1" | 40 | Rft. | 760 | 210 |  | 0 | 0 | 0
2 | Supply & Installation of Pre Formed Thermopore insulation (32 kg/m3 density) for chilled water M.S. pipes, bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz Canvas cloth than paint with Anti fungus paint etc, complete in all respects ready to operate.
2.1 | 25 mm Thick Insulation
a | Ø 1-1/2" | 5 | Rft. | 490 | 90 |  | 0 | 0 | 0
b | Ø 1-1/4" | 40 | Rft. | 470 | 85 |  | 0 | 0 | 0
c | Ø 1" | 40 | Rft. | 410 | 80 |  | 0 | 0 | 0
3 | Supply, Intallation & Commissioning of Valves with unions and accessories complete in all respects ready to operate as per drawings and specifications.
FOR MAIN CONNECTION
3.1 | Isolation / Gate Valve
a | Ø 1-1/2" | 2 | Nos. | 11500 | 1500 |  | 0 | 0 | 0
3.2 | Strainer
a | Ø 1-1/2" | 1 | No. | 9900 | 1500 |  | 0 | 0 | 0
3.3 | Balancing Valve
a | Ø 1-1/2" | 1 | No. | 19500 | 1500 |  | 0 | 0 | 0
FOR FAN COIL UNITS
3.4 | Isolation / Gate Valve
a | Ø 1-1/4" | 2 | Nos. | 11500 | 1500 |  | 0 | 0 | 0
b | Ø 1" | 2 | Nos. | 8900 | 1500 |  | 0 | 0 | 0
3.5 | Strainer
a | Ø 1-1/4" | 1 | No. | 9900 | 1500 |  | 0 | 0 | 0
b | Ø 1" | 1 | No. | 7000 | 1500 |  | 0 | 0 | 0
3.6 | Motorized Valve
a | Ø 1-1/4" | 1 | No. | 65000 | 2000 |  | 0 | 0 | 0
b | Ø 1" | 1 | No. | 50000 | 2000 |  | 0 | 0 | 0
3.7 | Balancing Valve
a | Ø 1-1/4" | 1 | No. | 18000 | 1500 |  | 0 | 0 | 0
b | Ø 1" | 1 | No. | 15000 | 1500 |  | 0 | 0 | 0
4 | Supply, Installation & Testing of uPVC (Sch. 40) Drain Pipe with 10 mm Thick Rubber Foam Insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape etc. complete in all respects and as per instructions of Consultant.
a | Ø 1-1/4" | 56 | Rft. | 340 | 90 |  | 0 | 0 | 0
b | Ø 1" | 4 | Rft. | 310 | 90 |  | 0 | 0 | 0
SUB-TOTAL FOR SECTION 01 (Rs.)
SECTION 02: SUPPLY, INSTALLATION & TESTING OF DUCTING & AIR DEVICES
1 | Supply, fabrication, Installation & Testing of Pre-Febricated Pre- Insulated Duct Work for supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connector, access door, transformation, plenums chambers, wooden frame, anchors as per SMACNA Standards along with supports & hangers complete in all respects ready to operate as per drawings, instruction and approval of Consultant.
a | For AC Supply / Return | 590 | Sq.ft. | 600 | 75 | 790.2 | 474120 | 59265 | 533385
3 | Supply, Installation & Commissioning of Aluminum Fabricated, Powder Coated Air Devices for supply, return, exhaust & fresh air. including framing, hangers & supports and other accessories etc. complete in all respects ready to operate as per instruction of Consultant.
3.1 | Diffusers/Grilles/Registers (with Dampers)
For AC - Supply Air
a | Round Diffuser - Ø 6" | 2 | Nos. | 3800 | 1200 | 2 | 7600 | 2400 | 10000
b | Round Diffuser - Ø 10" | 14 | Nos. | 6000 | 1200 | 14 | 84000 | 16800 | 100800
For AC - Return Air
c | RALBG - 84" x 3-½" | 6 | Nos. | 6800 | 1000 | 6 | 40800 | 6000 | 46800
SUB-TOTAL FOR SECTION 02 (Rs.)
SECTION 03: SUPPLY & INSTALLATION OF FIRE EXTINGUISHERS
1 | Fire Extinguishers
a | 06 KG DCP | 2 | Nos. | 19000 | 1000 |  | 0 | 0 | 0
b | 05 KG CO2 | 2 | Nos. | 14000 | 1000 |  | 0 | 0 | 0
SUB-TOTAL FOR SECTION 03 (Rs.)
SECTION 04: MISCELLANEOUS WORKS
1 | Supply & Installation of Brass Tags for Equipment and System. | 1 | Job. | 10000 | 5000 |  | 0 | 0 | 0
2 | Supply, Installation and Commissioning of Fire Stopping Material as per specifications and drawings complete in all respect. | 1 | Job. | 15000 | 5000 |  | 0 | 0 | 0
3 | Making of Shop Drawings and As-Built Drawings on Auto CAD with sectional details, equipment details and their foundation details, Technical submittals and sample boards complete in all respect as per instruction of Consultant. | 1 | Job. | 10000 | 10000 | 1 | 10000 | 10000 | 20000
4 | Supply, Installation and Commissioning of items not listed in BOQ but required for complition of work to ensure satisfactory performance. (Contractor to provide list) | 1 | Job. | 0 |  |  | 0 | 0 | 0
SUB-TOTAL FOR SECTION 04 (Rs.)
TOTAL COST OF WORKS (SECTION 01 TO SECTION 04) (Rs.) | [8 empty] | 710985