## Quotation
PS/TF/015/05/22. | [6 empty] | 2022-05-18
Bill for installation of Fan Coil units (EBCO Supermarket - The Forum Shopping mall)
S. No | Description | Qty | Unit | Material Rate | Labor Rate | Material Amount | Labor Amount
1 | Supply and installation of M.S SCH-40 Pipe 1-1/4" | 485 | Rft | 950 | 185 | 460750 | 89725
2 | Supply and installation of thermopore insulation 1-1/4" | 485 | Rft | 410 | 65 | 198850 | 31525
3 | Supply and installation of Cladding | 485 | Rft | 300 | 85 | 145500 | 41225
4 | Supply and installation of Gate Valve 1-1/4" | 8 | Nos | 6116 | 1000 | 48928 | 8000
5 | Supply & installation of Strainer 1-1/4" | 4 | Nos | 5500 | 1000 | 22000 | 4000
6 | Supply and installation of Balancing Valve 1-1/4" | 4 | Nos | 10500 | 1000 | 42000 | 4000
7 | Supply and installation of Motorized Valve 1-1/4" | 4 | Nos | 25000 | 1000 | 100000 | 4000
8 | Supply and installation of thermostat | 4 | Nos | 19500 | 2000 | 78000 | 8000
9 | Supply and installation of drain Pipe with insulation | 80 | Rft | 160 | 60 | 12800 | 4800
10 | Supply and installation of G.I ducting | 120 | Sqft | 240 | 60 | 28800 | 7200
11 | Supply and installation of Fiber glass insulation. | 120 | Sqft | 120 | 50 | 14400 | 6000
12 | Removal & re-installation of units. | 4 | Nos | 0 | 13000 | 0 | 52000
13 | Supply and installation of electrical wiring. | 1 | Job | 116000 | 24000 | 116000 | 24000 |  | 175000 | 35000 |  | 58333.3333 | 11666.6667
14 | Supply and installation of flexible duct connector. | 1 | Job | 29000 | 7000 | 29000 | 7000 |  | 35000 | 10000 |  | 11666.6667 | 3333.3333
15 | Supply and installation of hangers and supports | 1 | Job | 50000 | 15000 | 50000 | 15000 |  | 75000 | 25000 |  | 25000 | 8333.3333
16 | Core cuttings works | 1 | Job | 0 | 40000 | 0 | 40000
17 | Testing and commissioing of system. | 1 | Job | 0 | 17000 | 0 | 17000 |  |  | 25000 |  |  | 8333.3333
Sub Total Amount Rs. | [5 empty] | 1347028 | 363475
Grand Total Amount Rs | [5 empty] | 1710503 |  | 273750 | 35587.5 | 28470
A/C to Mr. Sajjad Already paid on cash | [5 empty] | 840000 |  | 605700 | 78741 | 62992.8
Remaining balance | [5 empty] | 870503 |  | 564475 | 73381.75 | 58705.4
Note: False Ceiling cutting & repairing work is not included in our scope, client will furnish this work.
Thanking you,
0
For PIONEER ENGINEERING SERVICES.
#REF!
1026301.8
828630
107721.9
| Ceiling fore cutting, reparing work is not insucl in our scopy, Client will | [7 empty] | 936351.9
60616.26
1286411.74
PIONEER SERVICES