## Summary
2023-07-17
TriFit Gym
COM-01, CLIFTON KARACHI.
GRAND SUMMARY OF RUNNING BILL NO 03
SR.NO. | DESCRIPTION |  | AMOUNT PAK Rs.
1 | ACMV WORKS | Rs. | 14437531
2 | FSS WORKS | Rs. | 4141364
3 | HVAC VARIATION | Rs. | 322054.36
| Total Work: Rs. |  | 18900949.36

## HVAC
Bill of Quantities
ACMV Works
TriFit Gym
Com-1 Clifton, Karachi.
Engineer's Estimate
RUNNING BILL NO-03
BILL OF QUANTITIES
Sr. No. |  | DESCRIPTION | UNIT | QTY | Supply |  | Installation |  | Total Amount Rs. | As per site QTY | Supply (% age) |  |  |  | Installation (% age) |  |  |  | Total Amount
[5 empty] | Rate | Amount | Rate | Amount |  |  | Previous | Current | Total | Amount | Previous | Current | Total | Amount | Previous | Current | Total
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Unloading, rigging, lifting, placement, installation, testing and commissioning of (OWNER SUPPLIED) VRF / VRV air conditioning units with multiple indoor evaporative units of different capacities with central controller complete in all respects, ready to operate including supply & installation of supports, brackets, flexible duct connector / connection, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | GF-CU-01 (4 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 0 |  |  |  | 0 |  |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 1.2 | GF-CU-02 (7 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 0 |  |  |  | 0 |  |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
2 |  | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 2.1 | FF-AC-01 | Nos. | 2 | 5250 | 10500 | 5250 | 10500 | 21000 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 2.2 | SF-AC-01 | Nos. | 2 | 5250 | 10500 | 5250 | 10500 | 21000 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 2.3 | SF-AC-02 | No. | 1 | 7350 | 7350 | 6300 | 6300 | 13650 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 2.4 | GF-CSU-02 | Nos. | 2 | 9450 | 18900 | 8400 | 16800 | 35700 | 2 |  |  | 0% | 0 |  | 100% | 100% | 16800 | 0 | 16800 | 16800
| 2.5 | FF-CSU-01 | Nos. | 13 | 8925 | 116025 | 4725 | 61425 | 177450 | 3 |  |  | 0% | 0 |  | 100% | 100% | 14175 | 0 | 14175 | 14175
| 2.6 | FF-CSU-02 | Nos. | 7 | 8925 | 62475 | 6300 | 44100 | 106575 | 20 |  |  | 0% | 0 |  | 100% | 100% | 126000 | 0 | 126000 | 126000
| 2.7 | SF-CSU-01 | Nos. | 5 | 7875 | 39375 | 6300 | 31500 | 70875 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 2.8 | SF-CSU-02 | Nos. | 12 | 8925 | 107100 | 6300 | 75600 | 182700 | 17 |  |  | 0% | 0 |  | 100% | 100% | 107100 | 0 | 107100 | 107100
3 |  | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
(VRF / VRV Units copper pipes sizes & quantities shall be vary according to the equipment brand / selection)
| 3.1 | 1/4" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 3.2 | 3/8" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 3.3 | 1/2" dia | Rft | 160 | 945 | 151200 | 210 | 33600 | 184800 | 211.74 |  | 100% | 100% | 200094.3 |  | 100% | 100% | 44465.4 | 0 | 244559.7 | 244559.7
| 3.4 | 5/8" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 3.5 | 3/4" dia | Rft | 160 | 1375.5 | 220080 | 210 | 33600 | 253680 | 187.97 |  | 100% | 100% | 258552.735 |  | 100% | 100% | 39473.7 | 0 | 298026.435 | 298026.435
| 3.6 | 7/8" dia | Rft | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 3.7 | 1 1/8" dia | Rft | 160 | 2677.5 | 428400 | 231 | 36960 | 465360 | 40 |  | 100% | 100% | 107100 |  | 100% | 100% | 9240 | 0 | 116340 | 116340
| 3.8 | 1 3/8" dia (also for 1-1/4") | Rft | 160 | 3528 | 564480 | 236 | 37760 | 602240 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 3.9 | 1 5/8" dia (also for 1-1/2") | Rft | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
4 |  | Supply & installation of control wiring for VRF Units in G.I. for external / PVC for internal from outdoor unit to indoor units including microprocessor & central controller wiring & fixing / installation of central controller supplied with unit complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Lot | 1 | 525000 | 525000 | 131250 | 131250 | 656250 | 1 |  | 100% | 100% | 525000 |  | 100% | 100% | 131250 | 0 | 656250 | 656250
5 |  | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
|  | Soft Pipes for all Wall Mounted Units | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.1 | FF-AC-01 | Rft | 250 | 945 | 236250 | 189 | 47250 | 283500 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.2 | SF-AC-01 | Rft | 220 | 945 | 207900 | 189 | 41580 | 249480 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.3 | SF-AC-02 | Rft | 100 | 1260 | 126000 | 210 | 21000 | 147000 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
|  | Hard Pipes for all Cassette Type Units | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.4 | GF-CSU-02 | Rft | 200 | 2159.85 | 431970 | 210 | 42000 | 473970 | 200 |  | 100% | 100% | 431970 |  | 80% | 80% | 33600 | 0 | 465570 | 465570
| 5.5 | FF-CSU-01 | Rft | 1500 | 1768.2 | 2652300 | 210 | 315000 | 2967300 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.6 | FF-CSU-02 | Rft | 580 | 2193.45 | 1272201 | 210 | 121800 | 1394001 | 2000 |  | 100% | 100% | 4386900 |  | 80% | 80% | 336000 | 0 | 4722900 | 4722900
| 5.7 | SF-CSU-01 | Rft | 340 | 1768.2 | 601188 | 210 | 71400 | 672588 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.8 | SF-CSU-02 | Rft | 740 | 2257.5 | 1670550 | 210 | 155400 | 1825950 | 2200 |  | 100% | 100% | 4966500 |  | 80% | 80% | 369600 | 0 | 5336100 | 5336100
6 |  | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 1500 | 682.5 | 1023750 | 168 | 252000 | 1275750 | 1078.87 |  | 100% | 100% | 736328.775 |  | 100% | 100% | 181250.16 | 0 | 917578.935 | 917578.935
7 |  | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 7.1 | 1" dia | Rft | 850 | 1039.5 | 883575 | 126 | 107100 | 990675 | 175.35 |  | 100% | 100% | 182276.325 |  | 100% | 100% | 22094.1 | 0 | 204370.425 | 204370.425
| 7.2 | 1.25" dia | Rft | 390 | 633.15 | 246928.5 | 126 | 49140 | 296068.5 | 186.47 |  | 100% | 100% | 118063.4805 |  | 100% | 100% | 23495.22 | 0 | 141558.7005 | 141558.7005
| 7.3 | 1.5" dia | Rft | 85 | 756 | 64260 | 126 | 10710 | 74970 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 7.4 | 2" dia | Rft | 10 | 957.6 | 9576 | 126 | 1260 | 10836 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 7.4 | 3" dia | Rft | 80 | 1470 | 117600 | 137 | 10960 | 128560 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
8 |  | Supply & installation of air curtains including, supports, electrical connection / power wiring from isolation box to unit (10' to 15' radius) etc, complete in all respects ready to operate as per drawings, specification & as per instruction of consultant. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 8.1 | 3 Feet length | Nos. | 4 | 85050 | 340200 | 5775 | 23100 | 363300 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
9 |  | Unloading, rigging, lifting, placement, installation, testing and commissioning of (OWNER SUPPLIED) heat recovery ventilator (HRV) as per mentioned in schedule, including supply & installation of duct mounted electronic temp controller with temp sensor, vibration isolator, starter panel, electrical connection, flexible duct connection / connector, power wiring from isolation box to unit (10' to 15' radius), support & hangers, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 9.1 | GF-HRV-01 | No. | 1 | 52500 | 52500 | 26250 | 26250 | 78750 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 9.2 | GF-HRV-01 | No. | 1 | 52500 | 52500 | 26250 | 26250 | 78750 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 9.3 | GF-HRV-03 | No. | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 9.4 | FF-HRV-01 | No. | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 9.5 | FF-HRV-01 | No. | 1 | 36750 | 36750 | 26250 | 26250 | 63000 | 1 |  |  | 0% | 0 |  | 100% | 100% | 26250 | 0 | 26250 | 26250
| 9.6 | SF-HRV-01 | No. | 1 | 36750 | 36750 | 26250 | 26250 | 63000 |  |  |  | 0% | 0 |  |  | 100% | 0 | 0 | 0 | 0
| 9.7 | SF-HRV-02 | No. | 1 | 36750 | 36750 | 26250 | 26250 | 63000 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 9.5 | SF-HRV-03 | No. | 1 | 52500 | 52500 | 26250 | 26250 | 78750 | 1 |  |  | 0% | 0 |  | 100% | 100% | 26250 | 0 | 26250 | 26250
10 |  | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant. | Sqft | 8500 | 346.5 | 2945250 | 95 | 807500 | 3752750 | 1332.68 |  | 100% | 100% | 461773.62 |  | 100% | 100% | 126604.6 | 0 | 588378.22 | 588378.22
11 |  | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 8500 | 294 | 2499000 | 79 | 671500 | 3170500 | 1010.25 |  | 100% | 100% | 297013.5 |  | 100% | 100% | 79809.75 | 0 | 376823.25 | 376823.25
12 |  | Supply, fabrication and installation of epoxy painted M.S sheet metal welded duct of (18 Gauge) for condensing units exhaust air. complete in all respects including all changes in direction, transformation, plenums chambers, connection pecs of hood round to square, supports & hangers etc. complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.. | Sqft | 900 | 682.5 | 614250 | 158 | 142200 | 756450 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
13 |  | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqin | 11600 | 25.2 | 292320 | 6 | 69600 | 361920 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
14 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 14.1 | Fresh & Exhaust Air Register / Diffuser with Damper | Sqin | 14850 | 25.2 | 374220 | 6 | 89100 | 463320 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 14.2 | Exhaust Air Disc Valves 6" dia | Nos. | 41 | 3360 | 137760 | 840 | 34440 | 172200 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
15 |  | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqin | 3500 | 25.2 | 88200 | 6 | 21000 | 109200 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
16 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Lot | 1 | 288750 | 288750 | 36750 | 36750 | 325500 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
17 |  | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 0 | 0 | 131250 | 131250 | 131250 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
18 |  | Making of Shop drawings on Auto CAD latest version with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 26250 | 26250 | 26250 | 26250 | 52500 | 1 |  | 100% | 100% | 26250 |  | 100% | 100% | 26250 | 0 | 52500 | 52500
|  | Total Cost of Works Rs. |  |  |  | 19307158.5 |  | 3986685 | 23666068.5 | [8 empty] | 1739707.93 |  | 14437530.6655 | 14437530.6655
Discount Rs.
Total Cost of Works Rs.
Note:
1) | Electric power wiring / supply to be provided at outdoor, indoor units & other ACMV equipment with isolation box by electrical contractor.
2) | The refrigerant pipes sized + quantity provided for reference only. The contractor / supplier shall calculate the refrigerant pipes, sized & length as per the drawing provided and shall submitted refrigerant piping layout to consultant for approval.
3) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
4) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## Fire
Bill of Quantities
ACMV Works
TriFit Gym
Com-1 Clifton, Karachi.
Engineer's Estimate
RUNNING BILL NO-03
BILL OF QUANTITIES
Sr. No. |  | DESCRIPTION | UNIT | QTY | Supply |  | Installation |  | Total Amount Rs. | As per site QTY | Supply (%age) |  |  |  | Installation(%age) |  |  |  | Total Amount
[5 empty] | Rate | Amount | Rate | Amount |  |  | Previous | Current | Total | Amount | Previous | Current | Total | Amount | Previous | Current | Total
Discount Rs.
Total Cost of Works Rs.
FIRE FIGHTING SERVICES
Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of consultants.
1 |  | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, nozzle guide, lock shield valve, pressure regulating valve automatic & manual operation 180 deg. swing type, with 2-fire extinguishers as shown on drawing.
| 1.1 | Type FHC | No. | 1 | 393750 | 393750 | 10500 | 4134375000 | 4134768750 | 1 |  | 100% | 100% | 393750 |  | 100% | 100% | 10500 | 0 | 404250 | 404250
2 |  | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, automatic & manual operation 180 deg. swing type, nozzle guide, lock sheild valve, pressure regulating valve with 2-1/2" dia size obliuqe landing valve, 2-fire extinguishers as shown on drawing. | [18 empty] | 0
| 2.1 | Type FHC-LV | Nos. | 5 | 320250 | 1601250 | 7350 | 36750 | 1638000 | 5 |  | 100% | 100% | 1601250 |  | 100% | 100% | 36750 | 0 | 1638000 | 1638000
3 |  | Fire department breeching connection 2 ways as per BSS 5041-3 including cabinet with breakable glass, SS frame & drain plug. | No. | 1 | 162750 | 162750 | 7350 | 7350 | 170100 | 1 |  | 100% | 100% | 162750 |  | 0% | 0% | 0 | 0 | 162750 | 162750
4 |  | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
| 4.1 | Dia 1" (Threaded fitting) | Rft. | 20 | 724.5 | 14490 | 205 | 4100 | 18590 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 4.2 | Dia 1-1/4" (Threaded fitting) | Rft. | 60 | 871.5 | 52290 | 221 | 13260 | 65550 | 66.66 | 50% | 50% | 100% | 58094.19 |  | 100% | 100% | 14731.86 | 29047.095 | 43778.955 | 72826.05
| 4.3 | Dia 2" (Threaded fitting) | Rft. | 70 | 1438.5 | 100695 | 231 | 16170 | 116865 | 40 | 50% | 50% | 100% | 57540 |  | 100% | 100% | 9240 | 28770 | 38010 | 66780
| 4.4 | Dia 2-1/2" (Welded joints fitting) | Rft. | 300 | 1879.5 | 563850 | 273 | 81900 | 645750 | 260.68 | 50% | 50% | 100% | 489948.06 |  | 100% | 100% | 71165.64 | 244974.03 | 316139.67 | 561113.7
| 4.5 | Dia 4" (Welded joints fitting) | Rft. | 280 | 3360 | 940800 | 368 | 103040 | 1043840 | 299.82 | 50% | 50% | 100% | 1007395.2 |  | 100% | 100% | 110333.76 | 503697.6 | 614031.36 | 1117728.96
5 |  | Fire extinguishers with fixing accessories. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.1 | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. | 6 | 26250 | 157500 | 3150 | 18900 | 176400 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 5.2 | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. | 6 | 15750 | 94500 | 1050 | 6300 | 100800 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
6 |  | C.I body Check valve with matching flanges. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 6.1 | Size. 4" | No. | 1 | 50925 | 50925 | 5250 | 5250 | 56175 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
7 |  | C.I body Gate valve with matching flanges. | [10 empty] | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
| 7.1 | Dia. 2-1/2" | Nos. | 2 | 31395 | 62790 | 5250 | 10500 | 73290 | 2 |  | 100% | 100% | 62790 |  | 100% | 100% | 10500 | 0 | 73290 | 73290
8 |  | Making of As-Built & Shop Drawings on AutoCAD 2018 or latest version with sectional details complete in all respects as per instructions of consultant. | Job. | 1 | 15750 | 15750 | 10500 | 10500 | 26250 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
9 |  | Painting, identification and tagging to the installations and equipments. | Job. | 1 | 52500 | 52500 | 36750 | 36750 | 89250 | 1 |  | 50% | 50% | 26250 |  | 50% | 50% | 18375 | 0 | 44625 | 44625
10 |  | Flushing of entire fire pipe work according to (NFPA-13). | Job. | 1 | 0 | 0 | 21000 | 21000 | 21000 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
11 |  | Testing, and commissioning of entire fire fighting installation as per Consultant's approval. | Job. | 1 | 0 | 0 | 26250 | 26250 | 26250 |  |  |  | 0% | 0 |  |  | 0% | 0 | 0 | 0 | 0
|  | Total Cost of Fire Suppression Services Rs. |  |  |  | 4263840 |  | 4134773020 | 4139036860 |  |  |  |  | 1702017.45 |  |  |  | 281596.26 | 806488.725 | 3334874.985 | 4141363.71
Note:
1) | Electric power wiring / supply to be provided at outdoor, indoor units & other ACMV equipment with isolation box by electrical contractor.
2) | The refrigerant pipes sized + quantity provided for reference only. The contractor / supplier shall calculate the refrigerant pipes, sized & length as per the drawing provided and shall submitted refrigerant piping layout to consultant for approval.
3) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
4) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## VARIATION
VARIATION ORDER
TriFit Gym
Com-1 Clifton, Karachi.
2023-04-29
Variation of Copper Pipe & G.I ducting - TRIFIT COM-1 Karachi
S. # | Description | Unit | Qty | Labour Rate | Amount
1 | Dismantling of copper piping from room area & installation of copper piping in corridor area. | Job | 1 | 175000 | 175000
2 | Dismantling of G.I Ducting & installation of G.I Ducting in corridor area. | Job | 1 | 75000 | 75000
0
Total Amount Rs. |  |  |  |  | 250000
G.I DUCTING
BOQ Item # | Description | Unit | Quantity | Rate supply | Rate Labour | Total Amount
10 | Dismentling of Gi duct | sqft | 853.97 |  | 60 | 51238.2
10 | Installation of Gi duct | sqft | 204.08 |  | 102 | 20816.16
10 | Supply and Installation of Gi duct | sqft | 1233 |  |  | 0
| TOTAL AMOUNT |  |  |  |  | 72054.36

## MS-VO.
SUMMARY OF VO HVAC
TRIFIT LIMITED-T1 GYM CLIFTON KARACHI
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | CURRANT TOTAL
2 | Dismantling of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
|  | Sq.ft |  | 853.97 | 853.97
3 | Installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
|  | Sq.ft |  | 204.08 | 204.08
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct (DISMANTLING)
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 11.66 | 31.0156
| Elbow (12*4) L (2.33+.75 /2) |  | 2 | 1 | 0.33 | 1.54 | 4.0964
| Duct (12*4) |  | 2 | 1 | 0.33 | 2.66 | 7.0756
| End Cap (12*4) |  | 2 | 1 | 0.33 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.66 | 11.2068
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.16 | 2.2968
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Duct (12*6) |  | 2 | 1 | 0.5 | 12.25 | 36.75
| End Cap (12*6) |  | 2 | 1 | 0.5 | 0 | 0.5
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 7.08 | 28.1784
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 3.58 | 14.2484
| End Cap (14*10) |  | 2 | 1.16 | 0.83 | 0 | 0.97
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 4.25 | 11.305
| End Cap (12*4) |  | 2 | 1 | 0.33 | 0 | 0.33
| Neck (12*8) |  | 2 | 1 | 0.66 | 0.5 | 1.66
| Duct (12*8) |  | 2 | 1 | 0.66 | 3.33 | 11.0556
| Reducer (12+8)/2 (10+8)/2 |  | 2 | 0.83 | 0.75 | 1 | 3.16
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 13.33 | 39.7234
| Reducer (10+8)/2 (8+8)/2 |  | 2 | 0.75 | 0.66 | 1 | 2.82
| Duct (8*8) |  | 2 | 0.66 | 0.66 | 3.75 | 9.9
| Reducer (8+8)/2 (8+6)/2 |  | 2 | 0.66 | 0.58 | 1 | 2.48
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.08 | 7.1456
| End Cap (8*6) |  | 2 | 0.66 | 0.5 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 6.66 | 13.1868
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 6.58 | 13.0284
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 7.33 | 14.5134
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 13.5 | 26.73
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 8.08 | 18.7456
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.41 | 10.7118
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.33 | 2.6334
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.33 | 2.6334
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 3.16 | 6.2568
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 10.25 | 30.545
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 0.33 | 0.9834
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 4.58 | 13.6484
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 1.66 | 6.0424
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 6.08 | 22.1312
| End Cap (14*8) |  | 2 | 1.16 | 0.66 | 0 | 0.78
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 2.75 | 9.13
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 7.83 | 25.9956
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 2.58 | 8.5656
| Neck (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 12.41 | 45.1724
| Reducer (14+8)/2 (8+6)/2 |  | 2 | 0.91 | 0.58 | 1 | 2.98
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.16 | 7.3312
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 8.83 | 17.4834
| Elbow (8*4) L (1.83+.75 /2) |  | 2 | 0.66 | 0.33 | 1.29 | 2.5542
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.5 | 4.95
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2 | 3.96
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.58 | 5.1084
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 2.5 | 10
| End Cap (18*6) |  | 2 | 1.5 | 0.5 | 0 | 0.75
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 9.41 | 37.4518
| Elbow (14*10) L (2.58+.75 /2) |  | 2 | 1.16 | 0.83 | 1.65 | 6.567
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 8 | 31.84
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 1.33 | 3.9634
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 6.5 | 19.37
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 2.83 | 8.4334
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 7 | 20.86
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 6.33 | 18.8634
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 5.41 | 17.9612
| Elbow (14*6) L (2.58+.75 /2) |  | 2 | 1.16 | 0.5 | 1.66 | 5.5112
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 3.58 | 11.8856
| Elbow (14*6) L (2.58+.75 /2) |  | 2 | 1.16 | 0.5 | 1.66 | 5.5112
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 6.91 | 22.9412
| Reducer (14+6)/2 (14+4)/2 |  | 2 | 0.83 | 0.75 | 1 | 3.16
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 7.66 | 22.8268
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| This Bill Qty. | Sq.ft |  |  |  |  | 853.971
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct (INSTALLATION)
| Neck (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 2.75 | 8.195
| Reducer (10+8)/2 (8+8)/2 |  | 2 | 0.75 | 0.66 | 1.5 | 4.23
| Duct (8*8) |  | 2 | 0.66 | 0.66 | 4.58 | 12.0912
| Reducer (8+8)/2 (8+6)/2 |  | 2 | 0.66 | 0.58 | 1.5 | 3.72
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.5 | 8.12
| End Cap (8*6) |  | 2 | 0.66 | 0.5 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 10.08 | 19.9584
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 4 | 9.28
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1.5 | 3.24
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.5 | 10.89
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.25 | 4.455
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.91 | 1.8018
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 3.66 | 7.2468
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 10.08 | 19.9584
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 10.75 | 21.285
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 2.75 | 9.13
| Elbow (14*6) L (2.91+1.08 /2) |  | 2 | 1.16 | 0.5 | 1.99 | 6.6068
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 1.58 | 5.2456
| Elbow (14*6) L (2.91+1.08 /2) |  | 2 | 1.16 | 0.5 | 1.99 | 6.6068
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 9.33 | 30.9756
| End Cap (14*6) |  | 2 | 1.16 | 0.5 | 0 | 0.58
| This Bill Qty. | Sq.ft |  |  |  |  | 204.0764

## Measurements Sheet
SUMMARY OF HVAC
TRIFIT LIMITED-T1 GYM CLIFTON KARACHI
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | FIRST FLOOR | SECOND FLOOR | CURRANT TOTAL
2 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| GF-CSU-01-E | Nos. |  | 3 |  |  | 3
2.4 | GF-CSU-02 | Nos. |  | 2 |  |  | 2
2.6 | FF-CSU-02 | Nos. |  |  | 20 |  | 20
2.8 | SF-CSU-02 | Nos. |  |  |  | 17 | 17
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
3.2 | 3/8" Dia | Rft. |  | 181.74 |  |  | 181.74
3.3 | 1/2" Dia | Rft. |  | 40 |  |  | 40
3.4 | 5/8" Dia | Rft. |  | 187.97 |  |  | 187.97
3.7 | 1-1/8" Dia | Rft. |  | 40 |  |  | 40
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Hard Pipes for all Cassette Type Units
5.4 | GF-CSU-02 | Rft. |  | 214.55 |  |  | 214.55
5.6 | FF-CSU-02 | Rft. |  |  | 1840.18 |  | 1840.18
5.8 | SF-CSU-02 | Rft. |  |  |  | 2064.44 | 2064.44
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | [5 empty] | ,
|  | Sq.ft |  | 143.64 | 415.72 | 519.51 | 1078.87
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
7.1 | 1" Dia | Rft. |  | 175.35 |  |  | 175.35
7.2 | 1.25" Dia | Rft. |  | 186.47 |  |  | 186.47
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
|  | Sq.ft |  | 729.65 |  | 603.03 | 1332.68
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
|  | Sq.ft |  | 1010.25 |  |  | 1010.25
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-12
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
GROUND FLOOR
2 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
CASSETTE TYPE UNITS
GROUND FLOOR
| GF-CSU-01-E | Nos. | 3 |  |  |  | 3
2.4 | GF-CSU-02 | Nos. | 2 |  |  |  | 2
FIRST FLOOR
2.6 | FF-CSU-02 | Nos. | 20 |  |  |  | 20
SECOND FLOOR
2.8 | SF-CSU-02 | Nos. | 17 |  |  |  | 17
| This Bill Qty. | Nos. |  |  |  |  | 42
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| GROUND FLOOR |  |  | 3/8" | 5/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-12-TON
|  | Rft. | 1 | 1.25 | 0.66
|  |  | 1 | 18.33 | 17.83
|  |  | 1 | 3.66 | 4.16
|  |  | 1 | 8.75 | 9.25
|  |  | 1 | 1.41 | 1.91
|  |  | 1 | 8.83 | 9.66
|  |  | 1 | 5.91 | 6.41
|  |  | 1 | 1.41 | 1.91
|  |  | 1 | 8.83 | 9.66
|  |  | 1 | 13.91 | 14.41
| This Bill Qty. | Rft. |  | 72.29 | 75.86
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| GROUND FLOOR |  |  | 1/2" | 1-1/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-12-TON
Rft.
|  |  | 1 | 20 | 20
| This Bill Qty. | Rft. |  | 20 | 20
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| GROUND FLOOR |  |  | 3/8" | 5/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| Copper Pipe-24-TON | Rft. | 1 | 0.91 | 1.41
|  |  | 1 | 4.75 | 5.66
|  |  | 1 | 1.5 | 1.91
|  |  | 1 | 4.08 | 4.58
|  |  | 1 | 1.5 | 1.91
|  |  | 1 | 2.16 | 1.5
|  |  | 1 | 14 | 13.91
|  |  | 1 | 9.16 | 9.66
|  |  | 1 | 2.08 | 1.25
|  |  | 1 | 9.58 | 9.5
|  |  | 1 | 5.25 | 5.75
|  |  | 1 | 12.83 | 12.5
|  |  | 1 | 2.5 | 1.66
|  |  | 1 | 9 | 8.33
|  |  | 1 | 15.66 | 16
|  |  | 1 | 10.83 | 12.08
|  |  | 1 | 3.66 | 4.5
| This Bill Qty. | Rft. |  | 109.45 | 112.11
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| GROUND FLOOR |  |  | 1/2" | 1-1/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-24-TON
Rft.
|  |  | 1 | 20 | 20
| This Bill Qty. | Rft. |  | 20 | 20
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| GROUND FLOOR |  |  | 3/4" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-4-TON
5.4 | GF-CSU-02 | Rft. | 1 | 1.16 | 1.83
|  |  | 1 | 21.25 | 21.5
|  |  | 1 | 38.08 | 38.5
|  |  | 1 | 0.75 | 1.41
|  |  | 1 | 8.08 | 7.5
|  |  | 1 | 37.58 | 36.91
| This Bill Qty. | Rft. |  | 106.9 | 107.65
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| FIRST FLOOR |  |  | 3/4" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-4-TON
5.6 | FF-CSU-02 | Rft. | 1 | 5.58 | 5.83
|  |  | 1 | 52.58 | 52.66
|  |  | 1 | 5.08 | 4.91
|  |  | 1 | 22.08 | 22.16
|  |  | 1 | 47.16 | 47.58
|  |  | 1 | 7 | 7.33
|  |  | 1 | 20.91 | 20.41
|  |  | 1 | 48 | 48.16
|  |  | 1 | 9.83 | 10
|  |  | 1 | 32.58 | 32.91
|  |  | 1 | 9.25 | 9.41
|  |  | 1 | 9.75 | 10.08
|  |  | 1 | 22.25 | 22.08
|  |  | 1 | 2.08 | 1.75
|  |  | 1 | 49.16 | 49.5
|  |  | 1 | 14.33 | 14.33
|  |  | 1 | 4.66 | 4.75
|  |  | 1 | 48.91 | 48.25
|  |  | 1 | 14 | 14.16
|  |  | 1 | 39.41 | 39.75
|  |  | 1 | 19.66 | 19.91
|  |  | 1 | 37.83 | 38.25
|  |  | 1 | 9.08 | 9.25
|  |  | 1 | 17 | 17.5
|  |  | 1 | 4.41 | 4.58
|  |  | 1 | 48.66 | 48.5
|  |  | 1 | 4.91 | 5.08
|  |  | 1 | 38.91 | 39.08
|  |  | 1 | 6.16 | 6.33
|  |  | 1 | 18.83 | 19.08
|  |  | 1 | 2.66 | 2.83
|  |  | 1 | 52.41 | 52.25
|  |  | 1 | 3.16 | 3.33
|  |  | 1 | 39.33 | 39.66
|  |  | 1 | 2.25 | 2.41
|  |  | 1 | 13.83 | 14.08
|  |  | 1 | 1.91 | 2.08
|  |  | 1 | 52.66 | 52.91
|  |  | 1 | 1.66 | 1.83
|  |  | 1 | 39.58 | 39.83
|  |  | 1 | 19.75 | 19.08
|  |  | 1 | 13.08 | 13.33
|  |  | 1 | 4.5 | 6.16
| This Bill Qty. | Rft. |  | 916.83 | 923.35
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | L | H/D
| SECOND FLOOR |  |  | 3/4" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-4-TON
5.8 | SF-CSU-02 | Rft. | 1 | 9.58 | 10.16
|  |  | 1 | 18.08 | 18.41
|  |  | 1 | 37 | 36.75
|  |  | 1 | 32.41 | 32.58
|  |  | 1 | 9.08 | 9.41
|  |  | 1 | 0.66 | 0.91
|  |  | 1 | 37.16 | 37.16
|  |  | 1 | 32.16 | 32.33
|  |  | 1 | 10.25 | 9.83
|  |  | 1 | 16 | 15.83
|  |  | 1 | 35.75 | 36.41
|  |  | 1 | 31.75 | 31.91
|  |  | 1 | 5.5 | 5.75
|  |  | 1 | 17.91 | 18.33
|  |  | 1 | 12.33 | 12.33
|  |  | 1 | 33 | 33.25
|  |  | 1 | 4.91 | 5.25
|  |  | 1 | 2.83 | 3.08
|  |  | 1 | 12.5 | 12.41
|  |  | 1 | 32.75 | 32.91
|  |  | 1 | 13.91 | 14.16
|  |  | 1 | 53 | 53.33
|  |  | 1 | 13.25 | 13.58
|  |  | 1 | 41.83 | 42.25
|  |  | 1 | 9.33 | 9.58
|  |  | 1 | 12.08 | 12.41
|  |  | 1 | 1.33 | 1.75
|  |  | 1 | 8.41 | 8.58
|  |  | 1 | 50.33 | 50.08
|  |  | 1 | 2.41 | 2.83
|  |  | 1 | 7.66 | 7.83
|  |  | 1 | 45.41 | 45.83
|  |  | 1 | 7.58 | 7.5
|  |  | 1 | 32.58 | 32.5
|  |  | 1 | 46.08 | 46.25
|  |  | 1 | 6.91 | 7.08
|  |  | 1 | 32 | 32.41
|  |  | 1 | 45.58 | 45.83
|  |  | 1 | 2.58 | 2.83
|  |  | 1 | 52.75 | 53.08
|  |  | 1 | 2 | 2.25
|  |  | 1 | 36.08 | 36.33
|  |  | 1 | 3.5 | 3.83
|  |  | 1 | 50.41 | 50.75
|  |  | 1 | 4 | 4.33
|  |  | 1 | 34.66 | 35
|  |  | 1 | 2 | 1.83
|  |  | 1 | 2.58 | 2.75
|  |  | 1 | 15.33 | 15.5
| This Bill Qty. | Rft. |  | 1027.18 | 1037.26
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (6"x4") | Sqft. | 1 | 8.5 | 6 | 4 | 7.0833
|  |  | 1 | 10.08 | 6 | 4 | 8.4
|  |  | 1 | 5.83 | 6 | 4 | 4.8583
|  |  | 1 | 10.41 | 6 | 4 | 8.675
|  |  | 1 | 13.66 | 6 | 4 | 11.3833
|  |  | 1 | 2.33 | 6 | 4 | 1.9417
|  |  | 1 | 10.25 | 6 | 4 | 8.5417
|  |  | 1 | 3.16 | 6 | 4 | 2.6333
|  |  | 1 | 8.5 | 6 | 4 | 7.0833
|  |  | 1 | 7.33 | 6 | 4 | 6.1083
|  |  | 1 | 16.5 | 6 | 4 | 13.75
|  |  | 1 | 12 | 6 | 4 | 10
|  |  | 1 | 3.75 | 6 | 4 | 3.125
|  |  | 1 | 1.33 | 6 | 4 | 1.1083
|  |  | 1 | 1.33 | 6 | 4 | 1.1083
|  |  | 1 | 20.5 | 6 | 4 | 17.0833
|  |  | 1 | 36.91 | 6 | 4 | 30.7583
| This Bill Qty. | Sqft. |  |  |  |  | 143.6417
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
FIRST FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (6"x4") | Sqft. | 1 | 3.83 | 6 | 4 | 3.1917
|  |  | 1 | 5.08 | 6 | 4 | 4.2333
|  |  | 1 | 3.5 | 6 | 4 | 2.9167
|  |  | 1 | 5.66 | 6 | 4 | 4.7167
|  |  | 1 | 8 | 6 | 4 | 6.6667
|  |  | 1 | 8 | 6 | 4 | 6.6667
|  |  | 1 | 18.16 | 6 | 4 | 15.1333
|  |  | 1 | 1.58 | 6 | 4 | 1.3167
|  |  | 1 | 11.66 | 6 | 4 | 9.7167
|  |  | 1 | 3.91 | 6 | 4 | 3.2583
|  |  | 1 | 16.41 | 6 | 4 | 13.675
|  |  | 1 | 11.66 | 6 | 4 | 9.7167
|  |  | 1 | 6.83 | 6 | 4 | 5.6917
|  |  | 1 | 3.91 | 6 | 4 | 3.2583
|  |  | 1 | 4.16 | 6 | 4 | 3.4667
|  |  | 1 | 4.16 | 6 | 4 | 3.4667
|  |  | 1 | 2.66 | 6 | 4 | 2.2167
|  |  | 1 | 2.41 | 6 | 4 | 2.0083
|  |  | 1 | 1.25 | 6 | 4 | 1.0417
|  |  | 1 | 1.16 | 6 | 4 | 0.96667
|  |  | 1 | 1.16 | 6 | 4 | 0.96667
|  |  | 1 | 10.08 | 6 | 4 | 8.4
| This Bill Qty. | Sqft. |  |  |  |  | 112.6917
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
SECOND FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (6"x4") | Sqft. | 1 | 9 | 6 | 4 | 7.5
|  |  | 1 | 9 | 6 | 4 | 7.5
|  |  | 1 | 9 | 6 | 4 | 7.5
|  |  | 1 | 4.83 | 6 | 4 | 4.025
|  |  | 1 | 20.58 | 6 | 4 | 17.15
|  |  | 1 | 4.83 | 6 | 4 | 4.025
|  |  | 1 | 12.66 | 6 | 4 | 10.55
|  |  | 1 | 12.66 | 6 | 4 | 10.55
|  |  | 1 | 9.25 | 6 | 4 | 7.7083
|  |  | 1 | 1.25 | 6 | 4 | 1.0417
|  |  | 1 | 7.75 | 6 | 4 | 6.4583
|  |  | 1 | 2.25 | 6 | 4 | 1.875
|  |  | 1 | 7.75 | 6 | 4 | 6.4583
|  |  | 1 | 7.25 | 6 | 4 | 6.0417
|  |  | 1 | 6.83 | 6 | 4 | 5.6917
|  |  | 1 | 33.16 | 6 | 4 | 27.6333
|  |  | 1 | 1.41 | 6 | 4 | 1.175
|  |  | 1 | 1.41 | 6 | 4 | 1.175
|  |  | 1 | 3.33 | 6 | 4 | 2.775
|  |  | 1 | 3.33 | 6 | 4 | 2.775
|  |  | 1 | 1.5 | 6 | 4 | 1.25
|  |  | 1 | 2.08 | 6 | 4 | 1.7333
| This Bill Qty. | Sqft. |  |  |  |  | 142.5917
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
FIRST FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (10"x4") | Sqft. | 1 | 20.75 | 10 | 4 | 24.2083
|  |  | 1 | 42.5 | 10 | 4 | 49.5833
|  |  | 1 | 46.33 | 10 | 4 | 54.0517
|  |  | 1 | 49.5 | 10 | 4 | 57.75
|  |  | 1 | 50.25 | 10 | 4 | 58.625
|  |  | 1 | 50.41 | 10 | 4 | 58.8117
| This Bill Qty. | Sqft. |  |  |  |  | 303.03
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
SECOND FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (10"x4") | Sqft. | 1 | 38.58 | 10 | 4 | 45.01
|  |  | 1 | 37.83 | 10 | 4 | 44.135
|  |  | 1 | 31.75 | 10 | 4 | 37.0417
|  |  | 1 | 54.33 | 10 | 4 | 63.385
|  |  | 1 | 55 | 10 | 4 | 64.1667
|  |  | 1 | 53.83 | 10 | 4 | 62.8017
|  |  | 1 | 51.75 | 10 | 4 | 60.375
| This Bill Qty. | Sqft. |  |  |  |  | 376.915
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-01
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
7.1 | 1" Dia | Rft. | 1 | 2.83 |  |  | 2.83
|  |  | 1 | 7.33 |  |  | 7.33
|  |  | 1 | 2 |  |  | 2
|  |  | 1 | 11.75 |  |  | 11.75
|  |  | 1 | 2 |  |  | 2
|  |  | 1 | 12 |  |  | 12
|  |  | 1 | 1.83 |  |  | 1.83
|  |  | 1 | 1.83 |  |  | 1.83
|  |  | 1 | 18.58 |  |  | 18.58
|  |  | 1 | 2 |  |  | 2
|  |  | 1 | 5.75 |  |  | 5.75
|  |  | 1 | 15.33 |  |  | 15.33
|  |  | 1 | 5 |  |  | 5
|  |  | 1 | 0.75 |  |  | 0.75
|  |  | 1 | 1.33 |  |  | 1.33
|  |  | 1 | 0.91 |  |  | 0.91
|  |  | 1 | 1.33 |  |  | 1.33
|  |  | 1 | 16.08 |  |  | 16.08
|  |  | 1 | 2 |  |  | 2
|  |  | 1 | 13.5 |  |  | 13.5
|  |  | 1 | 1 |  |  | 1
|  |  | 1 | 13.91 |  |  | 13.91
|  |  | 1 | 12.58 |  |  | 12.58
|  |  | 1 | 4.66 |  |  | 4.66
|  |  | 1 | 1.16 |  |  | 1.16
|  |  | 1 | 2.66 |  |  | 2.66
|  |  | 1 | 15.25 |  |  | 15.25
| This Bill Qty. | Rft. |  |  |  |  | 175.35
7.2 | 1.25" Dia
|  |  | 1 | 2 |  |  | 2
|  |  | 1 | 6.16 |  |  | 6.16
|  |  | 1 | 40.25 |  |  | 40.25
|  |  | 1 | 41.08 |  |  | 41.08
|  |  | 1 | 26.08 |  |  | 26.08
|  |  | 1 | 6.08 |  |  | 6.08
|  |  | 1 | 16.5 |  |  | 16.5
|  |  | 1 | 12.25 |  |  | 12.25
|  |  | 1 | 1.16 |  |  | 1.16
|  |  | 1 | 34.91 |  |  | 34.91
| This Bill Qty. | Rft. |  |  |  |  | 186.47
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-06-02
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 11.08 | 29.4728
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 1.75 | 4.655
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 10.25 | 30.75
| End Cap (12*6) |  | 1 | 1 | 0.5 | 0 | 0.5
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 6.58 | 26.1884
| Reducer (14+10)/2 (12+4)/2 |  | 2 | 1 | 0.66 | 1.16 | 3.8512
| Duct (12*4) |  | 2 | 1 | 0.33 | 10.66 | 28.3556
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.25 | 4.455
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.91 | 1.8018
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 2.66 | 9.6824
| Elbow (14*8) L (2.91+1.08 /2) |  | 2 | 1.16 | 0.66 | 1.99 | 7.2436
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 2.83 | 10.3012
| Reducer (14+8)/2 (14+4)/2 |  | 2 | 0.91 | 0.75 | 1 | 3.32
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 2.16 | 6.4368
| End Cap (14*4) |  | 1 | 1.16 | 0.33 | 0 | 0.39
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 6.5 | 19.37
| End Cap (14*4) |  | 1 | 1.16 | 0.33 | 0 | 0.39
| Neck (10*10) |  | 2 | 0.83 | 0.83 | 0.25 | 0.83
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 5.66 | 18.7912
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 0.33 | 1.0956
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 9.16 | 42.6856
| Reducer (18+10)/2 (16+10)/2 |  | 2 | 1.16 | 1.08 | 1.5 | 6.72
| Duct (16*10) |  | 2 | 1.33 | 0.83 | 5.41 | 23.3712
| End Cap (16*10) |  | 1 | 1.33 | 0.83 | 0 | 1.11
| Neck (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 5.33 | 21.2134
| End Cap (16*8) |  | 1 | 1.33 | 0.66 | 0 | 0.89
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.25 | 2.475
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 2.66 | 10.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 9.5 | 38
| Elbow (18*6) L (1.08+3.41 /2) |  | 2 | 1.5 | 0.5 | 2.24 | 8.96
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 3.91 | 15.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 8 | 15.84
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.25 | 2.475
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 12.08 | 48.0784
| Neck (24*4) |  | 2 | 2 | 0.33 | 0.5 | 2.33
| Duct (24*4) |  | 2 | 2 | 0.33 | 3.5 | 16.31
| End Cap (24*4) |  | 1 | 2 | 0.33 | 0 | 0.66
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 12.25 | 48.755
| End Cap (14*10) |  | 1 | 1.16 | 0.83 | 0 | 0.97
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Offset (18*6) |  | 2 | 1.5 | 0.5 | 2 | 8
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 2 | 8
| Offset (18*6) |  | 2 | 1.5 | 0.5 | 2 | 8
| Elbow (18*6) L (1.66+.5 /2) |  | 2 | 1.5 | 0.5 | 1.08 | 4.32
| Offset (18*6) |  | 2 | 1.5 | 0.5 | 4.83 | 19.32
| Elbow (18*6) L (1.66+.5 /2) |  | 2 | 1.5 | 0.5 | 1.08 | 4.32
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 29.5 | 118
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 2.41 | 9.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| This Bill Qty. | Sq.ft |  |  |  |  | 729.6466
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
SECOND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 20 | 79.6
| End Cap (14*10) |  | 1 | 1.16 | 0.83 | 0 | 0.97
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.33 | 0.8778
| Elbow (12*4) L (2.33+.75 /2) |  | 2 | 1 | 0.33 | 1.54 | 4.0964
| Duct (12*4) |  | 2 | 1 | 0.33 | 3.83 | 10.1878
| Elbow (12*4) L (2.33+.75 /2) |  | 2 | 1 | 0.33 | 1.54 | 4.0964
| Duct (12*4) |  | 2 | 1 | 0.33 | 2.33 | 6.1978
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 5.91 | 13.7112
| End Cap (8*6) |  | 1 | 0.66 | 0.5 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 7.83 | 15.5034
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 4.58 | 9.0684
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (12*10) |  | 2 | 1 | 0.83 | 0.5 | 1.83
| Duct (12*10) |  | 2 | 1 | 0.83 | 8.58 | 31.4028
| Reducer (12+10)/2 (10+10)/2 |  | 2 | 0.91 | 0.83 | 1 | 3.48
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 9 | 29.88
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 34.91 | 115.9012
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 7.58 | 25.1656
| Reducer (10+10)/2 (8+8)/2 |  | 2 | 0.83 | 0.66 | 1 | 2.98
| Duct (8*8) |  | 2 | 0.66 | 0.66 | 8.16 | 21.5424
| Reducer (8+8)/2 (8+4)/2 |  | 2 | 0.66 | 0.5 | 1 | 2.32
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.5 | 10.89
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 4.66 | 10.8112
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 8.91 | 17.6418
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 6.33 | 14.6856
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 6.66 | 13.1868
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 0.83 | 1.9256
| End Cap (8*6) |  | 1 | 0.66 | 0.5 | 0 | 0.33
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 19.33 | 70.3612
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 1 | 3.64
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 3.08 | 11.2112
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 1 | 3.64
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 6.5 | 23.66
| Reducer (14+8)/2 (14+4)/2 |  | 2 | 0.91 | 0.75 | 1 | 3.32
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 9.33 | 27.8034
| End Cap (14*4) |  | 1 | 1.16 | 0.33 | 0 | 0.89
| This Bill Qty. | Sq.ft |  |  |  |  | 630.0324
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-12
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct
| Neck (14*6) |  | 2 | 1.16 | 0.5 | 0.5 | 1.66
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 11.08 | 36.7856
| End Cap (14*6) |  | 1 | 1.16 | 0.5 | 0 | 0.58
| Neck (14*6) |  | 2 | 1.16 | 0.5 | 0.5 | 1.66
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 1.75 | 5.81
| End Cap (14*6) |  | 1 | 1.16 | 0.5 | 0 | 0.58
| Neck (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 10.25 | 37.31
| End Cap (14*8) |  | 1 | 1.16 | 0.66 | 0 | 0.78
| Duct (16*12) |  | 2 | 1.33 | 1 | 6.58 | 30.6628
| Reducer (16+12)/2 (14+6)/2 |  | 2 | 1.16 | 0.83 | 1.16 | 4.6168
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 10.66 | 35.3912
| End Cap (14*6) |  | 1 | 1.16 | 0.5 | 0 | 0.58
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 2.25 | 5.985
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.91 | 2.4206
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Duct (16*10) |  | 2 | 1.33 | 0.83 | 2.66 | 11.4912
| Elbow (16*10) L (2.91+1.08 /2) |  | 2 | 1.33 | 0.83 | 1.99 | 8.5968
| Duct (16*10) |  | 2 | 1.33 | 0.83 | 2.83 | 12.2256
| Reducer (16+10)/2 (16+6)/2 |  | 2 | 1.08 | 0.91 | 1 | 3.98
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 2.16 | 7.9056
| End Cap (16*6) |  | 1 | 1.33 | 0.5 | 0 | 0.66
| Neck (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 6.5 | 23.79
| End Cap (16*6) |  | 1 | 1.33 | 0.5 | 0 | 0.66
| Neck (12*12) |  | 2 | 1 | 1 | 0.25 | 1
| Elbow (12*12) L (2.08+.75 /2) |  | 2 | 1 | 1 | 1.41 | 5.64
| Duct (12*12) |  | 2 | 1 | 1 | 5.66 | 22.64
| Elbow (12*12) L (2.08+.75 /2) |  | 2 | 1 | 1 | 1.41 | 5.64
| Duct (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Duct (20*12) |  | 2 | 1.66 | 1 | 9.16 | 48.7312
| Reducer (20+12)/2 (18+12)/2 |  | 2 | 1.33 | 1.25 | 1.5 | 7.74
| Duct (18*12) |  | 2 | 1.5 | 1 | 5.41 | 27.05
| End Cap (18*12) |  | 1 | 1.5 | 1 | 0 | 1.5
| Neck (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 5.33 | 24.8378
| End Cap (18*10) |  | 1 | 1.5 | 0.83 | 0 | 1.25
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 1.25 | 3.325
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 2.66 | 12.3424
| End Cap (20*8) |  | 1 | 1.66 | 0.66 | 0 | 1.11
| Neck (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 9.5 | 44.08
| Elbow (20*8) L (1.08+3.41 /2) |  | 2 | 1.66 | 0.66 | 2.24 | 10.3936
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 3.91 | 18.1424
| End Cap (20*8) |  | 1 | 1.66 | 0.66 | 0 | 1.11
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 8 | 21.28
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 1.25 | 3.325
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Duct (16*12) |  | 2 | 1.33 | 1 | 12.08 | 56.2928
| Neck (26*6) |  | 2 | 2.16 | 0.5 | 0.5 | 2.66
| Duct (26*6) |  | 2 | 2.16 | 0.5 | 3.5 | 18.62
| End Cap (26*6) |  | 1 | 2.16 | 0.5 | 0 | 1.08
| Duct (16*12) |  | 2 | 1.33 | 1 | 12.25 | 57.085
| End Cap (16*12) |  | 1 | 1.33 | 1 | 0 | 1.33
| Neck (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Offset (20*8) |  | 2 | 1.66 | 0.66 | 2 | 9.28
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 2 | 9.28
| Offset (20*8) |  | 2 | 1.66 | 0.66 | 2 | 9.28
| Elbow (20*8) L (1.66+.5 /2) |  | 2 | 1.66 | 0.66 | 1.08 | 5.0112
| Offset (20*8) |  | 2 | 1.66 | 0.66 | 4.83 | 22.4112
| Elbow (20*8) L (1.66+.5 /2) |  | 2 | 1.66 | 0.66 | 1.08 | 5.0112
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 29.5 | 136.88
| End Cap (20*8) |  | 1 | 1.66 | 0.66 | 0 | 1.11
| Neck (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 2.41 | 11.1824
| End Cap (20*8) |  | 1 | 1.66 | 0.66 | 0 | 1.11
| This Bill Qty. | Sq.ft |  |  |  |  | 868.1724
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-12
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct (Insulation Pocket)
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (12*10) |  | 2 | 1 | 0.83 | 0.5 | 1.83
| Duct (12*12) |  | 2 | 1 | 1 | 0.5 | 2
| Duct (12*12) |  | 2 | 1 | 1 | 0.5 | 2
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*12) |  | 2 | 1.33 | 1 | 0.5 | 2.33
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (20*8) |  | 2 | 1.66 | 0.66 | 0.5 | 2.32
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| This Bill Qty. | Sq.ft |  |  |  |  | 142.08
SUMMARY OF FIRE PIPE FOR
TRIFIT LIMITED-T1 GYM CLIFTON KARACHI
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | FIRST FLOOR | SECOND FLOOR | CURRANT TOTAL
1 | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, nozzle guide, lock shield valve, pressure regulating valve automatic & manual operation 180 deg. swing type, with 2-fire extinguishers as shown on drawing.
1.1 | Type FHC | Nos. |  | 1 |  |  | 1
2 | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, automatic & manual operation 180 deg. swing type, nozzle guide, lock sheild valve, pressure regulating valve with 2-1/2" dia size obliuqe landing valve, 2-fire extinguishers as shown on drawing.
2.1 | Type FHC-LV | Nos. |  | 1 | 2 | 2 | 5
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.2 | Dia 1-1/4" | Rft. |  | 66.66 |  |  | 66.66
4.3 | Dia 2" | Rft. |  | 12 | 14 | 14 | 40
4.4 | Dia 2-1/2" | Rft. |  |  | 142.38 | 118.3 | 260.68
4.5 | Dia 4" | Rft. |  | 299.82 |  |  | 299.82
7 | C.I body Gate valve with matching flanges.
7.1 | Dia. 2-1/2" | Nos. |  |  | 1 | 1 | 2
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Hose Cabinet
1 | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, nozzle guide, lock shield valve, pressure regulating valve automatic & manual operation 180 deg. swing type, with 2-fire extinguishers as shown on drawing.
1.1 | Type FHC
| GROUND FLOOR | Nos. | 1 |  |  |  | 1
| This Bill Qty. | Nos. |  |  |  |  | 1
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Hose Cabinet
2 | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, automatic & manual operation 180 deg. swing type, nozzle guide, lock sheild valve, pressure regulating valve with 2-1/2" dia size obliuqe landing valve, 2-fire extinguishers as shown on drawing.
2.1 | Type FHC-LV
| GROUND FLOOR | Nos. | 1 |  |  |  | 1
| FIRST FLOOR |  | 2 |  |  |  | 2
| SECOND FLOOR |  | 2 |  |  |  | 2
| This Bill Qty. | Nos. |  |  |  |  | 5
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
INSTALLATION
4.2 | Dia 1-1/4" | Rft. | 1 | 53.5 |  |  | 53.5
| This Bill Qty. | Rft. |  |  |  |  | 53.5
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.2 | Dia 1-1/4" | Rft. | 1 | 4.5 |  |  | 4.5
|  |  | 1 | 3.66 |  |  | 3.66
| Vertical Pipe |  | 1 | 5 |  |  | 5
| This Bill Qty. | Rft. |  |  |  |  | 13.16
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.3 | Dia 2" | Rft.
Riser No-01
| GROUND FLOOR |  | 1 | 12 |  |  | 12
| FIRST FLOOR |  | 1 | 14 |  |  | 14
| SECOND FLOOR |  | 1 | 14 |  |  | 14
| This Bill Qty. | Rft. |  |  |  |  | 40
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
FIRST FLOOR
Fire Pipe
4 | Seamless black pipe conforming to ASTM A-53 sch 40 & fittings conforming BS 534 of following diameters as specified.
4.4 | Dia 2-1/2" | Rft. | 1 | 2.16 |  |  | 2.16
|  |  | 1 | 27.41 |  |  | 27.41
|  |  | 1 | 15.66 |  |  | 15.66
|  |  | 1 | 3.91 |  |  | 3.91
|  |  | 1 | 0.5 |  |  | 0.5
|  |  | 1 | 2 |  |  | 2
|  |  | 1 | 7.16 |  |  | 7.16
|  |  | 1 | 20 |  |  | 20
|  |  | 1 | 17.83 |  |  | 17.83
|  |  | 1 | 25.25 |  |  | 25.25
|  |  | 1 | 2.5 |  |  | 2.5
| Vertical Pipe |  | 2 | 9 |  |  | 18
| This Bill Qty. | Rft. |  |  |  |  | 142.38
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
SECOND FLOOR
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.4 | Dia 2-1/2" | Rft. | 1 | 1.66 |  |  | 1.66
|  |  | 1 | 20.25 |  |  | 20.25
|  |  | 1 | 15.66 |  |  | 15.66
|  |  | 1 | 4.08 |  |  | 4.08
|  |  | 1 | 2.75 |  |  | 2.75
|  |  | 1 | 1.16 |  |  | 1.16
|  |  | 1 | 24.08 |  |  | 24.08
|  |  | 1 | 17.75 |  |  | 17.75
|  |  | 1 | 10.41 |  |  | 10.41
|  |  | 1 | 2.5 |  |  | 2.5
| Vertical Pipe |  | 2 | 9 |  |  | 18
| This Bill Qty. | Rft. |  |  |  |  | 118.3
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-05-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.5 | Dia 4" | Rft. | 1 | 33.75 |  |  | 33.75
|  |  | 1 | 157 |  |  | 157
|  |  | 1 | 14 |  |  | 14
|  |  | 1 | 21.91 |  |  | 21.91
|  |  | 1 | 16.66 |  |  | 16.66
|  |  | 1 | 0.5 |  |  | 0.5
| Riser No-01 Vertical Pipe |  | 2 | 14 |  |  | 28
| Riser No-02 Vertical Pipe |  | 2 | 14 |  |  | 28
| This Bill Qty. | Rft. |  |  |  |  | 299.82
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
7 | C.I body Gate valve with matching flanges.
7.1 | Dia. 2-1/2"
| FIRST FLOOR | Nos. | 1 |  |  |  | 1
| SECOND FLOOR | Nos. | 1 |  |  |  | 1
| This Bill Qty. | Nos. |  |  |  |  | 2