## Sheet1
Bill Summary for the project UEP 17th Floor DMC Karachi |  |  |  |  | MOBILIZATION ADVANCE |  | RETENTION AMOUNT
[5 empty] | WHT deducted once at the time of mob adv received |  | WHT deducted will be deducted and SST wil be added when retention amount released
Contract Amount |  |  |  | 55163506 | Contract Amount | 55163506 | DEDUCTION IN IPC 1 | 594201
Mobilizatin adv 20% |  |  |  | 11032701.2 | Mob advance 20% | 11032701.2 | DEDUCTION IN adhoc in IPC 2 | 1103270
[5 empty] | Tax 8% | 882616.096 | DEDUCTION IN IPC 2 | 2586024
| IPC-01 | IPC-02 | IPC-03 |  | CHQ Amount | 10150085.104
RUNNING BILL NO 1 | 11884018 |  |  | 11884018 |  |  | TOTAL RECEIVABLE | 4283495
Less Retention |  | 5% |  | 594200.9 | DEDUCTION
[5 empty] | DEDUCTION IN IPC 1 | 2971005
Balance Payable |  |  |  | 11289817.1 | DEDUCTION IN adhoc in IPC 2 | 5516351
[5 empty] | DEDUCTION IN adhoc in IPC 2 | 2545345
ADD SST 13% |  | 13% |  | 1467676.223
[5 empty] | TOTAL | 11032701
|  |  |  | 12757493.323 | Mob Payable | 0.2
Less Mobilization |  | 25% |  | 2971004.5
9786488.823
LESS SST TAX |  | 20% |  | 293535.2446
LESS WHTAX |  | 8% |  | 782919.1058
CHQ Amount |  |  |  | 8710034.4726

## Grand
Bill Summary for the project UEP 17th Floor DMC Karachi
Contract Amount | 55163506 | Contract Amount | 55163506 | LESS Retention 5% | 2766923
|  | Verified (IPC-1 + IPC-02) | 55338456 | ADD SST 13% | 359699.99
|  | LESS Retention 5% | 2766923 | Gross | 3126622.99
Verified (IPC-1 + IPC-02) | 55338456 | Remaining | 52571533 | LESS SST TAX 20% | 71939.998
|  | ADD SST 13% | 6834299.29 | LESS WHTAX 08% | 250129.8392
LESS Retention 5% | 2766923 | Gross Work Done | 59405832.29 | Remaining | 2804553.1528
|  | Amount Received | 47891047 |  |  |  | Verified BILL | 55338456
Remaining | 52571533 | Remaining | 11514785.29 |  |  |  | Less Mob | 11032701
|  | LESS SST TAX 20% | 1366859.858 |  | 12031295.7616 |  | Retention | 2918905
ADD SST 13% | 6834299.29 | LESS WHTAX 08% | 921182.8232 |  | 35032291 |  | Received | 36858346
|  | Remaining | 9226742.6088 |  | 47063586.7616 |  | Remaining | 4528504
Gross Work Done | 59405832.29
2725077
LESS Remaining Mobilization Adv | 11032701.2
Net | 48373131.09 |  | 7171255.78
62334761.78
Amount Received | 36858346 |  | 4986780.9424 |  | 0
1434251.156
Payable Amount | 11514785.09 |  | 55913729.6816
11884018
LESS SST TAX 20% | 1366859.858
LESS WHTAX 08% | 921182.8072
18170858
Amount Receivable | 9226742.4248 |  |  |  | 545015.4
17625842.6
|  | 11993665.4248 |  |  | 1453668.64
16172173.96
|  |  | 44259033.4248 |  | 16172173.96