## Grand Summary
GSK OFFICE AT DOLMEN SKY TOWER, KARACHI
Divisions | Description of Work | Supply Amount | Installation Amount | Total
1 | HVAC Works | 9534724.9814 | 1170040.2856 | 10704765.267
2 | Fire Works | 1829565.4 | 529555.94 | 2359121.34
3 | Plumbing Works | 2519876 | 169256 | 2689132
| Grand Total (in PKR): | 13884166.3814 | 1868852.2256 | 15753018.607
General Contractor's Markup on MEP Cost (in PKR):
Grand Total Inclusive of Markup (in PKR):
GST on Supply (in PKR):
SST on Installation (in PKR):
Grand Total Inclusive of Tax (in PKR):
Contractor to verify and coordinate DRAWINGS + BOQ, Discrepancies to be noted to architect/consultant and should be call out in tender clarification form.
This is an item rate based contract.
Any item that may be required for a successful closure of project, kindly add it as a separate line item during RFP.
Rates should be inclusive of WHT.

## HVAC
SECTION III/A: BILL OF QUANTITIES FOR HVAC WORKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | BRAND/MAKE | LEAD TIME
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7
AIR CONDITIONING AND VENTILATION SYSTEM
| 23 82 19 | Lifting, Shifting, Installation, Testing & Commissioning of Ceiling Suspended WCP Units complete with flexible duct connectors, hanger Supports (Lindaptor TR-60), Vibration Isolator, control wiring as per drawing, specification and instruction of consultant.
A |  | WCP-IT-01 | 1 | No. | 0 | 0 | 20000 | 20000 | 20000 | OFM
Lifting, Shifting, Installation, testing and Comissioning of Fancoil Units, complete in all respects with necessary fittings, flexible duct connectors, hanger Supports (Lindaptor TR-60), Vibration Isolator, control wiring as per schedule, drawings and specifications.
B |  | FCU-IT-01 | 1 | No. | 0 | 0 | 12000 | 12000 | 12000 | OFM
Lifting, Shifting, Supply, installation, testing and Comissioning of Fancoil Units, complete in all respects with necessary fittings, flexible duct connectors, hanger Supports (Lindaptor TR-60), Vibration Isolator, thermostat with scheduling option, control wiring and as per schedule, drawings and specifications.
C |  | FCU-LL-01 | 1 | No. | 250000 | 250000 | 8000 | 8000 | 258000 | Trane | 30 Days
Sub Total (Page 1)
Fan Coil Units and Water Cooled Packaged Units Controls
D |  | Supply, installation and Comissioning of complete control sets of Fancoil Units and WCPU as per the scheduled flow of cooling water and chilled water by landlord complete in all respects with necessary fittings and timer relays and as per schedule, drawings and specifications. | 1 | No. | 200000 | 200000 | 10000 | 10000 | 210000 | IMS | 60 Days
E |  | Duct Type Temperature Sensor. | 3 | Nos. | 6000 | 18000 | 1500 | 4500 | 22500 | IMS | 60 Days
E |  | Pressure Switch | 1 | No. | 18000 | 18000 | 1500 | 1500 | 19500 | IMS | 60 Days
F |  | Flow Meter | 1 | No. | 20000 | 20000 | 4000 | 2000 | 22000 | IMS | 60 Days
| 23 05 23 | Supply, installation & commissioning of valves complete in all respect as per drawings and specification.
Gate Valves
G |  | 20mm Diameter | 6 | Nos. | 8900 | 53400 | 1000 | 6000 | 59400 | GALA / SCON | 02 Weeks
| 23 05 23 | Double Regulating Valves
H |  | 20mm Diameter | 3 | Nos. | 27000 | 81000 | 1000 | 3000 | 84000 | GALA / SCON | 02 Weeks
Strainers
I |  | 20mm Diameter | 3 | Nos. | 7900 | 23700 | 1000 | 3000 | 26700 | GALA / SCON | 02 Weeks
2 Way Motorized Control Valves
J |  | 20mm Diameter | 2 | Nos. | 57500 | 115000 | 1000 | 2000 | 117000 | IMS | 60 Days
Drain Valve
K |  | 15mm Diameter | 3 | Nos. | 6800 | 20400 | 1000 | 3000 | 23400 | GALA / SCON | 02 Weeks
Sub Total (Page 2)
A |  | Supply, Installation and Commissioning of pressure gauges with Siphon and stop cocks as per specifications. | 6 | Nos. | 9000 | 54000 | 1000 | 6000 | 60000 | WEISS / WESKLER | 30 Days
B |  | Supply, Installation and Commissioning of thermometer gauge with wells as per drawings and specifications. | 6 | Nos. | 9000 | 54000 | 1000 | 6000 | 60000 | WEISS / WESKLER | 30 Days
C |  | Supply, Installation & Commissioning of Automatic air vents as per drawings and specifications. | 3 | Nos. | 4000 | 12000 | 1000 | 3000 | 15000 | SCON | 20 Days
D |  | Supply and Installation of flexible pipe connectors as per unit requirement, drawings and specifications. | 6 | Nos. | 8500 | 51000 | 1000 | 6000 | 57000 | GALA / SCON | 30 Days
| 23 31 00 | Supply, Installation and Commissioning of G.I Sheet metal air ducts as per ASHRAE Standards plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings as per drawings and specification.
|  | Ducting (Refer Standard Details for Duct Sizes as per SMACNA specified gauges) | [7 empty] | √ | √
E |  | 22 Gauge | 403.7451 | Sq.m | 3500 | 1413107.9859 | 600 | 242247.0833 | 1655355.0692 | ISL | 25 Days
F |  | 24 Gauge | 185.0967 | Sq.m | 3000 | 555290.1894 | 600 | 111058.0379 | 666348.2273 | ISL | 25 Days
G |  | 26 Gauge | 10.3122 | Sq.m | 2500 | 25780.379 | 600 | 6187.291 | 31967.67 | ISL | 25 Days
H | 23 07 00 | Supply and Installation of adhesive 20mm thick 25kg/m3 density rubber foam (XLPE) insulation with aluminum foil over supply & return duct and plenums, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | 659.2937 | Sq.m | 4500 | 2966821.5613 | 500 | 329646.8401 | 3296468.4015 | AEROFOAM | 30 Days
| 23 33 46 | Supply, installation and Commissioning of flexible ducts complete in all respects as per schedule, drawings and specifications.
I |  | 150mm Diameter | 17 | Nos. | 400 | 6800 | 100 | 1700 | 8500 | AFS / FLEXIVA | 15 Days
J |  | 200mm Diameter | 18 | Nos. | 450 | 8100 | 100 | 1800 | 9900 | AFS / FLEXIVA | 15 Days
Sub Total (Page 3)
| 23 37 13 | Supply, Installation and Commissioning of Air Devices and Accessories as per drawings, schedules and specifications.
Supply Air Grille with Damper
A |  | 700x400 | 3 | Nos. | 9000 | 27000 | 1000 | 3000 | 30000 | Mehran / Raees | 90 Days
B |  | 550x350 | 10 | Nos. | 7000 | 70000 | 1000 | 10000 | 80000
C |  | 650x200 | 1 | No. | 4500 | 4500 | 1000 | 1000 | 5500
D |  | 500x300 | 2 | Nos. | 5200 | 10400 | 1000 | 2000 | 12400
E |  | 300x150 | 1 | No. | 2500 | 2500 | 1000 | 1000 | 3500
Return Air Grille with Damper
F |  | 650x200 | 1 | No. | 4500 | 4500 | 1000 | 1000 | 5500 | Mehran / Raees | 90 Days
G |  | 3800x800 | 1 | No. | 90000 | 90000 | 8000 | 8000 | 98000
H |  | 4800x600 | 2 | Nos. | 90000 | 180000 | 8000 | 16000 | 196000
I |  | 600x600 | 1 | No. | 11000 | 11000 | 1000 | 1000 | 12000
Supply Air Diffuser with Damper
J |  | 375x375 | 2 | Nos. | 5000 | 10000 | 1000 | 2000 | 12000 | Mehran / Raees | 90 Days
K |  | 450x450 | 4 | Nos. | 5000 | 20000 | 1000 | 4000 | 24000
L |  | 225x225 | 1 | No. | 2500 | 2500 | 1000 | 1000 | 3500
M |  | 550x550 | 1 | No. | 10000 | 10000 | 1000 | 1000 | 11000
Supply Air Round Diffuser with Damper
N |  | 300mm Dia | 1 | No. | 6000 | 6000 | 1000 | 1000 | 7000
O |  | 350mm Dia | 2 | Nos. | 7000 | 14000 | 1000 | 2000 | 16000 | Mehran / Raees | 90 Days
Sub Total (Page 4)
Return Air Diffuser with Damper
A |  | 375x375 | 2 | Nos. | 5000 | 10000 | 500 | 1000 | 11000 | Mehran / Raees | 90 Days
Exhaust Air Diffuser with Damper
B |  | 150x150 | 8 | Nos. | 2500 | 20000 | 500 | 4000 | 24000 | Mehran / Raees | 90 Days
Exhaust Disc Valves with Damper
C |  | 100 mm Dia | 1 | No. | 2000 | 2000 | 500 | 500 | 2500 | Mehran / Raees | 90 Days
Supply Air Linear Slot Diffuser S.A.L.S.D Hit and miss damper
D |  | 2400-02-25 | 1 | No. | 10000 | 10000 | 500 | 500 | 10500 | Mehran / Raees | 90 Days
E |  | 2/25/1650 | 1 | No. | 7000 | 7000 | 500 | 500 | 7500
F |  | 2200-02-25 | 2 | Nos. | 9000 | 18000 | 500 | 1000 | 19000
G |  | 2/25/1250 | 1 | No. | 5000 | 5000 | 500 | 500 | 5500
H |  | 2/25/1050 | 1 | No. | 4000 | 4000 | 500 | 500 | 4500
I |  | 584445 | 1 | No. | 14000 | 14000 | 500 | 500 | 14500
J |  | 584473 | 1 | No. | 15000 | 15000 | 500 | 500 | 15500
K |  | 2/25/1100 | 1 | No. | 4500 | 4500 | 500 | 500 | 5000
Sub Total (Page 5)
Return Air Linear Slot Diffuser R.A.L.S.D
A |  | 2400-02-25 | 1 | No. | 10000 | 10000 | 500 | 500 | 10500 | Mehran / Raees | 90 Days
B |  | 2/25/1650 | 1 | No. | 6500 | 6500 | 500 | 500 | 7000
C |  | 2200-02-25 | 1 | No. | 9000 | 9000 | 500 | 500 | 9500
D |  | 2/25/1250 | 1 | No. | 5000 | 5000 | 500 | 500 | 5500
E |  | 2/25/1050 | 1 | No. | 4000 | 4000 | 500 | 500 | 4500
F |  | 584445 | 1 | No. | 14000 | 14000 | 500 | 500 | 14500
G |  | 584473 | 1 | No. | 15000 | 15000 | 500 | 500 | 15500
H |  | 2/25/1400 | 1 | No. | 5000 | 5000 | 500 | 500 | 5500
I |  | 2/25/1100 | 1 | #N/A | 4000 | 4000 | 500 | 500 | 4500
Volume Control Damper (VCD)
J |  | 150x100 | 7 | Nos. | 1800 | 12600 | 500 | 3500 | 16100 | Mehran / Raees | 90 Days
K |  | 550X350 | 10 | Nos. | 5000 | 50000 | 500 | 5000 | 55000
L |  | 700X400 | 3 | Nos. | 8000 | 24000 | 500 | 1500 | 25500
M |  | 500x300 | 2 | Nos. | 4000 | 8000 | 500 | 1000 | 9000
Fire Damper (FD)
N |  | 750x250 | 2 | Nos. | 4500 | 9000 | 500 | 1000 | 10000 | Mehran / Raees | 90 Days
O |  | 1150x250 | 2 | No. | 7000 | 14000 | 500 | 1000 | 15000
Non Return Damper (NRD)
P |  | 1150x250 | 2 | Nos. | 8000 | 16000 | 500 | 1000 | 17000 | Mehran / Raees | 90 Days
Q |  | 150x100 | 1 | No. | 2000 | 2000 | 500 | 500 | 2500
Sub Total (Page 6)
| 23 33 05 | Supply, installation, Testing/Commissioning, Engineering and Programming of VAVs with thermostats, control wiring complete in all respect as per drawing and specification and schedule.
VAVs
A |  | VAV-15F-01 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000 | IMS | 70 Days
B |  | VAV-15F-02 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
C |  | VAV-15F-03A | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
D |  | VAV-15F-03B | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
E |  | VAV-15F-04 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
F |  | VAV-15F-06 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
G |  | VAV-15F-08A | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
H |  | VAV-15F-08B | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
I |  | VAV-15F-08C | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
J |  | VAV-15F-09 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
K |  | VAV-15F-10 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
L |  | VAV-15F-11 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
M |  | VAV-15F-12 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
N |  | VAV-15F-13 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
O |  | VAV-15F-15 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
P |  | VAV-15F-16 | 1 | No. | 150000 | 150000 | 5000 | 5000 | 155000
Sub Total (Page 7)
Supply, Installation and Commissioning of U-PVC piping with insulation for condensate drain piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications.
A |  | 20mm Diameter | 11.1382 | Rm | 700 | 7796.7148 | 100 | 1113.8164 | 8910.5312 | DADEX | 2 Weeks
B |  | 25mm Diameter | 15.9874 | Rm | 800 | 12789.932 | 100 | 1598.7415 | 14388.6735
Supply, Installation and Commissioning of MS Schedule 40 piping for Condenser Water piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications.
C |  | 20mm Diameter | 39.4931 | Rm | 1700 | 67138.219 | 220 | 8688.4754 | 75826.6944 | PROTEK | 2 Weeks
Supply, Installation & Commissioning of ASTM Schedule 40 chilled water seamless piping (Supply/Return) complete with fittings, flanges unions, gaskets, specialties, flexible connections, etc, including all cutting, fixing fitting, laying, cleaning and making good complete in all respects as per drawings and specifications.
D |  | 20mm Diameter | 48 | Rm | 1600 | 76800 | 220 | 10560 | 87360 | PROTEK | 2 Weeks
E |  | 25mm Diameter | 25 | Rm | 1600 | 40000 | 280 | 7000 | 47000
| 23 07 19 | Supply, Installation & Commissioning of Closed Cell NBR Insulation for chilled water piping with complete in all respect as mentioned in the drawings & specifications.
40mm thickness
F |  | 20mm Diameter | 48 | Rm | 600 | 28800 | 280 | 13440 | 42240 | FORTE | 40 Days
G |  | 25mm Diameter | 25 | Rm | 800 | 20000 | 280 | 7000 | 27000
Sound Trap with duct Z-piece and sound lining for return lot air intake.
H |  | 350x150 | 2 | Nos. | 5000 | 10000 | 1000 | 2000 | 12000 | ISL | 40 Days
I |  | 450x150 | 1 | No. | 5000 | 5000 | 1000 | 1000 | 6000
J |  | 300x150 | 1 | No. | 5000 | 5000 | 1000 | 1000 | 6000
K |  | 300x100 | 3 | Nos. | 5000 | 15000 | 1000 | 3000 | 18000
L |  | 550x350 | 2 | Nos. | 5000 | 10000 | 1000 | 2000 | 12000
Sub Total (Page 8)
MISCELLANEOUS
A | 01 46 00 | Supply, Installation & Commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 10000 | 10000 | 10000 | 10000 | 20000 | Imported | 30 Days
B | 23 05 48 | Supply, Installation & Commissioning of hangers and supports for pipes and equipment (Lindaptor TR-60) including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 80000 | 80000 | 15000 | 15000 | 95000 | Mungo / INDEX | 7 to 10 days
C | 09 90 00 | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 10000 | 10000 | 15000 | 15000 | 25000 | ICI / BERGER | 7 to 10 days
D | 23 05 93 23 08 00 | Testing, adjusting, Water Balancing & Commissioning of HVAC system omplete in all respect. | 1 | Job |  | 0 | 35000 | 35000 | 35000
E | 23 05 93 23 08 00 | Testing, adjusting, Air Balancing & Commissioning of HVAC system omplete in all respect. | 1 | Job |  | 0 | 35000 | 35000 | 35000
F | 07 84 00 | Supply, Installation and commision of fire stopping solutions (including PVC sleeves at wal crossings) as per specifications and drawings complete in all respect. | 1 | Job | 10000 | 10000 | 10000 | 10000 | 20000 | SIKLA | 7 to 10 days
Drawings & Documentation
G | 01 00 00 23 05 01 | Submittals, samples, shop drawings, inspections, operation and maintenance manuals complete in all respect as required | 1 | Job |  | 0 | 40000 | 40000 | 40000
Sundries
H | 01 00 00 23 05 01 | Supply, installing and Commissioning of items not listed in BOQ but required. | 1 | Job |  | 0 |  | 0 | 0
Sub Total (Page 9)
|  | GRAND TOTAL FOR HVAC WORKS |  |  |  | 9534724.9814 |  | 1170040.2856 | 10704765.267

## FIRE
SECTION III/C: BILL OF QUANTITIES FOR FIRE FIGHTING WORKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | BRAND/MAKE | LEAD TIME
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7
Fire Fighting
| 21 11 00 | Supply, install and commission of Mild Steel Schedule 40 pipe including all special fittings, saddles and Hangers including the cost of breaking through wall and roof complete in all respects shown on drawings & specifications.
A |  | 25mm Diameter | 191.728 | Rm. | 1600 | 306764.8 | 770 | 147630.56 | 454395.36 | PROTEK / LONTRIN / IIL | 14 to 29 days
B |  | 32mm Diameter | 44.687 | Rm. | 1900 | 84905.3 | 820 | 36643.34 | 121548.64
C |  | 40mm Diameter | 41.686 | Rm. | 2100 | 87540.6 | 840 | 35016.24 | 122556.84
D |  | 50mm Diameter | 21.648 | Rm. | 2800 | 60614.4 | 880 | 19050.24 | 79664.64
E |  | 65mm Diameter | 8.883 | Rm. | 4500 | 39973.5 | 930 | 8261.19 | 48234.69
F |  | 75mm Diameter | 36.07 | Rm. | 5300 | 191171 | 960 | 34627.2 | 225798.2
G |  | 80mm Diameter | 4.461 | Rm. | 7800 | 34795.8 | 970 | 4327.17 | 39122.97
| 21 11 00 | Supply, install and commissioning of Sprinklers including all accessories complete in all respects as per drawings & specifications.
H |  | Concealed Pendent Sprinkler with Paint Finish and Cover Plate (Quick Response) | 41 | Nos. | 6000 | 246000 | 1000 | 41000 | 287000 | VIKINH / LIFFCO / RELIABLE | 60 to 70 Days
I |  | Upright Sprinkler Head Quick Response | 69 | Nos. | 2200 | 151800 | 1000 | 69000 | 220800
| 21 20 00 | Supply, install and commission Fire Extinguisher as per drawing & specification.
J |  | CO2 Extinguisher Capacity 5 kg | 2 | Nos. | 22000 | 44000 | 1500 | 3000 | 47000 | SAFEECO / NAFCOO | 60 Days
K |  | Foam Type Extinguisher Capacity 06 Litres | 2 | Nos. | 16000 | 32000 | 1500 | 3000 | 35000
Supply, install and commissioning of Gate Valve complete in all respects as shown on drawings & specifications.
L |  | 25mm Diameter | 1 | Nos. | 62000 | 62000 | 2000 | 2000 | 64000 | Shield / Reliable | 20 Days
M |  | Corrugated Stainless Steel Flexible Connector 1inch x 3ft (ULFM) | 41 | Nos. | 8000 | 328000 | 1000 | 41000 | 369000 | Shield / Reliable | 45 Days
Sub Total (Page 1)
Miscellaneous
A | 01 46 00 | Supply, Installation & Commissioning of brass tags of 2" dia tags for valves and fixed with chains complete as per drawings & specifications. | 1 | Job | 10000 | 10000 | 5000 | 5000 | 15000 | Imported | 30 Days
B | 21 11 00 | Supply, Installation & Commissioning of seismic hangers and supports for pipes and Equipments including roller type (if required) as per drawings & specifications. | 1 | Job | 125000 | 125000 | 20000 | 20000 | 145000 | INDEX | 30 Days
C | 07 84 00 | Supply, installation and commision fire stopping aid as per specifications and drawings complete in all respect. | 1 | Job | 10000 | 10000 | 5000 | 5000 | 15000 | SIKLA | 7 to 10 days
D | 22 11 00 | Painting of equipment / Hangers, Supports (Lindaptor TR-60), Pipe etc as per specifications. | 1 | Job | 15000 | 15000 | 15000 | 15000 | 30000 | ICI / BERGER | 2 Weeks
E | 21 05 05 | Testing, Flushing & commissioning as per NFPA standards of Fire Fighting System. | 1 | Job |  | 0 | 20000 | 20000 | 20000
Drawings & Documentation
F | 21 05 01 | Submittals, samples, shop drawings, inspections, operation and maintenance manuals complete in all respect as required | 1 | Job |  | 0 | 20000 | 20000 | 20000
Sundries
G |  | Supply, installing and commissioning of items not listed in BOQ but required.(Contractors to provide list) | 1 | Job |  | 0 |  | 0 | 0
Sub Total (Page 2)
|  | GRAND TOTAL FOR FIRE FIGHTING WORKS |  |  |  | 1829565.4 |  | 529555.94 | 2359121.34

## PLUMBING
SECTION III/B: BILL OF QUANTITIES FOR PLUMBING WORKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | BRAND/MAKE | LEAD TIME
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7
| 22 10 00 | Supply, install, testing and commission of PP-R type 3 piping for Cold Water (fittings PN 20) and Hot Water Supply (fittings PN 25) system complete in all respects with all fittings & accessories as per drawings and specifications.
A |  | Ø32mm | 6 | Rm | 1200 | 7200 | 200 | 1200 | 8400 | DADEX | 20 Days
B |  | Ø20mm | 43.52 | Rm | 800 | 34816 | 200 | 8704 | 43520
C |  | Ø15mm | 15 | Rm | 680 | 10200 | 200 | 3000 | 13200
| 22 10 00 | Open cell rubber foam insulation 3/8" thick & pvc tape wrapping for hot water pipes.
D |  | Ø20mm | 43.52 | Rm | 500 | 21760 | 100 | 4352 | 26112 | Super loan | 20 Days
E |  | Ø15mm | 15 | Rm | 400 | 6000 | 100 | 1500 | 7500
| 22 10 00 | Supply, installation, Testing and commissioning of Valves with accessories as per drawings and specifications
|  | Ball Valves | [9 empty] | #DIV/0!
D |  | Ø20mm | 2 | Nos. | 7000 | 14000 | 1000 | 2000 | 16000 | DADEX | 20 Days
E |  | Ø32mm | 1 | No. | 8000 | 8000 | 1000 | 1000 | 9000
Angle Valve
F |  | Ø15mm | 18 | Nos. | 1800 | 32400 | 500 | 9000 | 41400 | GROHE | 15 Days
Electric Water Heater
G |  | EWH-01 (80 Litres Capacity) 220V/1Ph/50Hz | 1 | No. | 90000 | 90000 | 1000 | 1000 | 91000 | ARISTON- ITLAY | 20 Days
Supply, install and commission Drip Tray running underneath existing drain piping on slab complete in all respects as per drawings & specifications.
H |  | 300mm width | 50 | Rm | 600 | 30000 | 100 | 5000 | 35000 | ISL | 14 Days
Sub Total Page 1
| 22 05 23 | Supply, install and commission uPVC type Drains complete in all respects as per drawings & specifications.
A |  | Floor Drains | 9 | No. | 5500 | 49500 | 500 | 4500 | 54000 | DADEX | 10 Days
| 22 10 00 | Supply, install, testing and commission of plumbing fixtures and fittings complete in all respects as shown on drawings & specifications.
B |  | Supply, install, testing and commission of European type Water Closet with "P" or "S" trap, seat and cover best approved quality including imported flush Tank C.P. stop cock, C.P., Muslim shower, grab rail (for female/handicapped toilet) with all accessories & fittings, complete all connection and relative material making requisite hole in walls, floors and plinth for pipe connections and making good with approved materials complete in all respects in as shown on drawings & specifications. | 6 | Nos. | 135000 | 810000 | 4000 | 24000 | 834000 | GROHE | 45 Days
C |  | Supply, install, testing and commission of vanity-type Wash Basin including imported one hole C.P. faucet with electronic sensor, angle vavle, C.P. stop cocks for hot and cold water, C.P. bottle trap, C.P. strainer C.P. copper pipe connections, C.P. brass waste chain plug complete with concealed safety brackets, waste water jointing assembly, making requisite number of holes in walls, floor and plinth for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. | 5 | Nos. | 110000 | 550000 | 4000 | 20000 | 570000 | GROHE | 45 Days
D |  | Supply, install, testing and commission of Toilet Hand Spray with flexible chain & telephone type shower Including tee stop cock etc. complete in all respect. | 6 | Nos. | 8000 | 48000 | 1000 | 6000 | 54000 | GROHE | 45 Days
E |  | Supply, install, testing and commission of Wash basin hot and cold water mixer, etc. | 5 | Nos. | 30000 | 150000 | 1000 | 5000 | 155000 | GROHE | 45 Days
F |  | Supply, Installation of Wall Mounted Soap Dispensers for Vanity as per drawings & specifications. | 4 | Nos. | 22000 | 88000 | 3000 | 12000 | 100000 | GROHE | 45 Days
G |  | Supply, Installation of 3-Point Hand Dryers with sensor as per drawings & specifications. | 3 | Nos. | 45000 | 135000 | 2000 | 6000 | 141000 | SIEMENS | 45 Days
Pantry
H |  | Supply, Installation of Kitchen Sinks (SS) with angle valves (SS), sink mixer (SS) and all accessories and valves as per drawings & specifications. | 1 | No. | 45000 | 45000 | 2000 | 2000 | 47000 | ZILVER | 45 Days
Sub Total Page 2
A |  | Supply, testing and commission of Toilet Paper Holder (SS) as per drawings & specifications. | 6 | Nos. | 13000 | 78000 | 500 | 3000 | 81000 | GROHE | 45 Days
B |  | Supply, testing and commission of Tissue Paper Dispenser as per drawings & specifications. | 3 | Nos. | 4000 | 12000 | 500 | 1500 | 13500 | GROHE | 45 Days
B |  | Supply, Installation of Towel Ring as per drawings & specifications. | 3 | Nos. | 4000 | 12000 | 500 | 1500 | 13500 | GROHE | 45 Days
C |  | Supply, Installation of Robe Hook(SS) as per drawings & specifications. | 6 | Nos. | 3000 | 18000 | 500 | 3000 | 21000 | GROHE | 45 Days
H |  | Supply, install, testing and commission of ablution taps wih hold and cold mixer with all accessories as per drawings & specifications. | 3 | Nos. | 85000 | 255000 | 3000 | 9000 | 264000 | GROHE | 45 Days
I | 22 05 29 | Supply, Installation & commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 15000 | 15000 | 10000 | 10000 | 25000 | INDEX | 30 Days
| 01 00 00 | Drawings
J |  | Submittals, samples, shop drawings, inspections, operation and maintenance manuals complete in all respect as required | 1 | Job |  | 0 | 25000 | 25000 | 25000
| 01 00 00 | Testing & Commissioning
L |  | Water Supply System | 1 | Job |  | 0 |  | 0 | 0
Sub Total Page 3
|  | GRAND TOTAL FOR PLUMBING WORKS |  |  |  | 2519876 |  | 169256 | 2689132