## Sheet1
Bill Summary for the project UEP 17th Floor DMC Karachi |  |  |  |  | MOBILIZATION ADVANCE |  | RETENTION AMOUNT
[5 empty] | WHT deducted once at the time of mob adv received |  | WHT deducted will be deducted and SST wil be added when retention amount released
Contract Amount |  |  |  | 55163506 | Contract Amount | 55163506 | DEDUCTION IN IPC 1 | 594201
Mobilizatin adv 20% |  |  |  | 11032701.2 | Mob advance 20% | 11032701.2 | DEDUCTION IN adhoc in IPC 2 | 1103270
[5 empty] | Tax 8% | 882616.096 | DEDUCTION IN IPC 2 | 2586024
| IPC-01 | IPC-02 | IPC-03 |  | CHQ Amount | 10150085.104
RUNNING BILL NO 1 | 11884018 |  |  | 11884018 |  |  | TOTAL RECEIVABLE | 4283495
Less Retention |  | 5% |  | 594200.9 | DEDUCTION
[5 empty] | DEDUCTION IN IPC 1 | 2971005
Balance Payable |  |  |  | 11289817.1 | DEDUCTION IN adhoc in IPC 2 | 5516351
ADD SST 13% |  | 13% |  | 1467676.223
[5 empty] | TOTAL | 8487356
|  |  |  | 12757493.323 | Mob Payable | 2545345.2
Less Mobilization |  | 25% |  | 2971004.5
9786488.823
LESS SST TAX |  | 20% |  | 293535.2446
LESS WHTAX |  | 8% |  | 782919.1058
CHQ Amount |  |  |  | 8710034.4726

## Grand
Bill Summary for the project UEP 17th Floor DMC Karachi
Contract Amount | 55163506 | Contract Amount | 55163506 | LESS Retention 5% | 2586024.4
|  | Verified (IPC-1 + IPC-02) | 51720488 | ADD SST 13% | 336183.172
|  | LESS Retention 5% | 2586024.4 | Gross | 2922207.572
Verified (IPC-1 + IPC-02) | 51720488 | Remaining | 49134463.6 | LESS SST TAX 20% | 67236.6344
|  | ADD SST 13% | 6387480.268 | LESS WHTAX 08% | 233776.6058
LESS Retention 5% | 2586024.4 | Gross Work Done | 55521943.868 | Remaining | 2621194.3318
|  | Amount Received | 47891047
Remaining | 49134463.6 | Remaining | 7630896.868
|  | LESS SST TAX 20% | 1277496.0536 |  | 8364123.3968
ADD SST 13% | 6387480.268 | LESS WHTAX 08% | 610471.7494 |  | 35032291
|  | Remaining | 5742929.065 |  | 43396414.3968
Gross Work Done | 55521943.868
2725077
LESS Remaining Mobilization Adv | 2545345.2
Net | 52976598.668 |  | 7171255.78
62334761.78
Amount Received | 27957346 |  | 4986780.9424 |  | 0
1434251.156
| 25019252.668 |  | 55913729.6816
LESS SST TAX 20% | 1277496.0536
LESS WHTAX 08% | 2001540.2134
18170858
Amount Receivable | 21740216.401 |  |  |  | 545015.4
17625842.6
1453668.64
16172173.96
|  |  | 56772507.401 |  | 16172173.96