## Summary
Daraz Nastp-Falcon plaza karachi ELECTRICAL, HVAC AND ALLIED SYSTEMS ENGINEERING ESTIMATE
2023-10-24
SUMMARY OF BILL OF QUANTITIES
S.No | Description | Amount
1 | AIR CONDITIONING WORK | 1441800
2 | HVAC | 4710750
| Grand Total Amount | 6152550
| Discount 7% | 430678.5
| Net Amount | 5721871.5
| Add 5.5% | 314702.9325
| Total Amount | 6036574.4325
| Variation Amount for 1st Floor | 7596000
| Variation Amount for Ground Floor | 4220000
| Total | 11816000
| Add 5.5% | 649880
| Total | 12465880
| Grand Total | 18502454.4325
| Received | 10854400
| Payable Amount | 7648054.4325

## Air Conditionioning work
BILL OF QUANTITES
Air Conditioning Works Vol-3
S. No. | Description | Qty | Unit | Supply | Installation, Testing and Commissioning | Amount
1 | SPLIT AC UNITS (FOR IT ROOMS)
AC Units Make: Haier / Gree / Diakin / Hitachi / Approved Eqv. Cables make: Pakistan / Newage / Fast / Coppergat / Golden Star cables. Conduit make: Plasco / Beta / Dadex Pipes
1.01 | Supply at site, installation, testing & comissioning of DC Inverter Heat & Cool type Air Conditioning units having net operational capacity at 45 degree celcius ambient temperature, including the cost of mounting arrangement, with angle iron bracket, rawal bolts, fitting hangers, refrigerant pipe connections, wiring connections, complete in all resepects.
i) | Wall Mounted AC (1.5 ton) Net Capacity at 45 Deg Celsius Ambient | 3 | Nos | 187000 | 8000 | 585000
1.02 | Installation, testing & comissioning of DC Inverter Heat & Cool type (Owner Supplied) Air Conditioning units having net operational capacity at 45 degree celcius ambient temperature, including the cost of mounting arrangement, with angle iron bracket, rawal bolts, fitting hangers, refrigerant pipe connections, wiring connections, complete in all resepects. (Already Available)
i) | Wall Mounted AC (1.5 ton) Net Capacity at 45 Deg Celsius Ambient | 1 | Nos |  | 8000 | 8000
1.03 | Supply, chieseling, cutting, Laying and installation of refrigerant piping (Liquid + Gas of appropriate size) make Muller / approved equiavlent Pipe of 21 gauge with expanded rubber foam insulation (make Aeroflex-USA) protected with gray fiber tape duly wrapped with wet glue fabric. It includes the necessay "gas charging" if required, it also includes the necessay control wiring from inner unit to condenser unit. (Avg Length: 80')
i) | Wall Mounted AC (1.5 ton) | 320 | Rft | 1390 | 300 | 540800
Note : Sizes & Lengths of refrigerant pipes with amount required for refrigerant will be verified by the contractor
1.04 | Supply & installation of UP Scheduled drain Piping system Schedule 40 condensate drain from indoor unit to nearest drain point complete with traps, fittings, etc., as shown on drawings.
Pipe Make: Beta, Plasco
| i)Pipe Size: 1" dia Note : Actual Lengths should be verified by the contractor. | 320 | RFT | 365 | 60 | 136000
1.05 | Supply and wiring of 1/1.5/2 Ton Split AC systems with 3x6mm.sq. Cu/PVC Ins. 300/500V grade cable from DB MCB to Split AC unit in inlcuding the cost of 1" dia PVC/UPVC conduit class Electrical laid inside slab/walls/on slab surface/or in cable tray or as required, in including the cost of allied accessories, PVC conduiting accessories, complete in all respects. | 4 | Each | 37000 | 6000 | 172000
| Total Carried Over to Summary of Costs |  |  |  | Rs. | 1441800

## HVAC
BILL OF QUANTITES
HVAC Systems Vol-3
S. No. | Description | Qty | Unit | Supply | Installation, Testing and Commissioning | Amount
1 | HVAC SYSTEMS
1.01 | Reinstallation, Testing and Commissioning of Meeting Room Diffusers allong with all kinds of accessories like vanes, flanges, suspension rods , anchor bolts, GI bolts & nuts, canvas connections , duct connectors, duct dampers & splitter dampers etc.,and as required by the specifications. All size duct should be with ductmate joints. No C & Ss clip joints should be used. | 1 | Job | 0 | 20000 | 20000
1.02 | Supply, fabrication, and installation of G.I. duct work using prime quality sheet metal including hanger & supports and all tees, bends, reducers, elbows, turning vanes, and splitter etc. complete as specified in the specifications, shown on the layout drawing and standards drawing and as directed by the engineer incharge. *- Gauge 22 | 1275 | SFT | 450 | 80 | 675750
1.03 | Supply and installation of 1” thick, 16 kg/m3 density glass wool insulation with 8 oz. Canvas cloth wrapping around duct with adhesive. All longitudinal and circumferential joints shall be sealed with 2” wide adhesive tape as specified in the specifications and as directed by the engineer incharge. | 1275 | SFT | 180 | 50 | 293250
1.04 | Supply & installation of flexible duct connector of 1- 3/4"x 3"x1-3/4" size as shown in drawing and diiected by engineer incharge. | 225 | SFT | 650 | 100 | 168750
1.05 | Providing and installing opposed blade volume dampers with PVC gear, made from 16 SWG G.I. Sheet complete in the specifications, shown on the drawings and directed by the engineer incharge. | 864 | SFT | 3500 | 500 | 3456000
1.06 | Providing and installing extruded anodized aluminium grills for fresh and return air powder coated complete as specified in the specifications, shown on the drawings and directed by the engineer incharge. | 1800 | Sqin | 35 | 5 | 72000
1.07 | Cost of dismantling and handing over of as built equipment and or material at site to the Client, if required per engineer's recommendations, except chilled/hot water pipes, drain pipes, chilled/hot water insulation, valves, specialities etc. | 1 | Job | 10000 | 15000 | 25000
| Total Carried Over to Summary of Costs |  |  |  | Rs. | 4710750

## Plumbing
BILL OF QUANTITES
P.H Fixtures PUBLIC HEALTH WORKS
S. No. | Description | Qty | Unit | Supply | Installation, Testing and Commissioning | Amount
Part-1: PLUMBING FIXTURES (Zilver / Approved Equivalent)
1.01 | Supply and install SS Sinks 1 Compartment with single drainage board including Swirl Faucet with Mixer, Flexible pipes, Valves & all other required fittings, Traps & Accessories to complete the work, as per the Drawings, Specifications and Standards brackets, screws,15 mm dia. C.P. brass T. stop cocks, 40 mm dia heavy duty waste coupling and PVC flexible waste pipe of approved make and quality complete all respects.
| SS TEA POINT SINK (Single bowl ) | 4 | Nos. | 108000 | 8000 | 464000
1.02 | Providing and fixing 15 mm dia C.P. sink mixer with C.P pipe 15 mm dia, of “Porta or Approved Equivalent", Porta or approved equal complete including pipe connections, all fittings, testing etc.
| a) Sink mixer | 4 | Nos. | 54500 | 6000 | 242000
1.03 | Providing and fixing best quality soap dispansor, complete in all respect as per specifications and drawings | 4 | Nos. | 12500 | 1000 | 54000
1.04 | Providing and fixing chromium plated Tissu paper dispansor, “Porta or Approved Equivalent",complete in all respect as per specifications and drawings. | 4 | Nos. | 41500 | 1000 | 170000
1.05 | Providing and installing Electric Geyser including All types of Valves & fitting accessories, complete in all respect as per specifications and drawings.
| 06 Liter Electric Geyser | 5 | Nos. | 90000 | 6000 | 480000
1.06 | Making main sewer connection to the main Landlord sewerage complete in all respect as per specifications and drawings. | 1 | Job | 115000 | 60000 | 175000
1.07 | supply & fixing of European type water closet with WALL mounted with Concealed cistern & flush plate white / light colour, including 3 gallons cistern, P/S trap, C.P tee stop cock with wall cups, connection pipes, “Porta or Approved Equivalent", hinged double bacolite hydralic seat and cover of best quality, all joints to services and drains, plugging and screwing as necessary to the structure and make good the same, complete in all respect as per specifications and drawings. | 7 | Nos. | 132000 | 10000 | 994000
1.08 | Providing and fixing wash hand basin vanity, white / light colour, C.P. tee stop cock with wall cups, “Porta or Approved Equivalent", waste couplien, plug with C.P. brass chain, 1-1/2" dia. P.V.C. (D-type) Waste pipe, connections to water lines, C.P. brass union, nuts, washers, C.P. grating including C.P. bottle trap etc., consisting of 2 feet wide 1:2:4 R.C.C slab, reinforcement, fixing 20mm thick factory polished marble (white ) approved in one piece with 1:2 cement sand mortar making holes in marble for vanity, complete in all respect as per specifications and drawings. | 5 | Nos. | 51500 | 6000 | 287500
1.09 | Providing and fixing C.P. Muslim Shower with double bib cock of best quality, with C.P. flexible pipe of “Porta or Approved Equivalent", complete in all respect as per specifications and drawings. | 7 | Nos. | 14500 | 1000 | 108500
1.1 | Providing and fixing 15 mm dia C.P. mixer with C.P pipe 15 mm dia, of “Porta,Master or Approved Equivalent", Porta or Master approved equal complete including pipe connections, all fittings, testing etc. a) Wash basin mixer | 5 | Nos. | 45000 | 4000 | 245000
1.11 | Providing and fixing best quality soap dispansor of “Porta or Approved Equivalent", complete in all respect as per specifications and drawings | 5 | Nos. | 12500 | 1000 | 67500
1.12 | Providing and fixing chromium plated toilet paper holder, “Porta or Approved Equivalent",complete in all respect as per specifications and drawings. | 7 | Nos. | 11500 | 1000 | 87500
1.13 | Providing and fixing C.P. 3/4" dia. towel bar / rail, “Porta or Approved Equivalent"”, complete in all respect as per specifications and drawings | 5 | Nos. | 23000 | 1000 | 120000
1.14 | Providing and fixing best quality distortion free imported Belgium glass (beveled) mirrors 5mm thick, with hard board backing, chromium plated screws/brackets, complete in all respects as per specifications and drawings. | 80 | SFT | 2000 | 200 | 176000
1.15 | Making sewer and waste piping connection to the sewerage line in duct complete in all respect as per specifications and drawings. | 1 | Job | 65000 | 35000 | 100000
1.16 | Providing and fixing best quality hand drayer , complete in all respect as per specifications and drawings | 1 | Job | 27500 | 3000 | 30500
Part-2: WATER SUPPLY
2.1 | Providing, fixing, jointing and testing Polypropylene
Random (PPR) pipes, DADEX or approved equivalent,
pressure pipe for cold/hot water as per DIN 8077-
8078,PN-20 for pipes and DIN 16962,PN-25 for fittings
(polyfusion welded joints) inside building including
fittings and specials (sockets, tees, elbows, bends,
crosses, reducers, adaptor, plugs and union etc.)
supported on walls or suspended from roof slab or run in
chases including pipe hangers, supports, cutting and
making good the chases and holes, complete in all
respects.
| 25mm dia | 210 | Rft | 340 | 100 | 92400
| 32mm dia | 180 | Rft | 570 | 100 | 120600
| 40mm dia | 100 | Rft | 970 | 125 | 109500
50 mm dia
| Contractor to Verified from LL site engineer | 100 | Rft | 1300 | 150 | 145000
2.2 | Providing and installing ball valves of following nominal
dia, DADEX/SCON/KITZ make or approved Equaivalent,
including jointing, fitting, painting, testing, complete in all
respects to match with PPR and PE pipes of following
diameters.
| 32 mm | 6 | Nos. | 11500 | 1000 | 75000
Part-3: SEWERAGE & DRAINAGE
3.1 | Providing, laying, fixing and testing uPVC soil, waste, vent
and rain water as per ISO 3633:1991 or equivalent BS
specifications including uPVC fittings with solvent cement
jointing or rubber ring joints,DADEX Or Approved
Equivalent make as approved by the Engineer complete in
all respects, including clamps, bends, tees, Y-tees, cowls,
reducers, sleeves, clean out, waterproof sleeves, roof
drain, etc., embedded in floors and walls, clamped to
walls, suspended from slab (common hanger shall be used
for pipe hanging and fiber glass tray under pipes), painted
MS horizontal and vertical pipe hangers of approved
design making requisite no. of holes and making good the
same complete in all respect as per specifications and
drawings.
| 2" i.d | 60 | Rft | 400 | 100 | 30000
| 3" i.d | 185 | Rft | 850 | 125 | 180375
| 4" i.d | 325 | Rft | 1100 | 150 | 406250
3.2 | Providing, laying, fixing and testing floor drain (multifloor trap) uPVC including extension grating and stainless steel cover grating , P-trap best quality local make Porta or Approved Equivalent as approved Engineer, complete in all respect as per specifications and drawings.
|  | 19 | Nos. | 5000 | 1000 | 114000
3.3 | Providing and fixing clean out with threads ferule fixed in pipe with the help of solvent, as shown on drawing, complete in all respects as per specifications and drawings.
| 3" i.d | 2 | Nos. | 4000 | 1000 | 10000
| 4" i.d | 4 | Nos. | 5000 | 1000 | 24000
3.2 | Supply, Installation, Testing of Grease Traps of Holding capacity 8 gallons (approx size= 12"X18"X12") including all accessories & fiitings required for its operation asper drawings,specifications & standards.
|  | 4 | Nos. | 135000 | 5000 | 560000
| Total Carried Over to Summary of Costs |  |  | Rs. |  | 5668625