## Sheet1
M/S IK Associates | [7 empty] | 2024-09-12
Project: DHL Office, Fortune Center, Karachi
Attn: Mr. Taha Ghaznavi
Variation order No 2
Variation order for Extra Work for VRF & Split Units.
S. # | Description | Material Rate | Labour Rate | Over Head profit 28% | Total Rates | Unit | Qty | Amount
1 | Unloading of VRF units from container by regger, lifted and shifted with lifter to the 3rd floor parking and 12th floor. |  | 45000 | 12600 | 57600 | Job | 1 | 57600
2 | Unloading of split units from container by regger and lifted shifted with lifter to the 12th floor and roof. |  | 45000 | 12600 | 57600 | Job | 1 | 57600
3 | VRf condencing units lifted to the roof top by rgger including cuttings and reinstallation of grills' supports etc complete in all respect. |  | 90000 | 25200 | 115200 | Job | 1 | 115200
4 | Providing and making RCC plateform for VRF and split units condencing units. (as required by Building) |  | 160000 | 44800 | 204800 | Job | 1 | 204800
5 | Intallation of fresh air unit with related fittings. |  | 15000 | 4200 | 19200 | Job | 1 | 19200
6 | Core cuttings for split units and VRF copper pipes as roof given by building owner. |  | 1800 | 504 | 2304 | Nos | 42 | 96768
7 | Providing and installation of 1 HP pressure pump set with related fittings such as valve, non return valve, pressure cut out etc complete in all respect. | 155000 | 10000 | 46200 | 211200 | Job | 1 | 211200
8 | Supply of Freon of split AC and VRF system. | 60000 | 0 | 16800 | 76800 | Set | 3 | 230400
9 | Providing and installation of UPVC pipe 06" Dia with related fittings such as Reducing-Tee, elbow & Reducing Socket |  | 300 | 84 | 384 | Rft | 48 | 18432
9 | Providing and installation of UPVC pipe 04" Dia with related fittings such as Reducing-Tee, elbow & Reducing Socket |  | 200 | 56 | 256 | Rft | 54 | 13824
10 | Supply and installation of Disc valve. |  | 500 | 140 | 640 | Nos | 9 | 5760
Total Amount Rs. | [7 empty] | 1030784
Note: Vendor quotation attached
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib