## SUMMARY 01
Project: | ENGRO, THF, 3RD Floor | Date: |  | Date:
Consultant: S Mehboob & Company |  | Drawing No. |  | Drawing No. M04.07
Contractor: National Engineers Co. |  | Sheet # of |  | Sheet # 01 of 01
SUMMARY OF G. I. SHEET METAL DUCT WORK
B.O.Q | Description |  |  | SQFT | Remarks
Item No.
23 31 00
1 | Sheet No 1 |  |  | 728.56
2 | Sheet No 2 |  |  | 618.0139
3 | Sheet No 3 |  |  | 761.375
4 | Sheet No 4 |  |  | 357.6806
5 | Sheet No 5 |  |  | 234.97
6 | Sheet No 6 |  |  | 210.94
7 | Sheet No 7 |  |  | 442.58
8 | Sheet No 8 |  |  | 307.03
9 | Sheet No 9 |  |  | 299.72
10 | Sheet No 10 |  |  | 244.17
11 | Sheet No 11 |  |  | 532.1667
12 | Sheet No 12 |  |  | 879.9444
13 | Sheet No 13 |  |  | 517.25
14 | Sheet No 14 |  |  | 258.4444
15 | Sheet No 15 |  |  | 163.72
16 | Sheet No 16 |  |  | 553.89
17 | Sheet No 17 |  |  | 216.42
18 | Sheet No 18 |  |  | 85.97
19 | Sheet No 19 |  |  | 1040.06
20 | Sheet No 20 |  |  | 114.68
| TOTAL SQFT |  |  | 8567.585 | 0
Contractor's P.M / Site Engineer |  |  | Consultant's P.M / Site Engineer
Signature: |  |  | Signature:
Name: | RAZA |  | Name:

## 1
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 01 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
1 | Supply Air Duct Plenum | 74 | x | 33 |  | 66 |  | 1 | 98.0833
2 | End Cap | 74 | x | 33 |  |  |  | 1 | 16.9583
3 | Supply Air Duct Neck | 64 | x | 18 |  | 6 |  | 1 | 6.8333
3 | Supply Air Duct Pocket | 64 | x | 18 |  | 6 |  | 1 | 6.8333
4 | Supply Air Duct Offset | 64 | x | 18 |  | 48 |  | 1 | 54.6667
4 | Supply Air Duct Pocket | 64 | x | 18 |  | 6 |  | 1 | 6.8333
5 | Supply Air Duct (G.P) | 64 | x | 18 |  | 21 |  | 1 | 23.9167
5 | Supply Air Duct Pocket | 64 | x | 18 |  | 6 |  | 1 | 6.8333
6 | Supply Air Duct Elbow | 64 | x | 18 |  | 43 |  | 1 | 48.9722
6 | Supply Air Duct Pocket | 64 | x | 18 |  | 6 |  | 1 | 6.8333
7 | Supply Air Duct (G.P) | 64 | x | 18 |  | 15 |  | 1 | 17.0833
7 | Supply Air Duct Pocket | 64 | x | 18 |  | 6 |  | 1 | 6.8333
8 | Supply Air Duct | 36 | x | 18 |  | 45 |  | 1 | 33.75
8 | Supply Air Duct Pocket | 36 | x | 18 |  | 6 |  | 1 | 4.5
9 | Supply Air Duct Offset | 36 | x | 18 |  | 55 |  | 1 | 41.25
9 | Supply Air Duct Pocket | 36 | x | 18 |  | 6 |  | 1 | 4.5
10 | Supply Air Duct | 36 | x | 18 |  | 48 |  | 1 | 36
10 | Supply Air Duct Pocket | 36 | x | 18 |  | 6 |  | 1 | 4.5
11 | Supply Air Duct | 36 | x | 18 |  | 48 |  | 1 | 36
11 | Supply Air Duct Pocket | 36 | x | 18 |  | 6 |  | 1 | 4.5
12 | Supply Air Duct | 36 | x | 18 |  | 48 |  | 1 | 36
12 | Supply Air Duct Pocket | 36 | x | 18 |  | 6 |  | 1 | 4.5
13 | Supply Air Duct Reducer | 36 | x | 18 |  | 27 |  | 1 | 21.375
|  | 46 | x | 14
13 | Supply Air Duct Pocket | 46 | x | 14 |  | 6 |  | 1 | 5
14 | Supply Air Duct | 46 | x | 14 |  | 48 |  | 1 | 40
14 | Supply Air Duct Pocket | 46 | x | 14 |  | 6 |  | 1 | 5
15 | Supply Air Duct | 46 | x | 14 |  | 48 |  | 1 | 40
15 | Supply Air Duct Pocket | 46 | x | 14 |  | 6 |  | 1 | 5
16 | Supply Air Duct Round Square | 46 | x | 20 |  | 15 |  | 1 | 13.75
16 | Supply Air Duct Pocket | 46 | x | 20 |  | 6 |  | 1 | 5.5
17 | Supply Air Duct Round Square | 46 | x | 20 |  | 15 |  | 1 | 13.75
17 | Supply Air Duct Pocket | 46 | x | 20 |  | 6 |  | 1 | 5.5
18 | Supply Air Duct | 40 | x | 14 |  | 30 |  | 1 | 22.5
18 | Supply Air Duct Pocket | 40 | x | 14 |  | 6 |  | 1 | 4.5
19 | Supply Air Duct | 40 | x | 14 |  | 48 |  | 1 | 36
19 | Supply Air Duct Pocket | 40 | x | 14 |  | 6 |  | 1 | 4.5
| TOTAL SQFT | [7 empty] | 728.5556

## 1 (2)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 02 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
20 | Supply Air Duct Reducer | 40 | x | 16 |  | 18 |  | 1 | 13.5
|  | 40 | x | 12
20 | Supply Air Duct Pocket | 40 | x | 12 |  | 6 |  | 1 | 4.3333
21 | Supply Air Duct | 40 | x | 12 |  | 60 |  | 1 | 43.3333
21 | Supply Air Duct Pocket | 40 | x | 12 |  | 6 |  | 1 | 4.3333
22 | Supply Air Duct Elbow | 40 | x | 12 |  | 68 |  | 1 | 49.1111
22 | Supply Air Duct Pocket | 40 | x | 12 |  | 6 |  | 1 | 4.3333
23 | Supply Air Duct | 40 | x | 12 |  | 48 |  | 1 | 34.6667
23 | Supply Air Duct Pocket | 40 | x | 12 |  | 6 |  | 1 | 4.3333
24 | Supply Air Duct Elbow | 40 | x | 12 |  | 68 |  | 1 | 49.1111
24 | Supply Air Duct Pocket | 40 | x | 12 |  | 6 |  | 1 | 4.3333
25 | Supply Air Duct | 40 | x | 12 |  | 48 |  | 1 | 34.6667
25 | Supply Air Duct Pocket | 40 | x | 12 |  | 6 |  | 1 | 4.3333
26 | Supply Air Duct Reducer | 40 | x | 12 |  | 27 |  | 1 | 16.875
|  | 26 | x | 12
26 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
27 | Supply Air Duct | 26 | x | 12 |  | 39 |  | 1 | 20.5833
27 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
28 | Supply Air Duct | 26 | x | 12 |  | 48 |  | 1 | 25.3333
28 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
29 | Supply Air Duct | 26 | x | 12 |  | 48 |  | 1 | 25.3333
29 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
30 | Supply Air Duct | 26 | x | 12 |  | 48 |  | 1 | 25.3333
30 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
31 | Supply Air Duct Offset | 26 | x | 12 |  | 99 |  | 1 | 52.25
31 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
32 | Supply Air Duct | 26 | x | 12 |  | 200 |  | 1 | 105.5556
32 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
33 | Supply Air Duct Elbow | 26 | x | 12 |  | 15 |  | 1 | 7.9167
33 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
34 | Supply Air Duct | 26 | x | 12 |  | 88 |  | 1 | 46.4444
34 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
35 | Supply Air Duct Reducer | 26 | x | 12 |  | 27 |  | 1 | 13.5
|  | 22 | x | 12
| TOTAL SQFT | [7 empty] | 618.0139

## 1 (3)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 03 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
36 | Supply Air Duct Elbow | 22 | x | 12 |  | 49 |  | 1 | 23.1389
36 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
37 | Supply Air Duct | 22 | x | 12 |  | 205 |  | 1 | 96.8056
37 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
38 | Supply Air Duct Elbow | 26 | x | 20 |  | 84 |  | 1 | 53.6667
38 | Supply Air Duct Pocket | 26 | x | 20 |  | 6 |  | 1 | 3.8333
39 | Supply Air Duct (G.P) | 26 | x | 20 |  | 6 |  | 1 | 3.8333
39 | Supply Air Duct Pocket | 26 | x | 20 |  | 6 |  | 1 | 3.8333
40 | Supply Air Duct | 26 | x | 20 |  | 48 |  | 1 | 30.6667
40 | Supply Air Duct Pocket | 26 | x | 20 |  | 6 |  | 1 | 3.8333
41 | Supply Air Duct | 26 | x | 20 |  | 48 |  | 1 | 30.6667
41 | Supply Air Duct Pocket | 26 | x | 20 |  | 6 |  | 1 | 3.8333
42 | Supply Air Duct | 26 | x | 20 |  | 48 |  | 1 | 30.6667
42 | Supply Air Duct Pocket | 26 | x | 20 |  | 6 |  | 1 | 3.8333
43 | Supply Air Duct Reducer | 26 | x | 20 |  | 27 |  | 1 | 16.125
|  | 26 | x | 14
43 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
44 | Supply Air Duct Offset | 26 | x | 14 |  | 48 |  | 1 | 26.6667
44 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
45 | Supply Air Duct Elbow | 26 | x | 14 |  | 55 |  | 1 | 30.5556
45 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
46 | Supply Air Duct | 26 | x | 14 |  | 125 |  | 1 | 69.4444
46 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
47 | Supply Air Duct Offset | 26 | x | 14 |  | 43 |  | 1 | 23.8889
47 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
48 | Supply Air Duct | 26 | x | 14 |  | 304 |  | 1 | 168.8889
48 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
49 | Supply Air Duct Reducer | 26 | x | 14 |  | 18 |  | 1 | 11.25
|  | 40 | x | 10
49 | Supply Air Duct Pocket | 40 | x | 10 |  | 6 |  | 1 | 4.1667
50 | Supply Air Duct (G.P) | 40 | x | 10 |  | 41 |  | 1 | 28.4722
50 | Supply Air Duct Pocket | 40 | x | 10 |  | 6 |  | 1 | 4.1667
51 | Supply Air Duct Reducer | 40 | x | 10 |  | 18 |  | 1 | 11.25
|  | 26 | x | 14
51 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
52 | Supply Air Duct Elbow | 26 | x | 14 |  | 55 |  | 1 | 30.5556
52 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
53 | Supply Air Duct | 26 | x | 14 |  | 27 |  | 1 | 15
| TOTAL SQFT | [7 empty] | 761.375

## 1 (4)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 04 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
54 | Supply Air Duct (G.P) | 26 | x | 14 |  | 33 |  | 1 | 18.3333
54 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
55 | Supply Air Duct Elbow | 26 | x | 14 |  | 45 |  | 1 | 25
55 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
56 | Supply Air Duct (G.P) | 26 | x | 14 |  | 13 |  | 1 | 7.2222
56 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
57 | Supply Air Duct | 26 | x | 14 |  | 48 |  | 1 | 26.6667
57 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
58 | Supply Air Duct | 26 | x | 14 |  | 48 |  | 1 | 26.6667
58 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
59 | Supply Air Duct Reducer | 26 | x | 14 |  | 27 |  | 1 | 13.875
|  | 22 | x | 12
59 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
60 | Supply Air Duct | 22 | x | 12 |  | 48 |  | 1 | 22.6667
60 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
61 | Supply Air Duct | 22 | x | 12 |  | 48 |  | 1 | 22.6667
61 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
62 | Supply Air Duct | 22 | x | 12 |  | 48 |  | 1 | 22.6667
62 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
63 | Supply Air Duct | 22 | x | 12 |  | 27 |  | 1 | 12.75
63 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
64 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
64 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
65 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
65 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
66 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
66 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
67 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
67 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
68 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
68 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
69 | Supply Air Duct Elbow | 18 | x | 10 |  | 37 |  | 1 | 14.3889
69 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
70 | Supply Air Duct | 18 | x | 10 |  | 17 |  | 1 | 6.6111
| TOTAL SQFT | [7 empty] | 357.6806

## 1 (5)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 05 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
71 | Supply Air Duct Elbow | 18 | x | 10 |  | 37 |  | 1 | 14.3889
71 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
72 | Supply Air Duct Round Square | 18 | x | 10 |  | 15 |  | 1 | 5.8333
72 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
73 | Supply Air Duct Round Square | 18 | x | 10 |  | 15 |  | 1 | 5.8333
73 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
74 | Supply Air Duct | 18 |  | 10 |  | 48 |  | 1 | 18.6667
74 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
75 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
75 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
76 | Supply Air Duct Round Square | 18 | x | 10 |  | 15 |  | 1 | 5.8333
76 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
77 | Supply Air Duct Round Square | 18 | x | 10 |  | 15 |  | 1 | 5.8333
77 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
78 | Supply Air Duct | 18 | x | 10 |  | 48 |  | 1 | 18.6667
BRANCH 1
1 | Supply Air Duct Neck | 18 | x | 10 |  | 6 |  | 1 | 2.3333
1 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
2 | Supply Air Duct (G.P) | 10 | x | 10 |  | 27 |  | 1 | 7.5
2 | Supply Air Duct Pocket | 10 | x | 10 |  | 6 |  | 1 | 1.6667
3 | Supply Air Duct Round Square | 14 | x | 14 |  | 15 |  | 1 | 5.8333
3 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
4 | Supply Air Duct Round Square | 14 | x | 14 |  | 15 |  | 1 | 5.8333
4 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
5 | Supply Air Duct Elbow | 10 | x | 10 |  | 27 |  | 1 | 7.5
5 | Supply Air Duct Pocket | 10 | x | 10 |  | 6 |  | 1 | 1.6667
6 | Supply Air Duct | 10 | x | 10 |  | 48 |  | 1 | 13.3333
6 | Supply Air Duct Pocket | 10 | x | 10 |  | 6 |  | 1 | 1.6667
7 | Supply Air Duct | 10 | x | 10 |  | 48 |  | 1 | 13.3333
7 | Supply Air Duct Pocket | 10 | x | 10 |  | 6 |  | 1 | 1.6667
8 | Supply Air Duct | 10 | x | 10 |  | 38 |  | 1 | 10.5556
9 | End Cap | 10 | x | 10 |  | 6 |  | 1 | 0.69444
BRANCH 2
1 | Supply Air Duct Neck | 18 | x | 10 |  | 6 |  | 1 | 2.3333
1 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
2 | Supply Air Duct (G.P) | 10 | x | 10 |  | 39 |  | 1 | 10.8333
2 | Supply Air Duct Pocket | 10 | x | 10 |  | 6 |  | 1 | 1.6667
3 | Supply Air Duct Round Square | 14 | x | 14 |  | 15 |  | 1 | 5.8333
3 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
4 | Supply Air Duct Round Square | 14 | x | 14 |  | 15 |  | 1 | 5.8333
4 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
5 | Supply Air Duct | 10 | x | 10 |  | 39 |  | 1 | 10.8333
| TOTAL SQFT | [7 empty] | 234.9722

## 1 (6)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 06 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
6 | End Cap | 10 | x | 10 |  |  |  | 2 | 0.69444
BRANCH 3
1 | Supply Air Duct Neck | 18 | x | 10 |  | 6 |  | 1 | 2.3333
1 | Supply Air Duct Pocket | 18 | x | 10 |  | 6 |  | 1 | 2.3333
2 | Supply Air Duct (G.P) | 10 | x | 10 |  | 39 |  | 1 | 10.8333
2 | Supply Air Duct Pocket | 10 | x | 10 |  | 6 |  | 1 | 1.6667
3 | Supply Air Duct Round Square | 14 | x | 14 |  | 15 |  | 1 | 5.8333
3 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
4 | Supply Air Duct Round Square | 14 | x | 14 |  | 15 |  | 1 | 5.8333
4 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
5 | Supply Air Duct | 10 | x | 10 |  | 39 |  | 1 | 10.8333
6 | End Cap | 10 | x | 10 |  |  |  | 1 | 0.69444
BRANCH 4
1 | Supply Air Duct Neck | 28 | x | 12 |  | 6 |  | 1 | 3.3333
1 | Supply Air Duct Pocket | 28 | x | 12 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
2 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
3 | Supply Air Duct | 20 | x | 12 |  | 42 |  | 1 | 18.6667
3 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
4 | Supply Air Duct Neck | 32 | x | 12 |  | 6 |  | 1 | 3.6667
4 | Supply Air Duct Pocket | 32 | x | 12 |  | 6 |  | 1 | 3.6667
5 | Supply Air Duct | 16 | x | 12 |  | 41 |  | 1 | 15.9444
5 | Supply Air Duct Pocket | 16 | x | 12 |  | 6 |  | 1 | 2.3333
6 | Supply Air Duct | 16 | x | 12 |  | 41 |  | 1 | 15.9444
6 | Supply Air Duct Pocket | 16 | x | 12 |  | 6 |  | 1 | 2.3333
7 | Supply Air Duct | 16 | x | 12 |  | 48 |  | 1 | 18.6667
8 | End Cap | 16 | x | 12 |  |  |  | 2 | 1.3333
BRANCH 5
1 | Supply Air Duct Neck | 28 | x | 12 |  | 6 |  | 1 | 3.3333
1 | Supply Air Duct Pocket | 28 | x | 12 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
2 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
3 | Supply Air Duct | 20 | x | 12 |  | 42 |  | 1 | 18.6667
| TOTAL SQFT | [7 empty] | 210.9444

## 1 (7)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 07 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
BRANCH 5
4 | Supply Air Duct Neck | 32 | x | 12 |  | 6 |  | 1 | 3.6667
4 | Supply Air Duct Pocket | 32 | x | 12 |  | 6 |  | 1 | 3.6667
5 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
5 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
6 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
6 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
7 | Supply Air Duct | 20 | x | 12 |  | 27 |  | 1 | 12
7 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
8 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
9 | End Cap | 20 | x | 12 |  | 6 |  | 2 | 1.6667
BRANCH 6
1 | Supply Air Duct Neck | 38 | x | 12 |  | 6 |  | 1 | 4.1667
1 | Supply Air Duct Pocket | 38 | x | 12 |  | 6 |  | 1 | 4.1667
2 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
2 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
3 | Supply Air Duct | 30 | x | 12 |  | 40 |  | 1 | 23.3333
3 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
4 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
4 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
5 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
5 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
6 | Supply Air Duct Elbow | 30 | x | 12 |  | 41 |  | 1 | 23.9167
6 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
7 | Supply Air Duct | 30 | x | 12 |  | 27 |  | 1 | 15.75
7 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
8 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
8 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
9 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
9 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
10 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
10 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
11 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
11 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
12 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
12 | Supply Air Duct Pocket | 30 | x | 12 |  | 6 |  | 1 | 3.5
13 | Supply Air Duct | 30 | x | 12 |  | 27 |  | 1 | 15.75
| TOTAL SQFT | [7 empty] | 442.5833

## 1 (8)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 08 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
14 | Supply Air Duct | 30 | x | 12 |  | 48 |  | 1 | 28
15 | End Cap | 30 | x | 12 |  |  |  | 2 | 2.5
BRANCH 7
1 | Supply Air Duct Neck | 20 | x | 12 |  | 6 |  | 1 | 2.6667
1 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
2 | Supply Air Duct | 12 | x | 12 |  | 135 |  | 1 | 45
2 | Supply Air Duct Pocket | 12 | x | 12 |  | 6 |  | 1 | 2
3 | Supply Air Duct | 12 | x | 12 |  | 88 |  | 1 | 29.3333
4 | End Cap | 12 | x | 12 |  |  |  | 2 | 1
BRANCH 8
1 | Supply Air Duct Neck | 34 | x | 12 |  | 6 |  | 1 | 3.8333
1 | Supply Air Duct Pocket | 34 | x | 12 |  | 6 |  | 1 | 3.8333
2 | Supply Air Duct | 26 | x | 12 |  | 42 |  | 1 | 22.1667
2 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
3 | Supply Air Duct Round Square | 26 | x | 12 |  | 15 |  | 1 | 7.9167
3 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
4 | Supply Air Duct Round Square | 26 | x | 12 |  | 15 |  | 1 | 7.9167
4 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
5 | Supply Air Duct | 26 | x | 12 |  | 48 |  | 1 | 25.3333
5 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
6 | Supply Air Duct Elbow | 26 | x | 12 |  | 58 |  | 1 | 30.6111
6 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
7 | Supply Air Duct | 26 | x | 12 |  | 24 |  | 1 | 12.6667
7 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
8 | Supply Air Duct | 26 | x | 12 |  | 15 |  | 1 | 7.9167
BRANCH 9
1 | Supply Air Duct Elbow | 12 | x | 12 |  | 29 |  | 1 | 9.6667
1 | Supply Air Duct Pocket | 12 | x | 12 |  | 6 |  | 1 | 2
2 | Supply Air Duct | 12 | x | 12 |  | 15 |  | 1 | 5
2 | Supply Air Duct Pocket | 12 | x | 12 |  | 6 |  | 1 | 2
3 | Supply Air Duct | 12 | x | 12 |  | 48 |  | 1 | 16
3 | Supply Air Duct Pocket | 12 | x | 12 |  | 6 |  | 1 | 2
4 | Supply Air Duct | 12 | x | 12 |  | 48 |  | 1 | 16
| TOTAL SQFT | [7 empty] | 307.0278

## 1 (9)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 09 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
5 | End Cap | 12 | x | 12 |  |  |  | 1 | 1
BRANCH 10
1 | Supply Air Duct Elbow | 20 | x | 12 |  | 49 |  | 1 | 21.7778
1 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
2 | Supply Air Duct | 20 | x | 12 |  | 35 |  | 1 | 15.5556
2 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
3 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
3 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
4 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
4 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
5 | Supply Air Duct | 20 | x | 12 |  | 39 |  | 2 | 17.3333
5 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
6 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
6 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
7 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
7 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
8 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
8 | Supply Air Duct Pocket | 20 | x | 12 |  | 6 |  | 1 | 2.6667
9 | Supply Air Duct | 20 | x | 12 |  | 48 |  | 1 | 21.3333
10 | End Cap | 20 | x | 12 |  | 6 |  | 1 | 1.6667
BRANCH 11
1 | Supply Air Duct Neck | 22 | x | 12 |  | 6 |  | 1 | 2.8333
1 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
2 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
2 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
3 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
3 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
4 | Supply Air Duct | 14 | x | 12 |  | 27 |  | 1 | 9.75
4 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
5 | Supply Air Duct Elbow | 14 | x | 12 |  | 15 |  | 1 | 5.4167
5 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
6 | Supply Air Duct | 14 | x | 12 |  | 27 |  | 1 | 9.75
6 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
7 | Supply Air Duct Elbow | 14 | x | 12 |  | 26 |  | 1 | 9.3889
7 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
8 | Supply Air Duct Round Square | 14 | x | 12 |  | 15 |  | 1 | 5.4167
| TOTAL SQFT | [7 empty] | 299.7222

## 1 (10)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 10 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 01
BRANCH 11
9 | Supply Air Duct Round Square | 14 | x | 12 |  | 15 |  | 1 | 5.4167
9 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
10 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
10 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
11 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
11 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
12 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
12 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
13 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
14 | End Cap | 14 | x | 12 |  |  |  | 1 | 1.1667
BRANCH 12
1 | Supply Air Duct Neck | 22 | x | 12 |  | 6 |  | 1 | 2.8333
1 | Supply Air Duct Pocket | 22 | x | 12 |  | 6 |  | 1 | 2.8333
2 | Supply Air Duct Elbow | 14 | x | 12 |  | 33 |  | 1 | 11.9167
2 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
3 | Supply Air Duct Round Square | 14 | x | 12 |  | 15 |  | 1 | 5.4167
3 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
4 | Supply Air Duct Round Square | 14 | x | 12 |  | 15 |  | 1 | 5.4167
4 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
5 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
5 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
6 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
6 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
7 | Supply Air Duct | 14 | x | 12 |  | 48 |  | 1 | 17.3333
7 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
8 | Supply Air Duct | 14 | x | 12 |  | 27 |  | 1 | 9.75
8 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
9 | Supply Air Duct Elbow | 14 | x | 12 |  | 33 |  | 1 | 11.9167
9 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
10 | Supply Air Duct | 14 | x | 12 |  | 51 |  | 1 | 18.4167
10 | Supply Air Duct Pocket | 14 | x | 12 |  | 6 |  | 1 | 2.1667
11 | Supply Air Duct | 14 | x | 12 |  | 51 |  | 1 | 18.4167
12 | End Cap | 14 | x | 12 |  |  |  | 2 | 1.1667
| TOTAL SQFT | [7 empty] | 244.1667
|  | 12 |  | 10

## 1 (11)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 11 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
1 | Supply Air Duct Reducer | 70 | x | 20 |  | 18 |  | 1 | 21.75
|  | 64 | x | 20
1 | Supply Air Duct Pocket | 64 | x | 20 |  | 6 |  | 1 | 7
2 | Supply Air Duct | 64 | x | 20 |  | 69 |  | 1 | 80.5
2 | Supply Air Duct Pocket | 64 | x | 20 |  | 6 |  | 1 | 7
3 | Supply Air Duct Reducer | 64 | x | 20 |  | 30 |  | 1 | 29.1667
|  | 40 | x | 16
3 | Supply Air Duct Pocket | 40 | x | 16 |  | 6 |  | 1 | 4.6667
4 | Supply Air Duct Offset | 40 | x | 16 |  | 39 |  | 1 | 30.3333
4 | Supply Air Duct Pocket | 40 | x | 16 |  | 6 |  | 1 | 4.6667
5 | Supply Air Duct | 40 | x | 16 |  | 48 |  | 1 | 37.3333
5 | Supply Air Duct Pocket | 40 | x | 16 |  | 6 |  | 1 | 4.6667
6 | Supply Air Duct | 40 | x | 16 |  | 48 |  | 1 | 37.3333
6 | Supply Air Duct Pocket | 40 | x | 16 |  | 6 |  | 1 | 4.6667
7 | Supply Air Duct | 40 | x | 16 |  | 33 |  | 1 | 25.6667
7 | Supply Air Duct Pocket | 40 | x | 16 |  | 6 |  | 1 | 4.6667
8 | Supply Air Duct | 40 | x | 16 |  | 48 |  | 1 | 37.3333
8 | Supply Air Duct Pocket | 40 | x | 16 |  | 6 |  | 1 | 4.6667
9 | Supply Air Duct Reducer | 40 | x | 16 |  | 30 |  | 1 | 20
|  | 26 | x | 14
9 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
10 | Supply Air Duct Round Square | 26 | x | 14 |  | 15 |  | 1 | 8.3333
10 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
11 | Supply Air Duct Round Square | 26 | x | 14 |  | 15 |  | 1 | 8.3333
11 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
12 | Supply Air Duct | 26 | x | 14 |  | 99 |  | 1 | 55
12 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
13 | Supply Air Duct Reducer | 26 | x | 14 |  | 18 |  | 1 | 10.75
|  | 38 | x | 8
13 | Supply Air Duct Pocket | 38 | x | 8 |  | 6 |  | 1 | 3.8333
14 | Supply Air Duct | 38 | x | 8 |  | 39 |  | 1 | 24.9167
14 | Supply Air Duct Pocket | 38 | x | 8 |  | 6 |  | 1 | 3.8333
15 | Supply Air Duct Reducer | 38 | x | 8 |  | 18 |  | 1 | 10.75
|  | 26 | x | 14
15 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
16 | Supply Air Duct | 26 | x | 14 |  | 51 |  | 1 | 28.3333
| TOTAL SQFT | [7 empty] | 532.1667
|  | 12 |  | 10

## 1 (12)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 12 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
17 | Supply Air Duct | 18 | x | 14 |  | 155 |  | 1 | 68.8889
17 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
18 | Supply Air Duct | 18 | x | 14 |  | 124 |  | 1 | 55.1111
18 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
19 | Supply Air Duct Elbow | 18 | x | 14 |  | 24 |  | 1 | 10.6667
19 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
20 | Supply Air Duct | 18 | x | 14 |  | 196 |  | 1 | 87.1111
20 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
21 | Supply Air Duct Elbow | 18 | x | 14 |  | 42 |  | 1 | 18.6667
21 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
22 | Supply Air Duct | 18 | x | 14 |  | 150 |  | 1 | 66.6667
23 | End Cap | 18 | x | 14 |  | 6 |  | 2 | 3.5
24 | Supply Air Duct Neck | 66 | x | 16 |  | 6 |  | 1 | 6.8333
24 | Supply Air Duct Pocket | 66 | x | 16 |  | 6 |  | 1 | 6.8333
25 | Supply Air Duct Offset | 58 | x | 16 |  | 62 |  | 1 | 63.7222
25 | Supply Air Duct Pocket | 58 | x | 16 |  | 6 |  | 1 | 6.1667
26 | Supply Air Duct | 58 | x | 16 |  | 54 |  | 1 | 55.5
26 | Supply Air Duct Pocket | 58 | x | 16 |  | 6 |  | 1 | 6.1667
28 | Supply Air Duct Elbow | 58 | x | 16 |  | 105 |  | 1 | 107.9167
28 | Supply Air Duct Pocket | 58 | x | 16 |  | 6 |  | 1 | 6.1667
29 | Supply Air Duct | 58 | x | 16 |  | 48 |  | 1 | 49.3333
29 | Supply Air Duct Pocket | 58 | x | 16 |  | 6 |  | 1 | 6.1667
30 | Supply Air Duct | 58 | x | 16 |  | 94 |  | 1 | 96.6111
30 | Supply Air Duct Pocket | 58 | x | 16 |  | 6 |  | 1 | 6.1667
31 | Supply Air Duct Reducer | 58 | x | 16 |  | 30 |  | 1 | 22.9167
|  | 20 | x | 16
31 | Supply Air Duct Pocket | 20 | x | 16 |  | 6 |  | 1 | 3
32 | Supply Air Duct | 20 | x | 16 |  | 63 |  | 1 | 31.5
32 | Supply Air Duct Pocket | 20 | x | 16 |  | 6 |  | 1 | 3
33 | Supply Air Duct Elbow | 20 | x | 16 |  | 12 |  | 1 | 6
33 | Supply Air Duct Pocket | 20 | x | 16 |  | 6 |  | 1 | 3
34 | Supply Air Duct | 20 | x | 16 |  | 75 |  | 1 | 37.5
34 | Supply Air Duct Pocket | 20 | x | 16 |  | 6 |  | 1 | 3
35 | Supply Air Duct Elbow | 20 | x | 16 |  | 15 |  | 1 | 7.5
35 | Supply Air Duct Pocket | 20 | x | 16 |  | 6 |  | 1 | 3
36 | Supply Air Duct Round Square | 20 | x | 16 |  | 15 |  | 1 | 7.5
36 | Supply Air Duct Pocket | 20 | x | 16 |  | 6 |  | 1 | 3
37 | Supply Air Duct Round Square | 20 | x | 16 |  | 15 |  | 1 | 7.5
| TOTAL SQFT | [7 empty] | 879.9444
|  | 12 |  | 10

## 1 (13)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 13 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
38 | Supply Air Duct | 20 | x | 16 |  | 48 |  | 1 | 24
39 | End Cap | 20 | x | 16 |  |  |  | 1 | 2.2222
40 | Supply Air Duct Neck | 54 | x | 14 |  | 6 |  | 1 | 5.6667
40 | Supply Air Duct Pocket | 54 | x | 14 |  | 6 |  | 1 | 5.6667
41 | Supply Air Duct | 46 | x | 14 |  | 18 |  | 1 | 15
41 | Supply Air Duct Pocket | 46 | x | 14 |  | 6 |  | 1 | 5
42 | Supply Air Duct | 46 | x | 14 |  | 48 |  | 1 | 40
42 | Supply Air Duct Pocket | 46 | x | 14 |  | 6 |  | 1 | 5
43 | Supply Air Duct Reducer | 46 | x | 14 |  | 30 |  | 1 | 24.1667
|  | 42 | x | 14
43 | Supply Air Duct Pocket | 42 | x | 14 |  | 6 |  | 1 | 4.6667
44 | Supply Air Duct | 42 | x | 14 |  | 48 |  | 1 | 37.3333
44 | Supply Air Duct Pocket | 42 | x | 14 |  | 6 |  | 1 | 4.6667
45 | Supply Air Duct | 42 | x | 14 |  | 48 |  | 1 | 37.3333
45 | Supply Air Duct Pocket | 42 | x | 14 |  | 6 |  | 1 | 4.6667
46 | Supply Air Duct Elbow | 42 | x | 14 |  | 70 |  | 1 | 54.4444
46 | Supply Air Duct Pocket | 42 | x | 14 |  | 6 |  | 1 | 4.6667
47 | Supply Air Duct | 42 | x | 14 |  | 48 |  | 1 | 37.3333
47 | Supply Air Duct Pocket | 42 | x | 14 |  | 6 |  | 1 | 4.6667
48 | Supply Air Duct | 42 | x | 14 |  | 15 |  | 1 | 11.6667
48 | Supply Air Duct Pocket | 42 | x | 14 |  | 6 |  | 1 | 4.6667
49 | Supply Air Duct Elbow | 30 | x | 18 |  | 62 |  | 1 | 41.3333
49 | Supply Air Duct Pocket | 30 | x | 18 |  | 6 |  | 1 | 4
50 | Supply Air Duct Elbow | 30 | x | 18 |  | 46 |  | 1 | 30.6667
50 | Supply Air Duct Pocket | 30 | x | 18 |  | 6 |  | 1 | 4
51 | Supply Air Duct Round Square | 30 | x | 18 |  | 15 |  | 1 | 10
51 | Supply Air Duct Pocket | 30 | x | 18 |  | 6 |  | 1 | 4
52 | Supply Air Duct Round Square | 30 | x | 18 |  | 15 |  | 1 | 10
52 | Supply Air Duct Pocket | 30 | x | 18 |  | 6 |  | 1 | 4
53 | Supply Air Duct | 30 | x | 18 |  | 27 |  | 1 | 18
53 | Supply Air Duct Pocket | 30 | x | 18 |  | 6 |  | 1 | 4
54 | Supply Air Duct | 30 | x | 18 |  | 22 |  | 1 | 14.6667
54 | Supply Air Duct Pocket | 30 | x | 18 |  | 6 |  | 1 | 4
55 | Supply Air Duct | 30 | x | 18 |  | 48 |  | 1 | 32
56 | End Cap | 30 | x | 18 |  |  |  | 1 | 3.75
| TOTAL SQFT | [7 empty] | 517.25
|  | 12 |  | 10

## 1 (14)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 14 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
BRANCH 1
1 | Supply Air Duct Neck | 26 | x | 16 |  | 6 |  | 1 | 3.5
1 | Supply Air Duct Pocket | 26 | x | 16 |  | 6 |  | 1 | 3.5
2 | Supply Air Duct Round Square | 18 | x | 16 |  | 15 |  | 1 | 7.0833
3 | Supply Air Duct Round Square | 18 | x | 16 |  | 15 |  | 1 | 7.0833
3 | Supply Air Duct Pocket | 18 | x | 16 |  | 6 |  | 1 | 2.8333
4 | Supply Air Duct Neck | 32 | x | 16 |  | 6 |  | 1 | 4
4 | Supply Air Duct Pocket | 32 | x | 16 |  | 6 |  | 1 | 4
5 | Supply Air Duct | 18 | x | 16 |  | 225 |  | 1 | 106.25
6 | End Cap | 18 | x | 16 |  |  |  | 2 | 4
BRANCH 2
1 | Supply Air Duct Neck | 18 | x | 14 |  | 6 |  | 1 | 2.6667
1 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
2 | Supply Air Duct | 10 | x | 14 |  | 46 |  | 1 | 15.3333
2 | Supply Air Duct Pocket | 10 | x | 14 |  | 6 |  | 1 | 2
3 | Supply Air Duct Elbow | 10 | x | 14 |  | 33 |  | 1 | 11
3 | Supply Air Duct Pocket | 10 | x | 14 |  | 6 |  | 1 | 2
4 | Supply Air Duct | 10 | x | 14 |  | 88 |  | 1 | 29.3333
5 | End Cap | 10 | x | 14 |  |  |  | 1 | 0.97222
BRANCH 3
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 23 |  | 1 | 10.2222
BRANCH 4
1 | Supply Air Duct Neck | 26 | x | 14 |  | 6 |  | 1 | 3.3333
1 | Supply Air Duct Pocket | 26 | x | 14 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 18 | x | 14 |  | 39 |  | 1 | 17.3333
2 | Supply Air Duct Pocket | 18 | x | 14 |  | 6 |  | 1 | 2.6667
3 | Supply Air Duct Reducer | 18 | x | 14 |  | 24 |  | 1 | 10
|  | 14 | x | 14
| TOTAL SQFT | [7 empty] | 258.4444
|  | 12 |  | 10

## 1 (15)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 15 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
BRANCH 4
4 | Supply Air Duct | 14 | x | 14 |  | 63 |  | 1 | 24.5
4 | Supply Air Duct Pocket | 14 | x | 14 |  | 6 |  | 1 | 2.3333
5 | Supply Air Duct Reducer | 14 | x | 14 |  | 18 |  | 1 | 6.5
|  | 10 | x | 14
5 | Supply Air Duct Pocket | 10 | x | 14 |  | 6 |  | 1 | 2
6 | Supply Air Duct | 10 | x | 14 |  | 39 |  | 1 | 13
7 | End Cap | 10 | x | 14 |  |  |  | 1 | 0.97222
BRANCH 5
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
1 | Supply Air Duct Pocket | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 6
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
1 | Supply Air Duct Pocket | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 7
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
1 | Supply Air Duct Pocket | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 8
1 | Supply Air Duct Neck | 26 | x | 12 |  | 6 |  | 1 | 3.1667
1 | Supply Air Duct Pocket | 26 | x | 12 |  | 6 |  | 1 | 3.1667
2 | Supply Air Duct | 18 | x | 12 |  | 27 |  | 1 | 11.25
2 | Supply Air Duct Pocket | 18 | x | 12 |  | 6 |  | 1 | 2.5
3 | Supply Air Duct Elbow | 18 | x | 12 |  | 42 |  | 1 | 17.5
3 | Supply Air Duct Pocket | 18 | x | 12 |  | 6 |  | 1 | 2.5
4 | Supply Air Duct Offset | 18 | x | 12 |  | 23 |  | 1 | 9.5833
4 | Supply Air Duct Pocket | 18 | x | 12 |  | 6 |  | 1 | 2.5
5 | Supply Air Duct Round Square | 18 | x | 12 |  | 15 |  | 1 | 6.25
| TOTAL SQFT | [7 empty] | 163.7222
|  | 12 |  | 10

## 1 (16)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 16 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
BRANCH 8
6 | Supply Air Duct Round Square | 18 | x | 12 |  | 15 |  | 1 | 6.25
7 | Supply Air Duct | 18 | x | 12 |  | 99 |  | 1 | 41.25
8 | End Cap | 18 | x | 12 |  |  |  | 1 | 1.5
BRANCH 9
1 | Supply Air Duct | 16 | x | 14 |  | 39 |  | 1 | 16.25
1 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
2 | Supply Air Duct Elbow | 16 | x | 14 |  | 38 |  | 1 | 15.8333
2 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
3 | Supply Air Duct Elbow | 16 | x | 14 |  | 38 |  | 1 | 15.8333
3 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
4 | Supply Air Duct | 16 | x | 14 |  | 291 |  | 1 | 121.25
4 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
5 | Supply Air Duct Bridge Piece | 16 | x | 14 |  | 44 |  | 1 | 18.3333
5 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
6 | Supply Air Duct Elbow | 16 | x | 14 |  | 38 |  | 1 | 15.8333
6 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
7 | Supply Air Duct | 16 | x | 14 |  | 27 |  | 1 | 11.25
7 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
8 | Supply Air Duct Round Square | 16 | x | 14 |  | 15 |  | 1 | 6.25
9 | Supply Air Duct Round Square | 16 | x | 14 |  | 15 |  | 1 | 6.25
9 | Supply Air Duct Pocket | 16 | x | 14 |  | 6 |  | 1 | 2.5
10 | Supply Air Duct | 16 | x | 14 |  | 147 |  | 1 | 61.25
11 | End Cap | 16 | x | 14 |  | 6 |  | 1 | 1.5556
BRANCH 10
1 | Supply Air Duct Neck | 22 | x | 14 |  | 6 |  | 1 | 3
1 | Supply Air Duct Pocket | 22 | x | 14 |  | 6 |  | 1 | 3
2 | Supply Air Duct | 22 | x | 14 |  | 89 |  | 1 | 44.5
2 | Supply Air Duct Pocket | 22 | x | 14 |  | 6 |  | 1 | 3
3 | Supply Air Duct | 22 | x | 14 |  | 244 |  | 1 | 122
3 | Supply Air Duct Pocket | 22 | x | 14 |  | 6 |  | 1 | 3
4 | Supply Air Duct Elbow | 22 | x | 14 |  | 33 |  | 1 | 16.5
| TOTAL SQFT | [7 empty] | 553.8889
|  | 12 |  | 10

## 1 (17)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 17 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
BRANCH 10
5 | Supply Air Duct | 22 | x | 14 |  | 195 |  | 1 | 97.5
6 | End Cap | 22 | x | 14 |  |  |  | 1 | 2.1389
BRANCH 11
1 | Supply Air Duct Neck | 18 | x | 14 |  | 6 |  | 2 | 2.6667
2 | Supply Air Duct | 10 | x | 14 |  | 111 |  | 1 | 37
3 | End Cap | 10 | x | 14 |  |  |  | 1 | 0.97222
4 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
5 | Supply Air Duct | 22 | x | 10 |  | 6 |  | 1 | 2.6667
BRANCH 12
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 13
1 | Supply Air Duct | 14 | x | 14 |  | 48 |  | 1 | 18.6667
2 | Supply Air Duct Reducer | 14 | x | 14 |  | 24 |  | 1 | 8.6667
|  | 10 | x | 14
3 | Supply Air Duct | 10 | x | 14 |  | 48 |  | 1 | 16
4 | End Cap | 10 | x | 14 |  |  |  | 1 | 0.97222
BRANCH 14
1 | Supply Air Duct | 14 | x | 14 |  | 27 |  | 1 | 10.5
| TOTAL SQFT | [7 empty] | 216.4167
|  | 12 |  | 10

## 1 (18)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 18 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00 | AHU 02
BRANCH 14
2 | Supply Air Duct Reducer | 14 | x | 14 |  | 24 |  | 1 | 8.6667
|  | 10 | x | 14
3 | Supply Air Duct | 10 | x | 14 |  | 45 |  | 1 | 15
4 | End Cap | 10 | x | 14 |  |  |  | 1 | 0.97222
BRANCH 15
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 16
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 17
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
BRANCH 18
1 | Supply Air Duct Neck | 30 | x | 10 |  | 6 |  | 1 | 3.3333
2 | Supply Air Duct | 22 | x | 10 |  | 27 |  | 1 | 12
| TOTAL SQFT | [7 empty] | 85.9722
|  | 12 |  | 10

## 1 (19)
Project: | ENGRO, THF, 3RD Floor | [5 empty] | Date: | Date:
Consultant: S Mehboob & Company | [6 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [6 empty] | Sheet # of | Sheet # 19 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [6 empty] | sqft.
23 31 00
1 | Plenum Box | 14 | x | 12 |  | 36 |  | 1 | 13
2 | Plenum Box | 14 | x | 12 |  | 102 |  | 1 | 36.8333
3 | Plenum Box | 14 | x | 12 |  | 36 |  | 1 | 13
4 | Plenum Box | 14 | x | 12 |  | 36 |  | 1 | 13
5 | Plenum Box | 14 | x | 12 |  | 174 |  | 1 | 62.8333
6 | Plenum Box | 14 | x | 12 |  | 198 |  | 1 | 71.5
7 | Plenum Box | 14 | x | 12 |  | 282 |  | 1 | 101.8333
8 | Plenum Box | 14 | x | 12 |  | 90 |  | 1 | 32.5
9 | Plenum Box | 14 | x | 12 |  | 126 |  | 1 | 45.5
10 | Plenum Box | 14 | x | 12 |  | 102 |  | 1 | 36.8333
11 | Plenum Box | 14 | x | 12 |  | 102 |  | 1 | 36.8333
12 | Plenum Box | 14 | x | 12 |  | 78 |  | 1 | 28.1667
13 | Plenum Box | 14 | x | 12 |  | 174 |  | 1 | 62.8333
14 | Plenum Box | 14 | x | 12 |  | 54 |  | 1 | 19.5
15 | Plenum Box | 14 | x | 12 |  | 106 |  | 1 | 38.2778
16 | Plenum Box | 14 | x | 12 |  | 106 |  | 1 | 38.2778
17 | Plenum Box | 14 | x | 12 |  | 114 |  | 1 | 41.1667
18 | Plenum Box | 14 | x | 12 |  | 234 |  | 1 | 84.5
19 | Plenum Box | 14 | x | 12 |  | 150 |  | 1 | 54.1667
20 | Plenum Box | 14 | x | 12 |  | 150 |  | 1 | 54.1667
21 | Plenum Box | 14 | x | 12 |  | 150 |  | 1 | 54.1667
22 | Plenum Box | 14 | x | 12 |  | 174 |  | 1 | 62.8333
23 | Plenum Box End Caps | 14 | x | 12 |  |  |  | 44 | 51.3333
| TOTAL SQFT | [7 empty] | 1040.0556
|  | 12 |  | 10

## 1 (20)
Project: | ENGRO, THF, 3RD Floor |  |  |  |  | Date: | Date:
Consultant: S Mehboob & Company | [5 empty] | Drawing No. | Drawing No. |  | RCP.07
Contractor: I.K ASSOCIATES | [5 empty] | Sheet # of | Sheet # 20 of |  | 20
G. I. SHEET METAL DUCT WORK
B.O.Q | Description | Size (Inch) |  | Length (Inch) | Length (Inch) |  | Nos | SQFT | Remarks
Item No. | [5 empty] | sqft.
23 31 00 | PLENUM NECKS
1 | Round Neck | 8 | Dia. |  | 6 |  | 2 | 2.0947
2 | Round Neck | 8 | Dia. |  | 6 |  | 4 | 4.1893
3 | Round Neck | 8 | Dia. |  | 6 |  | 2 | 2.0947
4 | Round Neck | 8 | Dia. |  | 6 |  | 1 | 1.0473
5 | Round Neck | 10 | Dia. |  | 6 |  | 4 | 5.2367
6 | Round Neck | 10 | Dia. |  | 6 |  | 6 | 7.855
7 | Round Neck | 10 | Dia. |  | 6 |  | 8 | 10.4733
8 | Round Neck | 10 | Dia. |  | 6 |  | 3 | 3.9275
9 | Round Neck | 10 | Dia. |  | 6 |  | 4 | 5.2367
10 | Round Neck | 10 | Dia. |  | 6 |  | 3 | 3.9275
11 | Round Neck | 10 | Dia. |  | 6 |  | 3 | 3.9275
12 | Round Neck | 10 | Dia. |  | 6 |  | 3 | 3.9275
13 | Round Neck | 10 | Dia. |  | 6 |  | 4 | 5.2367
14 | Round Neck | 10 | Dia. |  | 6 |  | 2 | 2.6183
15 | Round Neck | 10 | Dia. |  | 6 |  | 4 | 5.2367
16 | Round Neck | 10 | Dia. |  | 6 |  | 4 | 5.2367
17 | Round Neck | 10 | Dia. |  | 6 |  | 3 | 3.9275
18 | Round Neck | 10 | Dia. |  | 6 |  | 8 | 10.4733
19 | Round Neck | 10 | Dia. |  | 6 |  | 6 | 7.855
20 | Round Neck | 10 | Dia. |  | 6 |  | 6 | 7.855
21 | Round Neck | 10 | Dia. |  | 6 |  | 5 | 6.5458
22 | Round Neck | 10 | Dia. |  | 6 |  | 6 | 7.855
| TOTAL SQFT | [6 empty] | 114.683
|  | 12 | 10