## summary 19A
Project: ENGRO, THF, 3RD Floor | [6 empty] | Date:
Client: S Mehboob & Company | [6 empty] | Drawing No. FP-08
Contractor: I.K ASSOCIATES | [6 empty] | Sheet #. 01 of 01
SUMMARY 3RD FLOOR FIRE FIGHTING WORK
M. S. PIPING WORK SPRINKLER SYSTEM
S. No. | Description | 1" | 1-1/4" | 1-1/2" | 2" | 2-1/2" | 3" | 4"
|  | Rft | Rft | Rft | Rft | Rft | Rft | Rft
1 | Sheet 1 | 169 | 21.5 | 0 | 17 | 0 | 54.5 | 75.5
2 | Sheet 2 | 135 | 26 | 11 | 0 | 24 | 0 | 0
3 | Sheet 3 | 128.5 | 29 | 31 | 51 | 20.5 | 0 | 18
4 | Sheet 4 | 173 | 11 | 0 | 0 | 0 | 71 | 10
5 | Sheet 5 | 134 | 12 | 16 | 21 | 17 | 0 | 0
| GRAND TOTAL Rft | 739.5 | 99.5 | 58 | 89 | 61.5 | 125.5 | 103.5
Contractor's P.M / Site Engineer | [5 empty] | Consultant's P.M / Site Engineer
Signature: | [5 empty] | Signature:
Name: | RAZA |  |  |  |  | Name:

## 1
Project: ENGRO, THF, 3RD Floor | [6 empty] | Date:
Client: S Mehboob & Company | [6 empty] | Drawing No. FP-08
Contractor: I.K ASSOCIATES | [6 empty] | Sheet #. 01 of 05
FIRE FIGHTING WORK
M. S. PIPING WORK SPRINKLER SYSTEM
S. No. | Description | 1" | 1-1/4" | 1-1/2" | 2" | 2-1/2" | 3" | 4"
|  | Rft | Rft | Rft | Rft | Rft | Rft | Rft
1 | Fire Pipe | [6 empty] | 7
2 | Fire Pipe | [6 empty] | 46
3 | Fire Pipe | 9
4 | Fire Pipe | 6
5 | Fire Pipe | 22
6 | Fire Pipe | [6 empty] | 16.5
7 | Fire Pipe | 10
8 | Fire Pipe | [6 empty] | 6
9 | Fire Pipe |  | 16
10 | Fire Pipe | 10
11 | Fire Pipe | 2
12 | Fire Pipe | 19
13 | Fire Pipe | 2
14 | Fire Pipe | [5 empty] | 13.5
15 | Fire Pipe |  | 5.5
16 | Fire Pipe | 20.5
17 | Fire Pipe | 14.5
18 | Fire Pipe | [5 empty] | 41
19 | Fire Pipe | 27
20 | Fire Pipe | 27
21 | Fire Pipe |  |  |  | 17
| TOTAL RFT | 169 | 21.5 | 0 | 17 | 0 | 54.5 | 75.5

## 2
Project: ENGRO, THF, 3RD Floor | [6 empty] | Date:
Client: S Mehboob & Company | [6 empty] | Drawing No. FP-08
Contractor: I.K ASSOCIATES | [6 empty] | Sheet #. 02 of 05
FIRE FIGHTING WORK
M. S. PIPING WORK SPRINKLER SYSTEM
S. No. | Description | 1" | 1-1/4" | 1-1/2" | 2" | 2-1/2" | 3" | 4"
|  | Rft | Rft | Rft | Rft | Rft | Rft | Rft
22 | Fire Pipe | 9
23 | Fire Pipe | 9
24 | Fire Pipe | 10
25 | Fire Pipe | 21
26 | Fire Pipe | 9
27 | Fire Pipe |  | 13
28 | Fire Pipe | 9.5
29 | Fire Pipe | 2
30 | Fire Pipe | 17.5
31 | Fire Pipe |  |  |  |  | 24
32 | Fire Pipe | 17
33 | Fire Pipe | 2
34 | Fire Pipe | 5
35 | Fire Pipe | 4
36 | Fire Pipe | 4
37 | Fire Pipe | 4
38 | Fire Pipe | 4
39 | Fire Pipe | 4
40 | Fire Pipe | 4
41 | Fire Pipe |  |  | 11
42 | Fire Pipe |  | 13
| TOTAL RFT | 135 | 26 | 11 | 0 | 24 | 0 | 0

## 3
Project: ENGRO, THF, 3RD Floor | [6 empty] | Date:
Client: S Mehboob & Company | [6 empty] | Drawing No. FP-08
Contractor: I.K ASSOCIATES | [6 empty] | Sheet #. 03 of 05
FIRE FIGHTING WORK
M. S. PIPING WORK SPRINKLER SYSTEM
S. No. | Description | 1" | 1-1/4" | 1-1/2" | 2" | 2-1/2" | 3" | 4"
|  | Rft | Rft | Rft | Rft | Rft | Rft | Rft
43 | Fire Pipe | 30
44 | Fire Pipe | 22
45 | Fire Pipe |  |  |  | 20
46 | Fire Pipe |  |  | 5
47 | Fire Pipe |  | 11
48 | Fire Pipe | 13
49 | Fire Pipe | 16
50 | Fire Pipe |  |  | 10
51 | Fire Pipe |  | 10
52 | Fire Pipe | 16
53 | Fire Pipe | [6 empty] | 18
54 | Fire Pipe | 5
55 | Fire Pipe |  |  |  |  | 20.5
56 | Fire Pipe | 2
57 | Fire Pipe | 3
58 | Fire Pipe | 5.5
59 | Fire Pipe |  |  |  | 31
60 | Fire Pipe |  |  | 16
61 | Fire Pipe |  | 8
62 | Fire Pipe | 14
63 | Fire Pipe | 2
| TOTAL RFT | 128.5 | 29 | 31 | 51 | 20.5 | 0 | 18

## 4
Project: ENGRO, THF, 3RD Floor | [6 empty] | Date:
Client: S Mehboob & Company | [6 empty] | Drawing No. FP-08
Contractor: I.K ASSOCIATES | [6 empty] | Sheet #. 04 of 05
FIRE FIGHTING WORK
M. S. PIPING WORK SPRINKLER SYSTEM
S. No. | Description | 1" | 1-1/4" | 1-1/2" | 2" | 2-1/2" | 3" | 4"
|  | Rft | Rft | Rft | Rft | Rft | Rft | Rft
64 | Fire Pipe | 9
65 | Fire Pipe | 2
66 | Fire Pipe | 6
67 | Fire Pipe | 1
68 | Fire Pipe | 25
69 | Fire Pipe | 2
70 | Fire Pipe | [6 empty] | 10
71 | Fire Pipe | 1
72 | Fire Pipe | [5 empty] | 71
73 | Fire Pipe | 13
74 | Fire Pipe | 4
75 | Fire Pipe | 10
76 | Fire Pipe | 5
77 | Fire Pipe | 5
78 | Fire Pipe | 17
79 | Fire Pipe | 5
80 | Fire Pipe | 26
81 | Fire Pipe | 19
82 | Fire Pipe |  | 11
83 | Fire Pipe | 18
84 | Fire Pipe | 5
| TOTAL RFT | 173 | 11 | 0 | 0 | 0 | 71 | 10

## 5
Project: ENGRO, THF, 3RD Floor | [6 empty] | Date:
Client: S Mehboob & Company | [6 empty] | Drawing No. FP-08
Contractor: I.K ASSOCIATES | [6 empty] | Sheet #. 05 of 05
FIRE FIGHTING WORK
M. S. PIPING WORK SPRINKLER SYSTEM
S. No. | Description | 1" | 1-1/4" | 1-1/2" | 2" | 2-1/2" | 3" | 4"
|  | Rft | Rft | Rft | Rft | Rft | Rft | Rft
85 | Fire Pipe | 3
86 | Fire Pipe | 3
87 | Fire Pipe | 8
88 | Fire Pipe |  |  |  |  | 17
89 | Fire Pipe |  |  |  | 15
90 | Fire Pipe |  |  | 4
91 | Fire Pipe |  | 5
92 | Fire Pipe | 15
93 | Fire Pipe | 30
94 | Fire Pipe | 16
95 | Fire Pipe |  |  | 5
96 | Fire Pipe |  | 7
97 | Fire Pipe | 3
98 | Fire Pipe | 16
99 | Fire Pipe |  |  |  | 6
100 | Fire Pipe | 9
101 | Fire Pipe |  |  | 7
102 | Fire Pipe | 13
103 | Fire Pipe | 8
104 | Fire Pipe | 4
105 | Fire Pipe | 6
| TOTAL RFT | 134 | 12 | 16 | 21 | 17 | 0 | 0