## Table 1
TOMO II SCHEDULE OF ITEMWISE PRICES
S.NO | DESCRIPTION | QUANTITY | COST OF EQUIPMENT & MATERIAL (Rupees) | COST OF INSTALLATION (Rupees) | TOTAL COST OF COLUMN 4 & 5 (Rupees)
1 | 2 | 3 | 4 | 5 | 6
1 | Owner supplied selfcontained aircooled packaged airconditioning unit complete with accessories. | 3 Nos. |  | 75000 | 75000
2 | Owner supplied Direct expansion coil with condensing unit, controls and accessories. | 3 No. |  | 45000 | 45000
3 | Owner supplied Electric type reheat coils complete with accessories and controls. | 3 Nos. |  | 45000 | 45000
4 | Viscous oil type 2” thick cleanable air filters. | 1 Lot | 20000 | 5000 | 25000
5 | 65% efficiency dust spot test, ASHRAE Standard 52-76 air filters (2 ft x 2ft x 2ft ) . | 12Nos. | 60000 | 12000 | 72000
6 | 95% efficiency dust spot test, ASHARE Standard 52-76 air filters (2ft x 2ft x 2ft) | 12 Nos. | 60000 | 12000 | 72000
7 | 99.97% efficiency hepa air filters complete housing and accessories (2ftx2ftx1ft) | 16 Nos | 2000000 | 100000 | 2100000
8 | MCC with circuit breakers, disconnect switches, fuses, starters etc. | 1 No. | 550000 | 25000 | 575000
9 | Complete electric wiring and earthing for equipment and controls. | Lot | 150000 | 30000 | 180000
10 | G.I. Sheet metal ducting, plenums, viscous oil and high efficiency filters, housings, volume control dampers, fire dampers and other sheet fabrications.
A | 18 gauge | 660 sqft | 330000 | 52800 | 382800
B | 22 gauge | 480 sqft | 201600 | 38400 | 240000
C | 22 gauge | 3800 sqft | 1596000 | 304000 | 1900000
11 | I inch thick Thermal insulation of air ducts complete with vapor barrier, jacketing and finishing. | 1520 sqft | 836000 | 91200 | 927200
12 | Supply return, fresh and exhaust air registers, grilles, dampers and louvers. | Lot | 450000 | 25000 | 475000
13 | Refrigerant piping complete with fittings, valves, insulation etc. | Lot | 475000 | 40000 | 515000
14 | Drain piping with insulation, fittings and specialties. | Lot | 60000 | 20000 | 80000
15 | 26 gauge G.I. sheet jacketing for exposed insulated air ducts and refrigerant piping. | Lot | 615000 | 100000 | 715000
16 | Temperature, humidity and room pressure controls complete with accessories. | Lot | 1240000 | 60000 | 1300000
17 | Equipment foundation. | Lot | 0 | 0 | 0
18 | Air balancing. | Lot | 0 | 60000 | 60000
19 | 26 gauge G.I Sheet jacketing complete with accessories for all insulated ducting and refrigerant piping. | Lot | 0 |  | 0
20 | Painting of all equipment and system components. | Lot | 30000 | 20000 | 50000
SUB TOTAL Rs. |  |  |  |  | 9834000
21 | Microbial Paint to be applied on all Duting. |  |  |  | 1200000
22 | Any other item, material, services which may be required to complete the given Scope of Works to be quoted and details to be attached. Any Quantity increase / decrease in the BOQ as per drawing may also be quoted here. NO ADDITIONAL MATERIAL (QUANTITY or Cost will be allowed). |  |  |  | 0
23 | Spare parts for two years operation. |  |  |  | 0
24 | As-installed drawings and transparencies 4 sets. |  |  |  | 30000
25 | Cost of special tools and instruments. |  |  |  | 90000
26 | Cost of testing, starting-up, commissioning, balancing, adjusting and handling over of the complete system including refrigerant and oil charging. |  |  |  | 75000
27 | Cost of one month test run. |  |  |  | 100000
TOTAL COST OF TENDER Rs. |  |  |  |  | 11329000
Very Special discount Rs. |  |  |  |  | 2129000
TOTAL COST AFTER DISCOUNT Rs. |  |  |  |  | 9200000
(Rupees …………………………………………………………………………………………………………………………………. …………………………………………………………………………………………………………………………………………..)
NOTES:
1. The work to be done in two shifts.
2. Qualified experienced Site Engineer to be deputed at Site.
3. Shop Drawings to be prepared before commencement of work.
|  |  |  | Deal Locked | 8263000
|  |  |  | Mob adv | 1652600