## HVAC
|  |  |  | Date | 29-12-23
M/S Dawat-e-Hadiyah Burhani Mahal |  |  |  | Invoice # | 331
Mciver Road, Karachi |  |  |  | NTN # | 4312149-7
Invoice
Installation of HVAC work Food Court - The North Walk Shopping Mall
S. # | Description | Unit | Qty | Labour Rate | Labour Amount
1 | Re-align, regging and shifting packaged unit as required including supply & installation of vibration islolator 4" thick (6 x 3 units) | Nos | 3 | 8000 | 24000
2 | Installation of G.I. sheet metal duct machine made (22 / 24 SWG) with flange, nut bolts, gasket, duct sealent etc complete in all respect. | Sqft | 4760 | 60 | 285600
3 | Installation of Glass wool insulation of 25mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 1980 | 30 | 59400
4 | Installation of Glass wool insulation of 25mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (external duct area) | Sqft | 2780 | 40 | 111200
5 | Installation of G.I Cladding on exposed area duct (26 SWG) for protection of insulation. | Sqft | 2780 | 60 | 166800
6 | Installation of Return air Grill
i) | (6" x 8 ft long) | Nos | 4 | 1000 | 4000
ii | (6" x 6 ft long) | Nos | 6 | 800 | 4800
7 | Installation of fresh air in take louver 12 x 20 | Nos | 3 | 1000 | 3000
8 | Installation of aluminium filter 1" thick 12 x 20 | Nos | 3 | 700 | 2100
10 | Installation of Flexible duct connector for return / supply air duct connection. | Rft | 42 | 100 | 4200
11 | Installation of volume control damper 12 x 20 | Nos | 3 | 1000 | 3000
12 | Installation of volume control damper 32 x 22 | Nos | 6 | 1500 | 9000
13 | Installation of Fire damper 32 x 22 | Nos | 3 | 1500 | 4500
14 | Installation of hangers / supports for G.I sheet metal ducts. | Job | 1 | 15000 | 15000
15 | Making of Shop drawings & As built on Auto CAD 2018. | Set | 1 | 10000 | 10000
16 | Installation of control wiring including installation of thermostat complete in all respect. | Job | 3 | 5000 | 15000
17 | Painting & Identification. | Job | 1 | 20000 | 20000 | 3661200 | 756600
19 | Testing & commissioning cordination with supplier | Job | 3 | 5000 | 15000 | 1830600 | 378300 | 49179 | 2258079
Sub- Total Amount Rs |  |  |  |  | 756600 |  |  |  | #REF!
SST Tax 13% |  |  |  |  | 98358 | Advance payment |  |  | #REF!
Total Amount Rs |  |  |  |  | 854958 | Advance | 50% | 2208900
[6 empty] | Less Tax | 7.5% | 165667.5
[6 empty] | Cheque amount |  | 2043232.5
Note: 1) Billing will be charged on actual measurement. 2) 50% Mob adv. & 50% after completion of work 3) Completion time 45 days |  |  |  | Discount | 217269
4299115
[6 empty] | 1830600 | 378300
For PIONEER SERVICES. | [5 empty] | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | Gross amout |  | #REF!
[6 empty] | received amount |  | 2208900
[6 empty] | Net |  | #REF!
[6 empty] | Less Tax 7.5% |  | #REF!
[6 empty] | Net |  | #REF!
[6 empty] | Less 20% SRB w/H |  | 19671.6
#REF!
#REF!
PIONEER SERVICES

## working
|  |  | Discount | 4.811%
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
Discount | 88065.0403 | 18198.9538
Sub Total Amount | 1742534.9597 | 360101.0462
SRB 13% on Labour | 0 | 46813.136
Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
SRB 13% on Labour | 0 | 49179
Total Amount | 1830600 | 427479
Discount | 88065.0403 | 20564.8177
Grand Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419