## Table 1
Procurement Schedule EY Karachi - 19th Floor
HVAC
Description | Duration | ORDER PlACED | EXPECTED DELIVERY
FAN COIL UNITS | 20 Weeks
WATER COOLED PACKAGED AIR CONDITIONER | 28 Weeks
VAV | 12 Weeks
HVAC CONTROLS | 12 Weeks
DUCT WORK | 30 Days
Supports | 04 Weeks
Flexible Ducts | 21 Days
Butterfly Dampers | 30 Days
Fire Damper - (UL - Listed) | 90 Days
Backdraft Damper | 45 Days
PIPING | 45 Days
VALVES & SPECIALITIES | 60 Days
THERMAL INSULATION | 60 Days
AIR DEVICES | 45 Days
METER & GAUGES (SECTION 23 05 19) | 60 Days
HVAC CONTROLS | 12 Weeks
Instant Electric Operated Hot Water Heaters | 45 Days
PLUMBING FIXTURES & FITTINGS | 45 Days
PAINTING & FINISHING | 7 Days
FIRE FIGHTING
Description | Duration | ORDER PlACED | EXPECTED DELIVERY
FIRE SPRINKLERS | 12 Weeks
CORRUGATED STAINLESS STEEL FLEXIBLE CONNECTOR | 12 Weeks
PORTABLE FIRE EXTINGUISHER | 12 Weeks
BLACK STEEL SCHEDULE-40 PIPING (S | 05 Weeks
GATE VALVE | 05 Weeks
SIESMIC BRACING | 05 Weeks
PAINTING COATING & STENCILING | 02 Weeks
PIPE SUPPORT SYSTEM | 04 Weeks