## Sheet1
ABSTRACT
HVAC WORKS

## Rationalized HVAC BOQ
ABSTRACT | [12 empty] | FINAL BILL
ACMV WORKS
KANTEEN
KOHSAR MARKET F-6 , ISLAMABAD
S.No. |  | Description | Units | Qty | BILL Qty | Material |  | Labour |  | Amount | FINAL BILL
[6 empty] | Rate | Amount | Rate | Amount |  | Material Amount | Labor Amount | TOTAL AMOUNT
All Heating, Ventilation & Air Conditioning Services shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Client & Consultant.
1 |  | Supply, installation, testing and commissioning of air conditioning units decorative & ducted & Split - type (reversible) of different capacities (as per drawing & schedule) including supply of supports, brackets, rubber isolator, flashing, control wiring & power wiring (connection) in G.I. for external / PVC for internal from outdoor unit to indoor unit complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.
| 1.1 | AC-01 (As per schedule) | No. | 1 | 1 |  | 0 |  | 0 | 0 |  | 0 | 0
| 1.2 | AC-02 (As per schedule) | No. | 4 | 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2 |  | Supply, installation, testing and commissioning of refrigerant pipes (liquid + gas) with 12mm thick expended rubber foam insulation, PVC tape wrapping + control wiring from indoor to outdoor for single & multi split type units including gas charging if required and installation of branch distributor (supplied with units) complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of Consultant. | [6 empty] | 0 | 0 | 0 | 0 | 0
| 2.1 | AC-01 (As per schedule) | Rft | 10 | 18 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 2.2 | AC-02 (As per schedule) | Rft | 245 | 210 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3 |  | Supply,Unloading, rigging, lifting, placement, installation, testing and commissioning of heat recovery ventilator (HRV) as per mentioned in schedule, including supply & installation of duct mounted electronic temp controller with temp sensor, vibration isolator, electrical connection, flexible duct connection / connector, power wiring from isolation box to unit (10' to 15' radius), support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | [6 empty] | 0 | 0 | 0 | 0 | 0
| 3.1 | HRV-01 (As per schedule) | No. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
4 |  | Supply and installation of 18 SWG Painted G.I. sheet metal tray for refrigerant pipes and control wiring exposed to weather complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Lot | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
5 |  | Supply and installation of uPVC pipe (Drain) for internal units with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | [6 empty] | 0 | 0 | 0 | 0 | 0
| 5.1 | 1" dia | Rft | 100 | 53 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 5.2 | 1-1/4" dia | Rft | 32 | 61 |  | 0 |  | 0 | 0 | 0 | 0 | 0
6 |  | Supply, fabrication and installation of M.S sheet metal welded duct of 2.0 mm (14 Gauge) thickness for kitchen exhaust air. complete in all respects including 300 x150 access doors at all changes in direction, transformation, plenums, chambers, connection piece of hood round to square, supports & hangers etc. complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqft | 680 | 759.8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
7 |  | Supply, fabrication and installation of 50mm thick Rockwool insulation of 50kg/m3 density with wire mesh reinforcement for M.S sheet metal ducts of kitchen exhaust air, complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqft | 714 | 759.8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
8 |  | Supply, Fabrication and installation of G.I sheet metal duct for external duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connector, access door, transformation, plenums chambers, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqft | 820 | 1052 |  | 0 |  | 0 | 0 | 0 | 0 | 0
9 |  | Supply, fabrication and installation of G.I Sheet 0.46mm (26-SWG) protective cladding over the insulation work of above Kitchen MS-Duct complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqft | 785.4 | 887 |  | 0 |  | 0 | 0 | 0 | 0 | 0
10 |  | Supply, rigging, lifting, placement, Installation, testing and commissioning of Ventilation Fans (as per mentioned in schedule) including supply of vibration isolator, electrical connection, flexible duct connection, support & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.
| 10.1 | EAF-01 (As per schedule) | No. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 10.2 | EAF-02 (As per schedule) | No. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 10.3 | FAF-01 (As per schedule) | No. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 10.4 | FAF-02 (As per schedule) | No. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
11 |  | Supply, installation testing and commissioning of SS-304 fabricated , double skin exhaust hood, including, supports, hangers, electric connections, pipe connection & other accessories complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 11.1 | EH-01 (size 10' 6" x 4' 1")Wall Mounted Canopy Type | No. | 1 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 11.2 | EH-02 (size 22' 0" x 2' 4") Back Shelf Low Proximity Type | No. | 1 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
12 |  | Supply & installation of Air Curtains complete in all respects ready to operate including supply of support brackets electrical connection complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.
| 12.1 | 4 ft length | No. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 12.2 | 6 ft length | No. | 1 | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
13 |  | Supply & installation of aluminum fabricated powder coated Fresh Air louvers including supply of wooden frame, wooden sheet for close future's lovers, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 13.1 | 10" × 10" | No. | 2 | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 13.2 | 48" × 12" | No. | 2 | 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
14 |  | Supply & Installation of Aluminium fabricated, power coated grills, Diffuser & Registers for supply air, return air, exhaust air & fresh air of different sizes of (Grade A) supply of wooden frame, support etc. complete in all respects ready to operate as per drawing specification, instruction and approval of consultant.
| 14.1 | Exhaust/Fresh Air Grill
| i | 10" × 10" | No. | 2 | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 14.2 | Perforated Supply Air with two way directional control & with fine tune damper,
| i | PAS Module 600mm × 600mm (neck size shown in drawing) | No. | 5 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 5
15 |  | Supply and installation, testing and commissioning of ceiling exhaust fan including electrical connection, flexible duct connection, uPVC pipe, exhaur air louver, support & hangers complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Nos. | 3 | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
16 |  | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant.
| 16.1 | 10" Dia | Rft | 22 | 110 |  | 0 |  | 0 | 0 | 0 | 0 | 0
17 |  | Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of Consultant.
| 17.1 | 10" Dia | Nos | 6 | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 1
18 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Job. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
19 |  | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Job. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
20 |  | Making of Shop Drawings & AS BUILT drawings (4 sets) on AutoCAD 2013 with sectional details with Technical / Operational manual, LOG book for each equipment complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Job. | 1 | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Cost of ACMV Works Rs. |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
A |  | Additional Work Amount | [10 empty] | 0
|  | Total Cost of ACMV Works including Additional work Rs. |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0

## VO
VARIATION ORDERS SUMMARY
KANTEEN F6 ISLAMABAD
Sr. No. | VO. No. | Category of Work | Description | Date | Reason | Verified Impact |  |  |  | Status
C |  | HVAC Work |  |  |  | Qty | Unit | Rate | Amount
1 | HVAC-01 | HVAC Work | S.S Kitchen Hood | 2025-03-12 | Cost Variation | 0 | Job |  | 0 | Approved
2 | HVAC-02 | HVAC Work | AC Split Unit 1TR | 2025-03-17 | Additional Item | 1 | Job |  | 0 | Approved
3 | HVAC-03 | HVAC Work | Exhuast Fan | 2025-03-20 | Cost Variation | 1 | Job |  | 0 | Approved
TOTAL Amount | [8 empty] | 0