## sum
2025-03-15
Summary of Variation Orders - Spar Super Market Karachi
Sr # | DESCRIPTION | AMOUNT
* | Variation order of Valves for cold room | 1375360
* | Variation order of Lifting & shifitng of VRF units | 416000
| Variation order of Refregrent gas | 823840
* | Variation order of HDPE Pipe, Wire & conduits | 281404.16
| Total amount Rs. | 2896604.16

## Valves for cold room
M/S IK Associates | [7 empty] | 2025-03-15
Attn: Taha Ghaznavi
Project: Spar supermarket Karachi
Variation Order No 1
Supply and installation of Isolation valves for Cold Room Freezer
S. # | Description | Material Rate | Labour Rate | Over Head profit 28% | Total Rate | Unit | Qty | Amount
1 | Supply and installation of following valves for Cold room.
i | Isolation Valve 1/4" | 3650 | 1500 | 1442 | 6592 | Nos | 4 | 26368
ii | Isolation Valve 3/8" | 4500 | 1500 | 1680 | 7680 | Nos | 63 | 483840
iii | Isolation Valve 1/2" | 5900 | 1500 | 2072 | 9472 | Nos | 4 | 37888
iv | Isolation Valve 5/8" | 6200 | 1500 | 2156 | 9856 | Nos | 44 | 433664
v | Isolation Valve 7/8" | 6700 | 1500 | 2296 | 10496 | Nos | 12 | 125952
vi | Solenoid Valve 3/8" | 16000 | 2000 | 5040 | 23040 | Nos | 6 | 138240
2 | Supply and installation of P-Traps for walk-in cold room | [6 empty] | 0
i | P Trap 5/8" | 3500 | 800 | 1204 | 5504 | Nos | 4 | 22016
ii | P Trap 3/4" | 4200 | 900 | 1428 | 6528 | Nos | 8 | 52224
iii | P Trap 7/8" | 4900 | 1000 | 1652 | 7552 | Nos | 4 | 30208
3 | Supply and installation of expansion valve | 18500 | 1000 | 5460 | 24960 | Nos | 1 | 24960
Total Amount Rs. | [7 empty] | 1375360
Note: Supplier's quotation attached
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib

## Lifting shifting
M/S IK Associates | [7 empty] | 2025-03-15
Project: Spar Super Market.
Project: Spar supermarket Karachi
Variation Order No 2
Lifting / Shifitng of Indoor + Outdoor units at various location.
S. # | Description | Material Rate | Labour Rate | Over Head profit 28% | Total Rate | Unit | Qty | Amount
1 | 1st consignment of VRF indoor units received container unloaded units lifted and shifted at Lowe basement. | 0 | 80000 | 22400 | 102400 | Job | 1 | 102400
2 | 2nd consignment of VRF of indoor + outdoor units received container nnloaded, indoor units kept at basement and outdoor units kept at 1srt floor parking | 0 | 75000 | 21000 | 96000 | Job | 1 | 96000
3 | Regging, lifting, shifting & placing of VRF condensing units at M.S platform (1st floor parking) | 0 | 65000 | 18200 | 83200 | Job | 1 | 83200
4 | Removal of VRF condensing units from 1st floor and regging lifting and shifted at M.S Platform on 2nd Floor. | 0 | 60000 | 16800 | 76800 | Job | 1 | 76800
5 | Lifting, shifting of VRF condensing units / cold room freezer from 1st floor parking to back of the house paltform. | 0 | 45000 | 12600 | 57600 | Job | 1 | 57600
Total Amount Rs. | [7 empty] | 416000
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib

## GAs
M/S IK Associates | [7 empty] | 2025-03-15
Project: Spar Super Market.
Project: Spar supermarket Karachi
Variation Order No 3
Refrigerant Gas charged for Cold Room
S. # | Description | Material Rate | Labour Rate | Over Head profit 28% | Total Rate | Unit | Qty | Amount
1 | Provided and charged compressor oil (SUNISO BELGIUM) 4 Ltr for cold room & freezers. | 28500 | 2000 | 8540 | 39040 | Gal | 1 | 39040
2 | Refrigerant R-404 Gas charged in refrigeration units and Freezers | 35000 | 2000 | 9800 | 46800 | Jar | 2 | 93600
3 | Freon R-410 charged in VRF system. | 30000 | 0 | 8400 | 38400 | Jar | 18 | 691200
Total Amount Rs. | [7 empty] | 823840
Note: Supplier's quotation attached
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib

## misc
M/S IK Associates | [7 empty] | 2025-03-15
Project: Spar Super Market.
Project: Spar supermarket Karachi
Variation Order No 4
Misc work for Cold room area.
S. # | Description | Material Rate | Labour Rate | Over Head profit 28% | Total Rate | Unit | Qty | Amount
4 | Supply and installation of HDPE Pipe 6" Dia PN-10 for external under drive area including digging of earth dismantle of RCC beam and refilling of earth. | 3500 | 1000 | 1260 | 5760 | MTR | 24 | 138240
6 | Supply & installation of control wire for cold room and freezers. |  |  | 0 | 0 |  |  | 0
i | 1mm x 2 core Flexible | 280 | 70 | 98 | 448 | MTR | 17 | 7616
ii | 1mm x 3 core Flexible | 310 | 70 | 106.4 | 486.4 | MTR | 10 | 4864
iii | 2.5mm x 4 core Flexible | 795 | 80 | 245 | 1120 | MTR | 15 | 16800
iv | 1.5mm x 3 core Flexible | 310 | 70 | 106.4 | 486.4 | MTR | 160 | 77824
7 | Supply and installation of PVC conduits and fittings for refrigeration controls. |  |  | 0 | 0 |  |  | 0
i | PVC conduit Pipe 1" | 68 | 45 | 31.64 | 144.64 | MTR | 198 | 28638.72
ii | PVC conduit Bend 1" | 246 | 50 | 82.88 | 378.88 | Dozen | 8.5 | 3220.48
iii | PVC conduit Socket 1" | 115 | 45 | 44.8 | 204.8 | Dozen | 6 | 1228.8
iv | PVC conduit Junction Box | 624 | 150 | 216.72 | 990.72 | Dozen | 3 | 2972.16
Total Amount Rs. | [7 empty] | 281404.16
Note: Supplier's quotation attached
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib

## Extra work for cold storage and
M/S IK Associates | [5 empty] | 2025-05-21
Project: Spar supermarket Karachi
EXTRA WORK FOR COLD STORAGE AND FREEZER AREA - SPAR
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Amount
1 | Supply and installation of following copper pipe for extra work carried out
i | 3/4" dia | Rft | 688 | 1139.88 | 168 | 899821.44
ii | 3/8" dia | Rft | 1387.5 | 403.2 | 126 | 734265
iii | 7/8" dia | Rft | 286 | 1470 | 168 | 468468
iiv | 5/8" dia | Rft | 413.5 | 1008 | 168 | 486276
Total Amount Rs. | [5 empty] | 2588830.44
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib