## PES summary
2023-05-30
SANA SAFINAS
SUMMARY OF RUNNING BILL
Sr # | Scope of work | Supply Amount | Labor Amount | Total Amount
| CIVIL ID | 0 | 0 | 0
1 | RECEPTION / WAITING AREA | 0 | 0 | 0
2 | WORKSPACE + LOBBY | 0 | 0 | 0
3 | CABIN ( 6 NOS ) | 0 | 0 | 0
4 | CAFETERIA | 0 | 0 | 0
5 | GM OFFICE | 0 | 0 | 0
6 | BOARD ROOM | 0 | 0 | 0
7 | MEETING ROOM | 0 | 0 | 0
8 | COLLABORATIVE SPACE | 0 | 0 | 0
9 | STORAGE & IT ROOM | 0 | 0 | 0
| ELECTRICAL WORKS | 0 | 0 | 0
1 | LT SWITCHGEARS | 0 | 0 | 0
2 | CIRCUIT POINT WIRING & SWITCH FITTINGS | 0 | 0 | 0
3 | POWER CABLES AND CONDUITS | 0 | 0 | 0
4 | FITTING FIXTURES AND FANS | 0 | 0 | 0
5 | TELECOMMUNICATION SYSTEM | 0 | 0 | 0
6 | FIRE ALARM SYSTEM (ADDRESSABLE) | 0 | 0 | 0
7 | CC TV SYSTEM (IP BASED) | 0 | 0 | 0
8 | PUBLIC EVACUATION SYSTEM | 0 | 0 | 0
9 | ACCESS CONTROL SYSTEM | 0 | 0 | 0
10 | WI-FI NETWORKING SYSTEM(WIRING) | 0 | 0 | 0
11 | UL LISTED PEX TUBING | 0 | 0 | 0
12 | MISC ITEMS | 0 | 0 | 0
13 | UPS | 0 | 0 | 0
1 | HVAC WORKS | 1098000 | 231500 | 1329500
2 | Fire Fighting System | 780460 | 187800 | 968260
Total Amount |  | 1878460 | 419300 | 2297760
Add 4.5% |  |  |  | 103399.2
GRAND TOTAL |  |  |  | 2401159.2
| RUNNING BILL NO 1 |  |  | 3568560
| RUNNING BILL NO 2 |  |  | 2297760
5866320
| VARIATIONS |  |  | 1099464.4
| TOTAL |  |  | 6965784.4
| ADD 5% TAX |  |  | 348289.22
| GROSS TOTAL |  |  | 7314073.62
| RECEIVED |  |  | 6000000
| PAYABLE AMOUNT |  |  | 1314073.62

## summary
2023-10-17
SANA SAFINAS
SUMMARY OF RUNNING BILL NO 2
Sr # | Scope of work | Supply Amount | Labor Amount | Total Amount
| CIVIL ID | 0 | 0 | 0
1 | RECEPTION / WAITING AREA | 0 | 0 | 0
2 | WORKSPACE + LOBBY | 0 | 0 | 0
3 | CABIN ( 6 NOS ) | 0 | 0 | 0
4 | CAFETERIA | 0 | 0 | 0
5 | GM OFFICE | 0 | 0 | 0
6 | BOARD ROOM | 0 | 0 | 0
7 | MEETING ROOM | 0 | 0 | 0
8 | COLLABORATIVE SPACE | 0 | 0 | 0
9 | STORAGE & IT ROOM | 0 | 0 | 0
| ELECTRICAL WORKS | 0 | 0 | 0
1 | LT SWITCHGEARS | 0 | 0 | 0
2 | CIRCUIT POINT WIRING & SWITCH FITTINGS | 0 | 0 | 0
3 | POWER CABLES AND CONDUITS | 0 | 0 | 0
4 | FITTING FIXTURES AND FANS | 0 | 0 | 0
5 | TELECOMMUNICATION SYSTEM | 0 | 0 | 0
6 | FIRE ALARM SYSTEM (ADDRESSABLE) | 0 | 0 | 0
7 | CC TV SYSTEM (IP BASED) | 0 | 0 | 0
8 | PUBLIC EVACUATION SYSTEM | 0 | 0 | 0
9 | ACCESS CONTROL SYSTEM | 0 | 0 | 0
10 | WI-FI NETWORKING SYSTEM(WIRING) | 0 | 0 | 0
11 | UL LISTED PEX TUBING | 0 | 0 | 0
12 | MISC ITEMS | 0 | 0 | 0
13 | UPS | 0 | 0 | 0
1 | HVAC WORKS | 1098000 | 231500 | 1329500
2 | Fire Fighting System | 780460 | 187800 | 968260
3 | Variations Amount | 0 | 0 | 1099464.4
Total Amount |  |  |  | 3397224.4

## HVAC
BIILL OF QUANTITIES | [6 empty] | RUNNING BILL NO 2
S. No. |  | Description | Qty. | Unit | Material Rates | Labour Rates |  | Material |  |  | Labour |  |  |  | Total (Rs.)
[7 empty] | Prv Qty | Bill Qty | Total qty | Amount | Prv Qty | Bill Qty | Total qty | Amount | Amount
Section 01: Supply, Installation & Testing of Duct Works & Accessories
1 |  | Supply, fabrication, Installation & Testing of Machine Made G.I Sheet Metal Duct Work (galvanized G- 20 for internal & G-30 for external) for supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connector, access door, transformation, plenums chambers, wooden frame, anchors as per SMACNA Standards along with supports & hangers complete in all respects ready to operate as per drawings, instruction and approval of Consultant.
| a | For AC Supply / Return | 4700 | Sq.ft. | 300 | 65 | 2450 | 1800 | 4250 | 540000 | 2450 | 1800 | 4250 | 117000 | 657000
2 |  | Supply and Installation of Aluminum Faced Glass Wool insulation 1" thick for Internal ducts of different sections compete in all respect as per specifications, drawings and as per instructions of | 4700 | Sq.ft. | 140 | 50 | 2450 | 1800 | 4250 | 252000 | 2450 | 1800 | 4250 | 90000 | 342000
3 |  | Supply, Installation & Commissioning of Aluminum Fabricated, Powder Coated Air Devices for supply, return, exhaust & fresh air. including framing, hangers & supports and other accessories etc. complete in all respects ready to operate as per instruction of Consultant.
| 3.1 | Diffusers/Grilles/Registers (with Dampers)
For AC - Supply / Return Air
| a | Swirl Diffusers - 14" Dia. | 36 | Nos. | 13500 | 750 | 23 | 6 | 29 | 81000 | 23 | 6 | 29 | 4500 | 85500
| b | Square Diffusers - 12" x 12" | 2 | Nos. | 3800 | 750 | 2 |  | 2 | 0 | 2 | 0 | 2 | 1500 | 1500
| c | Square Diffusers - 9" x 9" | 5 | Nos. | 3000 | 500 |  | 5 | 5 | 15000 | 0 | 5 | 5 | 2500 | 17500
|  | For AC - Supply / Return Air | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| a | RAG - 30" x 16" | 4 | Nos. | 9500 | 750 |  | 4 | 4 | 38000 | 0 | 0 | 0 | 0 | 38000
| b | RAG - 30" x 14" | 8 | Nos. | 8250 | 750 |  | 8 | 8 | 66000 | 0 | 0 | 0 | 0 | 66000
|  | For Fresh Air | [7 empty] | 0 | 0 |  |  | 0 | 0
| a | FAG - 22" x 10" | 1 | No. | 4800 | 500 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| b | FAG - 14" x 10" | 1 | No. | 3800 | 500 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
4 |  | Supply, Installation & Commissioning of Aluminum Fabricated, Powder Coated Dampers including framing, hangers & supports and other accessories etc. complete in all respects ready to operate as per instructions and approval of Consultant.
| 4.1 | Volume Dampers
| a | 22" x 10" | 1 | No. | 6000 | 750 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| a | 14" x 10" | 1 | No. | 5500 | 750 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 4.2 | Fire Dampers | [7 empty] | 0 | 0 |  | 0 | 0 | 0
| a | 22" x 10" | 1 | No. | 6000 | 750 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| a | AIR GUIDE STEEL CRAFT SHAN INDUSTRIES ENGATECH E.A.P AIR DEVICIES | 1 | No. | [6 empty] | 0 |  | 0
Section 02: Miscellaneous Works | [10 empty] | 0
1 |  | Supply & Installation of Thermostats for AHUs along with control cables complete in all respect and ready to operate. | 8 | Nos. | 48000 | 8000 | 4 | 2 | 6 | 96000 | 4 | 2 | 6 | 16000 | 112000
2 |  | Testing, adjusting, Balancing & Commissioning of Entire HVAC system. | 1 | Job. | 0 | 75000 |  | 1 | 1 | 0 | 0 |  | 0 | 0 | 0
3 |  | Making of Shop Drawings & As-built Drawings on Auto CAD with sectional details, equipment details and their foundation details, Technical submittals and sample boards complete in all respect as per instruction of Consultant. | 1 | Job. | 10000 | 15000 |  | 1 | 1 | 10000 | 0 |  | 0 | 0 | 10000
4 |  | Supply, installation and Commissioning of items not listed in BOQ but required for complition of work to ensure satisfactory performance. (Contractor to provide list) | 1 | Job. | 0 | 0 |  | 1 | 1 | 0 | 0 |  | 0 | 0 | 0
TOTAL AMOUNT | [9 empty] | 1098000 |  |  |  | 231500 | 1329500

## Fire
BIILL OF QUANTITIES | [5 empty] | RUNNING BILL NO 2
Item No. | Description | Qty. | Unit | Material Rates | Labour Rates | Material |  |  |  | Labour |  |  |  | Total
[6 empty] | Prv Qty | Bill Qty | Total qty | Amount | Prv Qty | Bill Qty | Total qty | Amount | Amount (Rs.)
FIRE FIGHTING SERVICES
SECTION 01: SUPPLY AND INSTALLATION OF FIRE EXTINGUISHERS
1 | 5 Kg. CO2 | 5 | Nos. | 24000 | 500 | 2 | 3 | 5 | 72000 | 2 | 3 | 5 | 1500 | 73500
2 | 6 Kg. Dry Chemical Powder | 5 | Nos. | 14500 | 500 | 2 | 3 | 5 | 43500 | 2 | 3 | 5 | 1500 | 45000
SECTION 02: SUPPLY AND INSTALLATION OF FIRE SPRINKLERS
1 | Sprinkler Pendent type standard response K = 5.6 (Opening Temperature 57ºC) | 61 | Nos. | 5000 | 500 | 39 | 12 | 51 | 60000 | 39 | 12 | 51 | 6000 | 66000
2 | Sprinkler Upright type standard response K = 5.6 (Opening Temperature 57ºC) | 8 | Nos. | 4000 | 500 | 7 | 13 | 20 | 52000 | 7 | 13 | 20 | 6500 | 58500
SECTION 03: SUPPLY AND INSTALLATION OF MS PIPE WORK | [9 empty] | 0
1 | Supply & installation of MS SCH 40 pipes (seamless) with threaded & welded fittings (UL/FM) including sockets, tees, elbows, bends, reducers, unions, clamps, hangers & supports etc. making core cuts/holes (if required), painting and protection treatments on pipe. complete in all respect ready to opearte. | [8 empty] | 0
i | Dia. 1" (Threaded fitting) | 440 | Rft. | 630 | 150 | 310 | 296 | 606 | 186480 | 310 | 296 | 606 | 44400 | 230880
ii | Dia. 1-1/4" (Threaded fitting) | 100 | Rft. | 780 | 150 | 84 | 42 | 126 | 32760 | 84 | 42 | 126 | 6300 | 39060
iii | Dia. 1-1/2" (Threaded fitting) | 100 | Rft. | 910 | 200 | 80 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 0
iv | Dia. 2" (Threaded fitting) | 60 | Rft. | 1190 | 250 | 16 | 32 | 48 | 38080 | 16 | 32 | 48 | 8000 | 46080
v | Dia. 2-1/2" (Welded joints fitting) | 120 | Rft. | 1820 | 300 | 20 | 102 | 122 | 185640 | 20 | 102 | 122 | 30600 | 216240
vi | Dia. 3" (Welded joints fitting) | 120 | Rft. | 2550 | 400 | 88 | 0 | 88 | 0 | 88 | 0 | 88 | 0 | 0
SECTION 04: SUPPLY AND INSTALLATION OF PASSIVE FIRE PROTECTION | [9 empty] | 0
1 | Supply and Installation of Fire Stop Material (for passive fire fighting / smoke barrier) in all MEP openings and penetrations, either in slab or wall, complete in all respects, ready to operate as per fire stopper recommended material, and as per instruction of Consultant. | 1 | Job. | 50000 | 8000 |  | 1 | 1 | 50000 | 0 | 1 | 1 | 8000 | 58000
SECTION 05: MISCELLANEOUS ITEMS | [9 empty] | 0
1 | Providing Material Submittals and Samples for consultant's Approval. | 1 | Job. | 15000 | 5000 |  | 1 | 1 | 15000 | 0 | 1 | 1 | 5000 | 20000
2 | Making of Shop Drawings & As-Built Drawings for Consultant's Approval. | 1 | Job. | 0 | 15000 |  | 1 | 1 | 0 | 0 | 1 | 1 | 15000 | 15000
3 | Painting, Identification and Tagging as per standards. | 1 | Job. | 45000 | 30000 |  | 1 | 1 | 45000 | 0 | 1 | 1 | 30000 | 75000
4 | Testing and commissioning of entire fire fighting system as per approval of consultant. | 1 | Job. | 0 | 25000 |  | 1 | 1 | 0 | 0 | 1 | 1 | 25000 | 25000
5 | Supply, Installation and Commissioning of items not listed in BOQ but required to complete the system for satisfacotry performance. (Contractor to provide the list of item if required) | 1 | Job. | 0 |  |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0
TOTAL AMOUNT | [8 empty] | 780460 |  |  |  | 187800 | 968260