## gsk15
Pioneer Engineering Services
Measurement Sheet For Running Bill.
GSK 15 TH FLOOR DMC KARACHI.
01-08-2024
HVAC DUCTING FLOOR LAYOUT.
BOQ | Grid | FLOOR HVAC PLAN (SUPPLY,RETURN & EXHAUST AIR DUCT ) DWG NO.ACMV----- |  |  |  |  | 20 | 22 | 24 |  | NOTE WITH OUT ROUND SQUARE VAV
ITEM |  | Description | Width mm | Height mm | Length Mtr | Area Sq.Mtr. | 67.9935 | 116.6414 |  |  | ROUND NECK WITH OUT
| AHU-1 | Plenum box | 1400 | 800 | 4.3 | 18.92 | 11.5558 | 128.8151
|  | End Cap | 1400 | 800 |  | 2.24 | 99.5493 | 267.4565 | 244.5 | 611.5058
| BRANCH1 | Supply Air Duct | 1400 | 350 | 13.241 | 46.3435
|  | End Cap | 1400 | 350 |  | 0.49
| BRANCH2 | Elbow | 400 | 250 | 0.864 | 1.1232
|  | Supply Air Duct | 400 | 250 | 1.068 | 1.3884
|  | Elbow | 400 | 250 | 0.864 | 1.1232
|  | Supply Air Duct | 400 | 250 | 2.856 | 3.7128
|  | End Cap | 400 | 250 |  | 0.1
| BRANCH3 | Supply Air Duct | 500 | 300 | 1.015 | 1.624
|  | Supply Air Duct | 500 | 300 | 1.082 | 1.7312
|  | Reducer | 500 | 300 | 0.52 | 0.728
|  |  | 300 | 300
|  | Supply Air Duct | 300 | 300 | 2.35 | 2.82
|  | End Cap | 300 | 300 |  | 0.09
| BRANCH4 | Supply Air Duct | 1150 | 350 | 3.15 | 9.45
|  | Reducer | 1150 | 350 | 0.45 | 1.2375
|  |  | 900 | 350
|  | Supply Air Duct | 900 | 350 | 6.95 | 17.375
|  | Reducer | 900 | 350 | 0.45 | 1.0575
|  |  | 750 | 350
|  | Supply Air Duct | 750 | 350 | 6.875 | 15.125
|  | Reducer | 750 | 350 | 0.45 | 0.9225
|  |  | 600 | 350
|  | Supply Air Duct | 600 | 350 | 6.964 | 13.2316
|  | Reducer | 600 | 350 | 0.45 | 0.7875
|  |  | 450 | 350
|  | Supply Air Duct | 450 | 350 | 8 | 12.8
|  | End Cap | 450 | 350 |  | 0.1575
| BRANCH5 | Supply Air Duct | 1150 | 350 | 0.932 | 2.796
|  | Supply Air Duct | 1150 | 350 | 5.75 | 17.25
|  | Elbow | 1150 | 350 | 2.121 | 6.363
|  | Supply Air Duct | 1150 | 350 | 1.063 | 3.189
|  | Reducer | 1150 | 350 | 0.95 | 2.755
|  |  | 1000 | 400
|  | Supply Air Duct | 1000 | 400 | 13.578 | 38.0184
|  | Reducer | 1000 | 400 | 0.45 | 1.1025
|  |  | 700 | 350
|  | Supply Air Duct | 700 | 350 | 13 | 27.3
|  | Elbow | 700 | 350 | 1.571 | 3.2991
|  | Reducer | 700 | 350 | 0.64 | 1.248
|  |  | 600 | 300
TOTAL | [5 empty] | 257.8994
|  | Supply Air Duct | 600 | 300 | 2.551 | 4.5918
|  | Reducer | 600 | 300 | 0.45 | 0.72
|  |  | 400 | 300
|  | Half set | 400 | 300 | 1.75 | 2.45
|  | Supply Air Duct | 400 | 300 | 0.992 | 1.3888
|  | Reducer | 400 | 300 | 0.3 | 0.39
|  |  | 400 | 200
|  | Supply Air Duct | 400 | 200 | 3.386 | 4.0632
|  | Elbow | 400 | 200 | 0.864 | 1.0368
|  | Supply Air Duct | 400 | 200 | 0.79 | 0.948
|  | End Cap | 400 | 300 |  | 0.12
| BRANCH6 | Supply Air Duct | 400 | 200 | 0.73 | 0.876
|  | End Cap | 400 | 200 |  | 0.08
| BRANCH7 | Supply Air Duct | 1250 | 350 | 3.183 | 10.1856
|  | Reducer | 1250 | 350 | 0.442 | 1.3702
|  |  | 1150 | 350
|  | Supply Air Duct | 1150 | 350 | 2.69 | 8.07
|  | Elbow | 1150 | 350 | 2 | 6
|  | Reducer | 1150 | 350 | 1.2 | 3.48
|  |  | 1000 | 400
|  | Supply Air Duct | 1000 | 400 | 9.7 | 27.16
|  | Reducer | 1000 | 400 | 0.4 | 1.1
|  |  | 950 | 400
|  | Supply Air Duct | 950 | 400 | 1.393 | 3.7611
|  | Reducer | 950 | 400 | 0.4 | 1.06
|  |  | 900 | 400
|  | Supply Air Duct | 900 | 400 | 13 | 33.8
|  | Elbow | 900 | 400 | 2.042 | 5.3092
|  | Supply Air Duct | 900 | 400 | 6.105 | 15.873
|  | End Cap | 900 | 400 |  | 0.36
| BRANCH8 | Elbow | 250 | 150 | 0.55 | 0.44
|  | Supply Air Duct | 250 | 150 | 0.6 | 0.48
|  | Half set | 250 | 150 | 0.75 | 0.6
|  | Supply Air Duct | 250 | 150 | 1.86 | 1.488
|  | End Cap | 250 | 150 |  | 0.0375
| BRANCH9 | Supply Air Duct | 300 | 100 | 1.533 | 1.2264
|  | Elbow | 300 | 100 | 0.707 | 0.5656
|  | Supply Air Duct | 300 | 200 | 4.513 | 4.513
|  | End Cap | 300 | 200 |  | 0.06
| BRANCH10 | Supply Air Duct | 250 | 150 | 1.509 | 1.2072
|  | Elbow | 250 | 150 | 0.55 | 0.44
|  | Supply Air Duct | 250 | 150 | 3.776 | 3.0208
|  | Elbow | 250 | 150 | 0.55 | 0.44
|  | Supply Air Duct | 250 | 150 | 1.421 | 1.1368
|  | End Cap | 250 | 150 |  | 0.0375
| BRANCH11 | Elbow | 250 | 150 | 0.55 | 0.44
|  | Supply Air Duct | 250 | 150 | 1.288 | 1.0304
|  | Elbow | 250 | 150 | 0.55 | 0.44
|  | Supply Air Duct | 250 | 150 | 1.097 | 0.8776
|  | End Cap | 250 | 150 |  | 0.0375
TOTAL | [5 empty] | 152.712
| BRANCH12 | Elbow | 300 | 150 | 0.786 | 0.7074
|  | Supply Air Duct | 300 | 150 | 1.308 | 1.1772
|  | Elbow | 300 | 150 | 0.786 | 0.7074
|  | Supply Air Duct | 300 | 150 | 1.015 | 0.9135
|  | Elbow | 300 | 150 | 0.786 | 0.7074
|  | Supply Air Duct | 300 | 150 | 1.227 | 1.1043
|  | End Cap | 300 | 150 |  | 0.045
| BRANCH13 | Elbow | 300 | 200 | 0.786 | 0.786
|  | Supply Air Duct | 300 | 200 | 1.315 | 1.315
|  | Elbow | 300 | 200 | 0.786 | 0.786
|  | Supply Air Duct | 300 | 200 | 3.35 | 3.35
|  | Elbow | 300 | 200 | 0.786 | 0.786
|  | Supply Air Duct | 300 | 200 | 1.98 | 1.98
|  | End Cap | 300 | 200 |  | 0.06
| BRANCH14 | Supply Air Duct | 250 | 150 | 0.764 | 0.6112
|  | Elbow | 250 | 150 | 0.589 | 0.4712
|  | Supply Air Duct | 250 | 150 | 7.106 | 5.6848
|  | End Cap | 250 | 150 |  | 0.0375
| BRANCH15 | Supply Air Duct | 1000 | 350 | 0.45 | 1.215
|  | Supply Air Duct | 1000 | 350 | 4.568 | 12.3336
|  | Supply Air Duct | 400 | 350 | 1.2 | 1.8
|  | Supply Air Duct | 400 | 350 | 4.582 | 6.873
|  | End Cap | 400 | 350 |  | 0.14
|  | Supply Air Duct | 600 | 350 | 1.6 | 3.04
|  | Supply Air Duct | 600 | 350 | 1.869 | 3.5511
|  | Reducer | 600 | 350 | 0.45 | 0.765
|  |  | 400 | 350
|  | Supply Air Duct | 400 | 350 | 8.438 | 12.657
|  | End Cap | 400 | 350 |  | 0.14
| BRANCH16 | Supply Air Duct | 850 | 500 | 1.716 | 4.6332
|  | Supply Air Duct | 400 | 250 | 3.112 | 4.0456
|  | Elbow | 400 | 250 | 0.785 | 1.0205
|  | Supply Air Duct | 400 | 250 | 1.131 | 1.4703
|  | Elbow | 400 | 250 | 0.785 | 1.0205
|  | Supply Air Duct | 400 | 250 | 4.137 | 5.3781
|  | End Cap | 400 | 250 |  | 0.1
| BRANCH17 | Supply Air Duct | 250 | 200 | 2.361 | 2.1249
|  | Reducer | 250 | 200 | 0.37 | 0.3515
|  |  | 300 | 200
| BRANCH18 | Supply Air Duct | 550 | 250 | 1.203 | 1.9248
|  | Reducer | 550 | 250 | 0.38 | 0.589
|  |  | 500 | 250
|  | Elbow | 500 | 250 | 0.98 | 1.47
|  | Supply Air Duct | 500 | 250 | 2.957 | 4.4355
|  | End Cap | 500 | 250 |  | 0.125
| BRANCH19 | Supply Air Duct | 500 | 200 | 1.164 | 1.6296
|  | Elbow | 500 | 200 | 1.021 | 1.4294
|  | Supply Air Duct | 500 | 200 | 1.573 | 2.2022
|  | End Cap | 500 | 200 |  | 0.1
|  | Supply Air Duct | 500 | 150 | 3.33 | 4.329
TOTAL | [5 empty] | 102.1237
|  | Elbow | 500 | 150 | 1.021 | 1.3273
|  | Supply Air Duct | 500 | 150 | 0.806 | 1.0478
|  | End Cap | 500 | 150 |  | 0.075
| BRANCH20 | Supply Air Duct | 300 | 250 | 0.15 | 0.165
|  | Elbow | 300 | 250 | 0.628 | 0.6908
|  | Supply Air Duct | 300 | 250 | 1.18 | 1.298
|  | End Cap | 300 | 250 |  | 0.075
|  | Supply Air Duct | 400 | 250 | 2.869 | 3.7297
|  | End Cap | 400 | 250 |  | 0.1
TOTAL | [5 empty] | 8.5086
| 2-FCU-ROOM | Plenum box | 1100 | 300 | 0.4 | 1.12
|  | Plenum box | 1100 | 300 | 0.4 | 1.12
|  | Supply Air Duct | 500 | 350 | 4.112 | 6.9904
|  | Reducer | 500 | 350 | 0.55 | 0.935
|  |  | 650 | 200
| RAD | Plenum box | 1100 | 300 | 0.275 | 0.77
|  | Plenum box | 1100 | 300 | 0.275 | 0.77
|  | Return Air Duct | 500 | 350 | 4.188 | 7.1196
|  | Reducer | 500 | 350 | 0.55 | 0.935
|  |  | 650 | 200
TOTAL | [5 empty] | 19.76
| FCU-lift-lobby | Reducer | 1100 | 300 | 0.4 | 0.88
|  |  | 550 | 250
|  | Supply Air Duct | 550 | 250 | 0.936 | 1.4976
|  | Reducer | 550 | 250 | 0.3 | 0.45
|  |  | 450 | 250
|  | Supply Air Duct | 450 | 250 | 6.986 | 9.7804
|  | End Cap | 450 | 250 |  | 0.1125
TOTAL | [5 empty] | 12.7205
| EAD | Exhaust Air Duct | 400 | 250 | 0.427 | 0.5551
| 1 | Reducer | 400 | 250 | 0.2 | 0.24
|  |  | 350 | 200
|  | Exhaust Air Duct | 350 | 200 | 0.358 | 0.3938
|  | Elbow | 350 | 200 | 0.707 | 0.7777
|  | Exhaust Air Duct | 350 | 200 | 2.289 | 2.5179
|  | Reducer | 350 | 200 | 0.3 | 0.27
|  |  | 200 | 150
|  | Exhaust Air Duct | 200 | 150 | 0.33 | 0.231
|  | Elbow | 200 | 150 | 0.55 | 0.385
|  | Exhaust Air Duct | 200 | 150 | 5.462 | 3.8234
|  | Elbow | 200 | 150 | 0.4 | 0.28
|  | Exhaust Air Duct | 200 | 150 | 0.411 | 0.2877
|  | End Cap | 200 | 150 |  | 0.03
| 2 | Exhaust Air Duct | 200 | 150 | 0.926 | 0.6482
|  | Elbow | 200 | 150 | 0.471 | 0.3297
|  | Exhaust Air Duct | 200 | 150 | 0.358 | 0.2506
|  | Reducer | 200 | 150 | 0.2 | 0.13
|  |  | 200 | 100
|  | Exhaust Air Duct | 200 | 100 | 0.552 | 0.3312
|  | Elbow | 200 | 100 | 0.314 | 0.1884
|  | Exhaust Air Duct | 200 | 100 | 0.383 | 0.2298
|  | End Cap | 200 | 150 |  | 0.03
| 3 | Exhaust Air Duct | 200 | 100 | 1.283 | 0.7698
|  | End Cap | 200 | 100 |  | 0.02
| 4 | Exhaust Air Duct | 250 | 150 | 0.869 | 0.6952
|  | Elbow | 250 | 150 | 0.628 | 0.5024
|  | Exhaust Air Duct | 250 | 150 | 0.635 | 0.508
|  | End Cap | 250 | 150 |  | 0.0375
| 5 | Exhaust Air Duct | 200 | 100 | 0.864 | 0.5184
|  | End Cap | 200 | 100 |  | 0.02
|  | Exhaust Air Duct | 250 | 150 | 0.635 | 0.508
| 8nos | Exhaust Air Duct | 150 | 150 | 0.3 | 1.44
| 1nos | Exhaust Air Duct | 100 | 100 | 0.3 | 0.0942
TOTAL | [5 empty] | 17.043
| 5 NOS | Grill neck | 1000 | 200 | 0.43 | 5.16
| 1 NOS | Plenum box | 300 | 250 | 3.5 | 3.85
|  | End Cap | 300 | 250 |  | 0.15
| 2 NOS | Grill neck | 500 | 300 | 0.375 | 1.2
| 2 NOS | Round Neck | 350 | 350 | 0.15 | 0.35381
| 5 NOS | Grill neck | 1000 | 200 | 0.43 | 5.16
| 1 NOS | Round Neck | 300 | 300 | 0.15 | 0.14152
| 2 NOS | Sad | 225 | 225 | 0.3 | 0.54
| 1 NOS | Plenum box | 300 | 250 | 1.1 | 1.21
|  | End Cap | 300 | 250 |  | 0.15
| 1 NOS | Plenum box | 300 | 250 | 2.2 | 2.42
|  | End Cap | 300 | 250 |  | 0.15
| 1 NOS | Plenum box | 300 | 250 | 1.25 | 1.375
|  | End Cap | 300 | 250 |  | 0.15
| 1 NOS | Plenum box | 300 | 250 | 1.05 | 1.155
|  | End Cap | 300 | 250 |  | 0.15
| 1 NOS | Plenum box | 300 | 250 | 1.65 | 1.815
|  | End Cap | 300 | 250 |  | 0.15
| 1 NOS | Plenum box | 300 | 250 | 1.65 | 1.815
|  | End Cap | 300 | 250 |  | 0.15
| 1 NOS | Plenum box | 300 | 250 | 2.1 | 2.31
|  | End Cap | 300 | 250 |  | 0.15
| 3 NOS | Grill neck | 900 | 300 | 0.375 | 2.7
| 1 NOS | Plenum box | 300 | 250 | 3.5 | 3.85
|  | End Cap | 300 | 250 |  | 0.15
| 4 NOS | SAD | 450 | 450 | 0.3 | 2.16
| 2 NOS | Round Neck | 350 | 350 | 0.15 | 0.35381
| 2 NOS | SAD | 375 | 375 | 0.3 | 1.8
TOTAL | [5 empty] | 40.7191
GRAND TOTAL | [5 empty] | 611.4863 |  | 586 as per dwg

## fire pipe
Pioneer Engineering Services
Measurement Sheet For Running Bill.
GSK 15 TH FLOOR DMC KARACHI.
01-08-2024
FIRE FIGHTING FLOOR LAYOUT. | [8 empty] | AS PER DWG
BOQ | Grid | Description | LENGTH MTR |  | BOQ | Grid | Description | Length | FIRE PIPE 25mmDIA Drop
ITEM |  |  |  |  | ITEM |  |  | mm |  | 64.8
1 |  | FIRE PIPE 75mmDIA | 40.764 |  |  | 1 | 75mm dia | 234
1 |  | FIRE PIPE 65mmDIA | 14.291 |  |  | 1 | 75mm dia | 441
2 |  | FIRE PIPE 50mmDIA | 21.326 |  |  | 1 | 75mm dia | 3409
3 |  | FIRE PIPE 40mmDIA | 40.661 |  |  | 1 | 75mm dia | 25179
4 |  | FIRE PIPE 32mmDIA | 43.727 |  |  | 2 | 65mm dia | 2654
5 |  | FIRE PIPE 25mmDIA | 171.977 |  |  | 3 | 50mm dia | 3187
6 |  | FIRE PIPE 25mmDIA Drop | 64.8 |  |  | 3 | 50mm dia | 3699
[6 empty] | 4 | 40mm dia | 1631
[6 empty] | 5 | 32mm dia | 2996
BOQ | Grid | Description | QTY |  |  | 6 | 25mm dia | 2075
ITEM | [5 empty] | 6 | 25mm dia | 2619
1 |  | FIRE SPRINKLER PENDENT | 48 |  |  | 6 | 25mm dia | 759
2 |  | FIRE SPRINKLER UPRIGHT | 60 |  |  | 6 | 25mm dia | 458
[6 empty] | 7 | 25mm dia | 2606
[6 empty] | 7 | 25mm dia | 4075
BOQ | Grid | Description | QTY |  |  | 8 | 32mm dia | 1579
ITEM | [5 empty] | 9 | 25mm dia | 5328
1 |  | 11/2" TEST DRAIN PIPE |  |  |  | 9 | 25mm dia | 461
[6 empty] | 10 | 32mm dia | 1641
[6 empty] | 10 | 25mm dia | 5353
[6 empty] | 10 | 25mm dia | 497
[6 empty] | 11 | 32mm dia | 1641
[6 empty] | 11 | 25mm dia | 4877
[6 empty] | 12 | 40mm dia | 1565
[6 empty] | 12 | 32mm dia | 2712
[6 empty] | 12 | 25mm dia | 3580
[6 empty] | 12 | 25mm dia | 1494
[6 empty] | 13 | 32mm dia | 1565
[6 empty] | 13 | 32mm dia | 2712
[6 empty] | 13 | 25mm dia | 2223
[6 empty] | 13 | 25mm dia | 476
[6 empty] | 13 | 25mm dia | 472
[6 empty] | 13 | 25mm dia | 468
[6 empty] | 14 | 40mm dia | 1565
[6 empty] | 14 | 32mm dia | 2712
[6 empty] | 14 | 25mm dia | 3580
[6 empty] | 14 | 25mm dia | 1494
[6 empty] | 14 | 25mm dia | 475
[6 empty] | 14 | 25mm dia | 472
[6 empty] | 14 | 25mm dia | 468
[6 empty] | 15 | 40mm dia | 1558
[6 empty] | 15 | 32mm dia | 2712
[6 empty] | 15 | 25mm dia | 3580
[6 empty] | 15 | 25mm dia | 1494
[6 empty] | 16 | 32mm dia | 1575
[6 empty] | 16 | 32mm dia | 2712
[6 empty] | 16 | 25mm dia | 2213
[6 empty] | 16 | 25mm dia | 475
[6 empty] | 16 | 25mm dia | 471
[6 empty] | 16 | 25mm dia | 467
[6 empty] | 17 | 40mm dia | 1558
[6 empty] | 17 | 32mm dia | 2712
[6 empty] | 17 | 25mm dia | 3580
[6 empty] | 17 | 25mm dia | 1494
[6 empty] | 18 | 25mm dia | 1647
[6 empty] | 19 | 25mm dia | 1632
[6 empty] | 19 | 25mm dia | 900
[6 empty] | 20 | 25mm dia | 2176
[6 empty] | 20 | 25mm dia | 606
[6 empty] | 21 | 25mm dia | 1138
[6 empty] | 21 | 25mm dia | 900
[6 empty] | 22 | 25mm dia | 1640
[6 empty] | 23 | 25mm dia | 1627
[6 empty] | 23 | 25mm dia | 287
[6 empty] | 24 | 25mm dia | 1627
[6 empty] | 24 | 25mm dia | 287
[6 empty] | 25 | 25mm dia | 1617
[6 empty] | 25 | 25mm dia | 287
[6 empty] | 26 | 40mm dia | 3370
[6 empty] | 26 | 40mm dia | 1921
[6 empty] | 26 | 40mm dia | 1246
[6 empty] | 26 | 32mm dia | 2893
[6 empty] | 26 | 25mm dia | 4313
[6 empty] | 26 | 25mm dia | 582
[6 empty] | 26 | 25mm dia | 356
[6 empty] | 27 | 40mm dia | 1214
[6 empty] | 27 | 40mm dia | 813
[6 empty] | 27 | 40mm dia | 3971
[6 empty] | 27 | 32mm dia | 2815
[6 empty] | 27 | 25mm dia | 3696
[6 empty] | 27 | 25mm dia | 1434
[6 empty] | 27 | 25mm dia | 520
[6 empty] | 28 | 75mm dia | 9101
[6 empty] | 29 | 50mm dia | 7407
[6 empty] | 30 | 32mm dia | 3570
[6 empty] | 31 | 25mm dia | 1661
[6 empty] | 31 | 25mm dia | 838
[6 empty] | 32 | 25mm dia | 963
[6 empty] | 33 | 25mm dia | 2672
[6 empty] | 33 | 25mm dia | 322
[6 empty] | 34 | 25mm dia | 1031
[6 empty] | 35 | 25mm dia | 3766
[6 empty] | 35 | 25mm dia | 899
[6 empty] | 36 | 25mm dia | 534
[6 empty] | 36 | 25mm dia | 1961
[6 empty] | 37 | 25mm dia | 4096
[6 empty] | 38 | 40mm dia | 5939
[6 empty] | 39 | 25mm dia | 4270
[6 empty] | 40 | 25mm dia | 2668
[6 empty] | 41 | 25mm dia | 2668
[6 empty] | 42 | 25mm dia | 547
[6 empty] | 43 | 50mm dia | 1475
[6 empty] | 43 | 50mm dia | 2135
[6 empty] | 44 | 40mm dia | 2144
[6 empty] | 45 | 25mm dia | 3468
[6 empty] | 45 | 25mm dia | 470
[6 empty] | 46 | 25mm dia | 3211
[6 empty] | 47 | 25mm dia | 607
[6 empty] | 48 | 25mm dia | 325
[6 empty] | 49 | 25mm dia | 3137
[6 empty] | 50 | 25mm dia | 4038
[6 empty] | 50 | 25mm dia | 1140
[6 empty] | 51 | 25mm dia | 612
[6 empty] | 52 | 25mm dia | 2598
[6 empty] | 53 | 65mm dia | 4815
[6 empty] | 53 | 65mm dia | 4422
[6 empty] | 54 | 50mm dia | 1923
[6 empty] | 54 | 25mm dia | 458
[6 empty] | 55 | 40mm dia | 3924
[6 empty] | 55 | 25mm dia | 467
[6 empty] | 56 | 32mm dia | 1210
[6 empty] | 57 | 25mm dia | 5214
[6 empty] | 57 | 25mm dia | 1312
[6 empty] | 58 | 25mm dia | 2172
[6 empty] | 59 | 32mm dia | 826
[6 empty] | 59 | 25mm dia | 1713
[6 empty] | 59 | 25mm dia | 853
[6 empty] | 59 | 25mm dia | 997
[6 empty] | 60 | 40mm dia | 4607
[6 empty] | 60 | 40mm dia | 1334
[6 empty] | 61 | 32mm dia | 2527
[6 empty] | 62 | 25mm dia | 2550
[6 empty] | 63 | 25mm dia | 2941
[6 empty] | 64 | 25mm dia | 2941
[6 empty] | 65 | 40mm dia | 236
[6 empty] | 65 | 40mm dia | 565
[6 empty] | 66 | 32mm dia | 1117
[6 empty] | 67 | 25mm dia | 6565
[6 empty] | 68 | 25mm dia | 6936
[6 empty] | 1 | 75mm dia | 2400
[6 empty] | 2 | 65mm dia | 2400
[6 empty] | 3 | 50mm dia | 1500
[6 empty] | 4 | 40mm dia | 1500
[6 empty] | 5 | 32mm dia | 1500
[6 empty] | 6 | 25mm dia | 3000

## chwsr pipe
Pioneer Engineering Services
Measurement Sheet For Running Bill.
GSK 15 TH FLOOR DMC KARACHI.
01-08-2024
CHWSR PIPE FLOOR LAYOUT. |  |  |  |  | Chwsr Pipe 25mmDIA | Chwsr PIPE 20mmDIA | Cwsr Pipe 20mmDIA |  | AS PER DWG
BOQ | Grid | Description | LENGTH MTR |  | 843 | 1860 | 546 | C-drain Pipe 20mmDIA
ITEM |  |  |  |  | 9025 | 6908 | 1697 | 325 |  | C-drain Pipe 25mmDIA
1 | FCU | Chwsr Pipe 20mmDIA | 42.62 |  | 9868 | 8676 | 4404 | 3800 |  | 1587
2 | WCPU | Cwsr Pipe 20mmDIA | 38.65 |  |  | 1590 | 8624 | 300 |  | 3600
3 | FCU-LIFT | Chwsr Pipe 25mmDIA | 22.74 |  |  | 778 | 1431 | 4996 |  | 5187
[6 empty] | 19812 | 624 | 1171
[7 empty] | 17326 | 9025
624
699
20940
BOQ | Grid | Description | LENGTH MTR
ITEM
1 |  | C-drain Pipe 20mmDIA | 20.94
2 |  | C-drain Pipe 25mmDIA | 5.187

## Sheet1
Pioneer Engineering Services
Measurement Sheet For Running Bill.
GSK 15 TH FLOOR DMC KARACHI.
01-08-2024
BOQ | Grid | Description | QTY
ITEM
| 2 NOS | FCU UNIT VALVE ACCESSORIES
|  | GATE VALVE | 4
|  | STRAINER VALVE | 2
|  | BALANCING VALVE | 2
|  | 2WAY MOTORIZED VALVE | 2
|  | THERMOMETER | 4
|  | PRESSURE GAUGE | 4
|  | AIR VENT | 2
|  | DRAIN POINT | 2
|  | FLEXIBLE PIPE CONNECTOR | 4
| 1 NOS | WCPU UNIT VALVE ACCESSORIES
|  | GATE VALVE | 2
|  | STRAINER VALVE | 1
|  | BALANCING VALVE | 1
|  | 2WAY MOTORIZED VALVE | 1
|  | PRESSURE SWITCH | 1
|  | THERMOMETER | 2
|  | PRESSURE GAUGE | 2
|  | AIR VENT | 1
|  | DRAIN POINT | 1
|  | FLEXIBLE PIPE CONNECTOR | 2