## Sheet1
Precurement Schedule GSK Office DMC Karachi
Description | Approved Brand | Approval Stauts | Delivery
HVAC
Hangers & supports | NORM | Approved | Procured
Ducting | ISL | Approved | Fabrication in process
Duct Insulation | AEROFOAM | Approved | 2 Weeks
VAVs Boxes | IMS | Approved | 6-8 Weeks
MS Pipe | PROTEK | Approved | Procured
Valves / Stainers | WATTS | Approved | 2 Week
Pipe Insulation | FORTEFLEX | Approved | 2 Weeks
Condensate Drain Pipe with insulation | DADEX | Approved | Procured
Air devices | Raees Brothers | Not submitted | Fabrication in process
Paints / Identification | BERGER | Approved | Procured
Fan coil Unit - Lift Lobby | Trane | Awaiting for Approval | 6-8 Weeks
Fan coil Unit | Danhum Bush | Approved | 12-14 Weeks
Water cooled package unit | Danhum Bush | Approved | 12-14 Weeks
Plumbing Work
Hangers supports and related fittings | norm | Approved | Procured
PPRC Pipe & Fittings | DADEX | Approved | Procured
UPVC Pipe & Fittings | DADEX | Approved | Procured
Plumbing fixtures |  | Not submitted | 6-8 Weeks
FIRE Fighting
MS Pipe | IIL | Approved | Procured
Sprinklers | LIFFECO | Approved | 6-8 Weeks
Extinghuishers | FIREX | Approved | 6-8 Weeks
Paint / Identification | BERGER | Approved | Procured