## HVAC
M/S Dawat-e-Hadiyah Burhani Mahal |  |  |  | Date | 2024-02-12
Mciver Road, Karachi |  |  |  | Invoice # | 335
|  |  |  | NTN # | 4312149-7
Invoice
D11 - North Walk Shopping Mall
S. # | Description | Unit | Qty | Rate | Amount
1 | Supply of jazuki nozzels | Nos | 12 | 6350 | 76200
2 | Supply of PU insulation 50mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 2019 | 690 | 1393110
3 | Supply of Aluminium tapes. | Job | 1 | 35000 | 35000
4 | Supply of canvas cloth over ducts. | Job | 1 | 45000 | 45000
5 | Supply of Painting & Identification. | Job | 1 | 30000 | 30000
Total Amount Rs |  |  |  |  | 76200
[7 empty] | HVAC SCOPE | 5455410 | FIRE SCOPE | 912446
For PIONEER SERVICES. | [6 empty] | Received | 2874349 | Received | 446950
[8 empty] | 2581061 |  | 465496
[7 empty] | Received | 881091 | Received | 191350
[8 empty] | 1699970 |  | 274146
1974116
Work Order
[7 empty] | HVAC | 4299115 |  | 4393740
[7 empty] | FIRE | 912325
5211440
FINAL BILL
[5 empty] | #REF! |  | Material | 5455410
[5 empty] | #REF! |  | Labour | 1226592
[5 empty] | #REF! |  | TOTAL | 6682002
#REF!
[5 empty] | #REF! |  | Material | 500200
[5 empty] | #REF! |  | Labour | 239899
[7 empty] | TOTAL | 740099
[7 empty] | GRAND TOTAL | 7422101
[7 empty] | PAYABLE AMOUNT | 2210661
AMOUNT INCREASED DUE THE FOLLOWING
A) KITCHENS EXHAUST DUCTINGS AND INSULATION
B) INDOOR AREA GLASSWOOL INSULATION REPLACED WITH XLPE INSULATION
C) OUT DOOR DUCT GLASSWOOL INSULATION REPLACED WITH PU INSULATION
D) DUCT AND CLADDING INCREASED
PIONEER SERVICES

## working
|  |  | Discount | 4.811%
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
Discount | 88065.0403 | 18198.9538
Sub Total Amount | 1742534.9597 | 360101.0462
SRB 13% on Labour | 0 | 46813.136
Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
SRB 13% on Labour | 0 | 49179
Total Amount | 1830600 | 427479
Discount | 88065.0403 | 20564.8177
Grand Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419