## HVAC
PS/FTC/087/01/25 | [6 empty] | 20 Jan 25
Attn: Mr. Kamran Hassan
Invoice for HVAC rehabilitation work - 10-A Floor FTC Building Karachi
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
1 | Removal of existing G.I Sheet metal duct inluding contant volume damper controller, hangers supports and air devices. | Job | 1 | 0 | 30000 | 0 | 30000 | 385000 | 454300
2 | Supply and installation of G.I Sheet metal duct plenum with nut bolt gasket hangers supports etc complete in all respect. | SFT | 486 | 470 | 70 | 228420 | 34020
3 | Supply and installation of glass wool insulation 25mm thick 24 Kg with canvas cloth antifungus paint complete in all respect. | SFT | 486 | 225 | 50 | 109350 | 24300
4 | Supply and installation of air devices for return and supply air. 12 x 12 | Nos | 8 | 4500 | 1000 | 36000 | 8000
5 | Supply and installation of flexible duct 6" dia | Rft | 100 | 400 | 100 | 40000 | 10000
6 | Installation of removed diffuser. | Job | 1 | 0 | 15000 | 0 | 15000
7 | Supply and installation of hangers and supports. | Job | 1 | 20000 | 10000 | 20000 | 10000
8 | Testing and commissioning | Job | 1 |  | 20000 | 0 | 20000
Total Amount Rs | [5 empty] | 433770 | 151320
SST 15% on Labour | [5 empty] | 0 | 22698
Total after SRB | [5 empty] | 433770 | 174018
Grand Total Amount Rs | [6 empty] | 607788
Received from Civil contractor Rs | [6 empty] | 200000
Net payable | [6 empty] | 407788
For PIONEER SERVICES.
PIONEER SERVICES

## for working
2025-01-20
Attn: Mr. Jameel Baig
Bill for HVAC work at Jameel Baig Residence, Phase 8 Karachi
S. # | Description | Material Rate | Labour Rate | Overhead Profit & Transportation 25% | Tax 7.5% | Unit | Qty | Amount
A | B | C | D | E | F |  | H | I
|  |  |  | (C + D ) x 20% | (C + D + E) x 7.5% |  |  | (C + D + E + F) x H
1 | Air Conditioning Units
| Installation & Commissioning of Split Units. | 0 | 6500 |  |  | Nos | 34 | 221000
2 | Refrigerent Pipes
Supply & installation of refrigerant copper pipes .
| 5/8" Dia | 275 | 80 | 88.75 |  | Rft | 1500 | 665625
| 3/8" Dia | 161 | 80 | 60.25 |  | Rft | 1500 | 451875
| 1/2" Dia | 209 | 80 | 72.25 |  | Rft | 1500 | 541875
| 1/4" Dia | 117 | 80 | 49.25 |  | Rft | 1500 | 369375
3 | Refrigerent Pipes Insulation
Supply & installation of refrigerant copper pipes .
| 5/8" Dia | 91 | 65 | 39 |  | Rft | 1500 | 292500
| 3/8" Dia | 73 | 65 | 34.5 |  | Rft | 1500 | 258750
| 1/2" Dia | 81 | 65 | 36.5 |  | Rft | 1500 | 273750
| 1/4" Dia | 60 | 65 | 31.25 |  | Rft | 1500 | 234375
4 | Drain Piping
Supply, Installation, testing & Commissioning of UPVC Class D pipes & fittings for condensate drain system
| 1" Dia | 112 | 80 | 48 |  | Rft | 1500 | 360000
| 3/4" Dia | 84 | 80 | 41 |  | Rft | 1000 | 205000
5 | Drain Piping Insulation
Supply, Installation, testing & Commissioning of UPVC pipes insulation.
| 1" Dia | 142 | 65 | 51.75 |  | Rft | 1500 | 388125
| 3/4" Dia | 129 | 65 | 48.5 |  | Rft | 1000 | 242500
6 | Supply and installation of control wiring. | 10350 | 0 | 2587.5 |  | Coil | 6 | 77625
7 | Insulation tapes (wrapping tape) | 4800 | 0 | 1200 |  | Ctn | 6 | 36000
8 | Beam and wall cutting | 0 | 125000 |  |  | Job | 1 | 125000
Total Amount Rs. | [7 empty] | 4743375
Note: Supplier quotations attached.
For PIONEER ENGINEERING SERVICES.
M. Bilal Habib ur Rehman | [8 empty] | -4743375